## Sheet1
Implementing EOL in Brazil
Areas to Cover | Project | Main Items to Cover | Deliverables Situation | Task | Due Date | Status
| Accountability |  |  | Accountability
AFE Request or | Remi Collonges | Kishkill opted for project number only | Project Number (Odair) | Remi Collonges | 2000-05-15 | In Process
Project Number Request
Product list | Remi Collonges | Marketed Products | Direct Sales to provide list of products | Don Black | 2000-05-12 | In Process
| Ricardo Lisboa |  | ProDUCT Description | Remi Collonges | 2000-05-12 | Done
|  | Traded Products (Power) | Dave Forster/Mario Cardoso to approve Project Description | Dave Forster |  | In Process
Customers |  | Direct Sales customer list | Direct Sales to provide list | Don Black | 2000-05-12 | In Process
|  | Power Trading Customer List |  | Remi Collonges/ Ricardo L. | 2000-05-10 | Done
|  | Name and Contacts for Power | Luis Berti has started collecting | Ricardo Lisboa / Luis Berti | 2000-05-10 | In Process
IT | Steve Nagy | Increase Bandwidth | Collecting bids from companies | Julie Ramos | 2000-06-30 | In Process
| Julie Ramos | Install Citrix, other necessary softwares
IT Support
Back Office | Steve Nagy | EnPower or Spreadsheet |  | Scott Mills |  | In Process
| Scott Mills | Confirmation and Settlement |  | Scott Mills |  | In Process
|  | Accounting and Invoicing |  | Scott Mills |  | In Process
|  | Cash Balance Management |  | Scott Mills |  | In Process
|  |  | Negotiating with Mike McConnell earlier implementation date | Steve Nagy |  | In Process
Legal | Andrea Bertone | Legal Opinion on local enforceability of Online trading | Pinheiro Neto appointed as local counsel | Andrea Bertone |  | Done
|  | Master Agreement, Password application , General | Mark Taylor to send questioner to submit to local counsel | Mark Taylor | 2000-05-08 | In Process
|  | Terms and Conditions | Local counsel to produce opinion | Andrea Bertone
Tax | Ricardo Lisboa | Pis/Cofins, ICMS, CPMF | Local law firm hired as council
| Remi Collonges |  | Lacaz Martins, Halembeck, Pereira Neto, Gurevich & Shoueiri | Sami Arap |  | Done
|  |  | Local counsel to produce opinion | Sami Arap | 2000-05-12 | In Process
Regulatory |  | Regulatory environment | Initializing conversations with Jose Bestard | José Bestard |  | In process
Help Desk | Julie Ramos | Help desk to be listed on advertising material to | Number Selected |  |  | Done
|  | provide support to customers | Resource Selection |  |  | Initialized
|  | Training | Traning |  |  | Initialized
Marketing and Advertising Material | Denise Macedo | Leaflets and other material to distribute to potential | Advertising material : Required | Ricardo Lisboa |  | In Process
| Ricardo Lisboa | customers | Advertising material printing : in Houston | Mario Cardoso
|  | Orchestrate press campaign | Press Release / Advertising Campaign | Denise Macedo
Business Plan | Remi Collonges | Identify business potential volume and profits | Initial Presentation |  |  | Done
| Ricardo Lisboa | Competition | Possible updates for Jim and Diomedes and or Enron Corp. | Remi Collonges/Joe Kishkill
Trading Limits | Remi Collonges | Guidelines for Power Trading | Initial trading will be governed by ESA existing Trading Limits |  |  | Done
BA and SP to coordinate on scenario development in establishing "internal trading limits"
Front Office | Remi Collonges | Test Power Curves and Stack Manager | Build credible, market based power curves as well as proper fundamental analysis and | Dave Rosemberg / Remi Coll
| Dave M. Rosemberg | Test Applications | curve generation tools
Credit | Remi Collonges | Prepare Preapproved list | Rod Nelson received Financial Statements for 18 counterparts |  | 2000-04-30 | Done
| Ricardo Lisboa | Provide Financial Statements to selected customers | Preapproved customers with specific limits | Rod Nelson | 2000-05-15 | In Process