## Summary by BU
Enron - Adaytum Work Plan
ADAYTUM Resources
# of Consulting / Training Days Summary
Through August 17, 2001
ETS Omaha
|  | Corporate | ETS | (NBPL) | EBS | EES | EWS | Total
Consulting:
| Fred Ali | 3 | 1 | 0 | 1 | 0 | 0 | 5
| Shannon Hillier | 9 | 8 | 0 | 1 | 1 | 0 | 19
| Dennis Upshaw | 42.5 | 1 | 0 | 1 | 4 | 0 | 48.5
| Hoang Vo | 2 | 56 | 0 | 0 | 0 | 0 | 58
| Riaz Fatehi | 5 | 47 | 0 | 0 | 0 | 0 | 52
| Subtotal | 61.5 | 113 | 0 | 3 | 5 | 0 | 182.5
|  | 73800 | 135600 | 0 | 3600 | 6000 | 0 | 219000
Training:
| Mel Smith | 3 | 1 | 0 | 1 | 1 | 3 | 9
| Phil Benson | 0 | 3 | 3 | 0 | 3 | 0 | 9
| Subtotal | 3 | 4 | 3 | 1 | 4 | 3 | 18
| Multiply by 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Subtotal | 6 | 8 | 6 | 2 | 8 | 6 | 36
|  | 7200 | 9600 | 7200 | 2400 | 9600 | 7200 | 43200
| TOTAL DAYS | 67.5 | 121 | 6 | 5 | 13 | 6 | 218.5
|  | 81000 | 145200 | 7200 | 6000 | 15600 | 7200 | 262200
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Adaytum_Resources___Progress_Rpt__8_17_01_.xls'#$Summary by BU
2025-09-26 21:13

## Consulting
Enron - Adaytum Work Plan
Adaytum Resources
# of Consulting Days
TOTAL
| Date | Fred Ali | Shannon Hillier | Dennis Upshaw | Hoang Vo | Riaz Fatehi | # of Days
| 2001-04-23 | Scoping (Corp) |  |  |  |  | 1
| 2001-04-24 | Scoping (Corp) |  | Scoping (Corp) | Scoping (Corp) |  | 3
| 2001-04-25 | Scoping (Corp) |  | Scoping (Corp) | Scoping (Corp) |  | 3
2001-04-26
2001-04-27
| 2001-05-08 | Scoping (ETS) | Scoping (ETS) | Scoping (ETS) |  |  | 3
| 2001-05-09 | Scoping (EBS) | Scoping (EBS) | Scoping (EBS) |  |  | 3
| 2001-05-10 |  | Scoping (EES) | Scoping (EES) |  |  | 2
| 2001-05-21 |  | ETS |  |  | ETS | 2
| 2001-05-22 |  | ETS |  |  | ETS | 2
| 2001-05-23 |  |  |  | ETS | ETS | 2
| 2001-05-24 |  |  |  | ETS | ETS | 2
| 2001-05-25 |  |  |  |  | ETS | 1
| 2001-05-29 |  | ETS |  | ETS |  | 2
| 2001-05-30 |  | ETS |  | ETS |  | 2
| 2001-05-31 |  |  |  | ETS |  | 1
| 2001-06-01 |  |  |  | ETS |  | 1
| 2001-06-04 |  | Design (Corp) | Design (Corp) |  | ETS | 3
| 2001-06-05 |  | Design, Salary (Corp) | Design, Salary (Corp) |  | ETS | 3
| 2001-06-06 |  |  | Salary , H/C (Corp) - 1/2 day | ETS | ETS | 2.5
| 2001-06-07 |  |  |  | ETS |  | 1
| 2001-06-08 |  |  |  | ETS |  | 1
| 2001-06-11 |  | O&M (Corp) | O&M (Corp) | ETS | ETS | 4
| 2001-06-12 |  | O&M / Allocations (Corp) | O&M / Allocations (Corp) | ETS | ETS | 4
| 2001-06-13 |  | Allocations (Corp) | Allocations (Corp) | ETS | ETS | 4
| 2001-06-14 |  |  | Allocations (Corp) | ETS | ETS | 3
| 2001-06-15 |  |  | Allocations (Corp) | ETS | ETS | 3
| 2001-06-18 |  | Contributor (Corp) | Investment, DD&A (Corp) | ETS | ETS | 4
| 2001-06-19 |  | Contributor (Corp) | Contributor (Corp) | ETS | ETS | 4
| 2001-06-20 |  | Contributor (Corp) | Contributor (Corp) | ETS | ETS | 4
| 2001-06-21 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-06-22 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-06-23 |  |  |  | ETS |  | 1
| 2001-06-25 |  | Contributor (ETS) | Contributor (Corp) | ETS | ETS | 4
| 2001-06-26 |  | Contributor (ETS) | Contributor (Corp) | ETS | ETS | 4
| 2001-06-27 |  | Contributor (ETS ) | Contributor (Corp) | ETS | ETS | 4
| 2001-06-28 |  | Contributor (Corp) | Contributor (Corp) | ETS | ETS | 4
| 2001-06-29 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-06-30 |  |  |  | ETS | ETS | 2
| 2001-07-02 |  |  |  | ETS | ETS | 2
| 2001-07-03 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-05 |  |  | Contributor (Corp) |  | ETS | 2
| 2001-07-06 |  |  | Contributor (Corp) |  | ETS | 2
| 2001-07-08 |  |  |  |  | ETS | 1
| 2001-07-09 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-10 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-11 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-12 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-13 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-14 |  |  |  | ETS |  | 1
| 2001-07-15 |  |  |  | ETS - 1/2 day |  | 0.5
| 2001-07-16 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-17 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-18 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-19 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-20 |  |  | Contributor (Corp) / EES | ETS | ETS | 3
| 2001-07-23 |  |  | Contributor (Corp) / EES | ETS | ETS | 3
| 2001-07-24 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-25 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-26 |  |  | Contributor (Corp) | ETS | ETS | 3
| 2001-07-27 |  |  | Contributor (Corp) |  | ETS | 2
| 2001-07-30 |  |  |  | ETS | ETS | 2
| 2001-07-31 | [5 empty] | 0
| 2001-08-01 | [5 empty] | 0
| 2001-08-02 |  |  |  | ETS | ETS | 2
| 2001-08-03 |  |  |  | ETS | ETS | 2
| 2001-08-06 |  |  | Contributor (Corp) | ETS | Corporate (Links) | 3
| 2001-08-07 |  |  | Contributor (Corp) | ETS | Corporate (Links) | 3
| 2001-08-08 |  |  | Contributor (Corp) | ETS | Corporate (Links) | 3
| 2001-08-09 |  |  | Contributor (Corp) | ETS | Corporate (Links) | 3
| 2001-08-10 |  |  |  | ETS | Corporate (Links) | 2
| 2001-08-13 |  |  |  | ETS |  | 1
| 2001-08-14 |  |  | Contributor (Corp) | ETS |  | 2
| 2001-08-15 |  |  | Contributor (Corp) | ETS |  | 2
| 2001-08-16 |  |  | EES | ETS |  | 2
| 2001-08-17 |  |  | EES | ETS - 1/2 day |  | 1.5
| Total Days | 5 | 19 | 48.5 | 58 | 52 | 182.5
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Adaytum_Resources___Progress_Rpt__8_17_01_.xls'#$Consulting
2025-09-26 21:13

## Training
Enron - Adaytum Work Plan
ADAYTUM Resources
# of Training Days
|  |  |  | Adaytum | # of
|  |  | Dates | Resources | Days
Training:
|  | Consolidated / Corporate | 4/18 - 4/20 | Mel Smith | 3
|  | ETS, EBS & EES | 5/01 - 5/03 | Mel Smith | 3
|  | EWS | 5/15 - 5/17 | Mel Smith | 3
|  | ETS (additional) | 5/15 - 5/17 | Phil Benson | 3
|  | ETS Omaha (NBPL) | 6/04 - 6/06 | Phil Benson | 3
|  | EES (additional) | 6/26 - 6/28 | Phil Benson | 3
18
Scoping / Design Work:
|  | Consolidated / Corporate |  |  | 77
|  | ETS |  |  | 40
|  | ETS Omaha (NBPL) |  |  | 25
|  | EES |  |  | 12
|  | EBS |  |  | 11
|  | EWS |  |  | 8
173
|  |  |  | Prepaid consulting | 60
|  |  |  | Estimated addt'l consulting | 113
173
Notes per Adaytum:
*Negotiated Rate
First 60 Days at $1,178/Day. Additional days based on voucher system.
Vouchers must be prepaid prior to use.
*Please note: Consultant hourly costs do not include travel, housing, nor meal expenses.
Any items not included in the scope/milestones that require consultant support will result
in additional consulting hours.
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Adaytum_Resources___Progress_Rpt__8_17_01_.xls'#$Training
2025-09-26 21:13