## Cover
Asset Marketing Group
WEEKLY UPDATE
Highly Confidential
PRINT

## Americas
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
Alamac | Sale of 2 coal plants in North Carolina | $20 - $30 | Don Miller
ENE Banker: | Action Items: |  | John Hoff
None | Negotiating with AIG on purchase. Also discussing purchase with several counterparties. Reliant and Duke have expressed an early interest in taking a look at asset. |  | Heather Kroll
ENE O/S Legal: |  |  | Steve Van Hooser
Bracewell & Patterson |  | Basis ($MM) | Ozzie Pagan
Counterparty Banker: | Update: | 7.5
N/A | AIG should close no later than May 14, 2201. Duke and Reliant will soon be reviewing assets.
Counterparty O/S Legal: |  | Implied Gain ($MM)
N/A |  | $12.5 - $22.5
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Cornhusker | Sale of our 100% interest in Texas QF plant. | 260 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | In early discussions with El Paso. Issues on sale include East Coast Power problems with El Paso, and Brazos arbitration. |  | Don MIller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
Le Boeuf | Update: | 239
Counterparty Banker: | Received early indications of interest from El Paso; should hear a preliminary value data point the week of May 14.
N/A |  | Implied Gain ($MM)
Counterparty O/S Legal: |  | 21
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Don Miller
Vitro | Sell 50% - 80% of our interest in Mexican project. | $52 - $57 (80%) | Max Yzaguirre
ENE Banker: | Action Items: |  | Robert George
Soc Gen | Proposal and marked up documents received from ENEL 3/1/01. Received follow up proposal on 4/09/01. Meeting with ENEL on 5/2/01. Tactebel submitted preliminary bid on 4/12/01. Binding bid is due 5/7/01. Will be working with both counterparties over coming week. |  | Maria Elena Garcia Don Miller Jon Hoff
ENE O/S Legal: |  |  | Steve Irvin
Bracewell & Patterson |  |  | Jon Hoff
Counterparty Banker: |  | Basis ($MM) | Marc Sabine
ENEL (West LB), Tractebel-None |  | 42
Counterparty O/S Legal: | Update:
ENEL (Fulbright), Tractebel (Baker) | Received binding offer from Tractebel at $12MM, which has been raised to $15MM. Will most likely be negotiating with Tractebel the week of May 14. | Implied Gain ($MM)
| Max and Irvin are planning trip to IDB to discuss sale the week of May 14. | $10 - $15
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
New Albany | Sale of New Albany Peaker | 150 | Don Miller
ENE Banker: | Action Items: | ($405/kw) | John Hoff
None | Looking for feedback from NRG and Cinergy. Pull together list of bidders.
ENE O/S Legal: |  | Basis ($MM)
Andrews & Kurth | Update: | 145
Counterparty Banker: | Duke and Reliant now have info memo. Still waiting to hear from NRG. Cinergy has deferred its interest. | ($390/kw)
N/A
Counterparty O/S Legal:
N/A |  | Implied Gain ($MM)
5
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Michigan Power-Motown | Reviewing near-term options with Michigan QF asset. | 45 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | This QF asset has existing restructuring opportunities. This asset is also a candidate for QF Fund or eventual sale. In discussions with Consumers Electric for reverse toll (term sheet sent 4/30/01). Issues exist with Consumers over refund of past capacity changes. Our exposure is approximately $8 million; value is net of $8 million. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
None |  | 52
Counterparty Banker:
N/A
Counterparty O/S Legal: | Update: | Implied Gain ($MM)
N/A | Sent updated term sheet to Consumers 5/08/01. | -8
In conversations with Consumers on reverse toll.
Project Name: | Overview: |  | Don Miller
QF Fund | Evaluating new financing/funding options for existing QF's, and QF's to be purchased. | $400 - $700 | Lisa Bills
ENE Banker: | Action Items:
N/A | Working with ENA Treasury and LJM to determine market for QF Fund (closest proxy is Turbo Park) to hold QF assets off-balance sheet and off-credit for 3 to 5 years. Focus is on flexibility, cost of funds, and term.
ENE O/S Legal:
N/A | Update:
Counterparty Banker: | Will send QF models to LJM on Monday, the 14th.
N/A
Counterparty O/S Legal:
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Don Miller
Mission Bid | Edison Mission is auctioning 8 Non-California QF assets. |  | Chris Calger
ENE Banker: | Action Items: |  | David Marks
None | Included in Mission's assets are Saguaro in which ENA owns a 15% interest, and EcoElectrica, in which EGA and EGM own 50% interest. We are on the bid and offer on these two assets, and are evaluating the other six assets, including Brooklyn Navy Yard. |  | Mike Etringer Mariella Mahan Bill Keeney
ENE O/S Legal:
LeBoeuf, Andrews & Kurth | Update:
Counterparty Banker: | Made round II on all of the assets. Will initiate due diligence week of May 14th. Finalizing what assets we have an interest in pursuing.
CSFB
Counterparty O/S Legal:
N/A
Project Name: | Overview: | Sale Price ($MM) | Ron Tapscott
Doyle | Managing Doyle to maximize value. | $5 - $6
ENE Banker: | Action Items:
None | The value proposition with Doyle includes:
ENE O/S Legal: | 4 Effect Payout of Output Bonus ($1.75 MM) | Basis ($MM)
King & Spalding | 4 Resolve outstanding Unit 1 claim ($2- $6 MM) | N/A
Counterparty Banker: | 4 Selldown of equity ($3 - $4 MM)
N/A
Counterparty O/S Legal: | Update:
N/A |  | Implied Gains ($MM)
N/A