## Cover
Asset Marketing Group
WEEKLY UPDATE
Highly Confidential
PRINT

## Americas
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
Alamac | Sale of 2 coal plants in North Carolina | $20 - $30 | Don Miller
ENE Banker: | Action Items: |  | John Hoff
None | Sold plants to AIG on May 16, 2001. Reliant and Duke are looking at the plants. Will soon be starting formal auction process to capture 90% of upside with sale. |  | Heather Kroll
ENE O/S Legal: |  |  | Steve Van Hooser
Bracewell & Patterson |  | Basis ($MM) | Ozzie Pagan
Counterparty Banker: | Update: | 7.5
N/A
Counterparty O/S Legal: |  | Implied Gain ($MM)
N/A |  | $12.5 - $22.5
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Cornhusker | Sale of our 100% interest in Texas QF plant. | 250 - 260 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | In early discussions with El Paso. Issues on sale include East Coast Power problems with El Paso, and Brazos arbitration. |  | Don MIller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
Le Boeuf | Update: | 239
Counterparty Banker: | Received early indications of interest from El Paso that are encouraging. El Paso conducting site visits and completing additional due dili. Will continue to work process them.
N/A |  | Implied Gain ($MM)
Counterparty O/S Legal: |  | 2001-11-21
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Don Miller
Vitro | Sell 50% - 80% of our interest in Mexican project. | $52 - $57 (80%) | Max Yzaguirre
ENE Banker: | Action Items: |  | Robert George
Soc Gen | Proposal and marked up documents received from ENEL 3/1/01. Received follow up proposal on 4/09/01. Meeting with ENEL on 5/2/01. Tactebel submitted preliminary bid on 4/12/01. Binding bid is due 5/7/01. Will be working with both counterparties over coming week. |  | Maria Elena Garcia Don Miller Jon Hoff
ENE O/S Legal: |  |  | Steve Irvin
Bracewell & Patterson |  |  | Jon Hoff
Counterparty Banker: |  | Basis ($MM) | Marc Sabine
ENEL (West LB), Tractebel-None |  | 42
Counterparty O/S Legal: | Update:
ENEL (Fulbright), Tractebel (Baker) | Tractebel raised bid to $15MM. Confident that we can get them to $16MM. Negotiating docs with them. Also testing internal appetite to actually sell down our position by looking at other structures. Running into accounting issues. | Implied Gain ($MM)
$10 - $15
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
New Albany | Sale of New Albany Peaker | 150 | Don Miller
ENE Banker: | Action Items: | ($405/kw) | John Hoff
None | Looking for feedback from NRG and Cinergy. Pull together list of bidders.
ENE O/S Legal: |  | Basis ($MM)
Andrews & Kurth | Update: | 145
Counterparty Banker: | Duke, Reliant and Cleco now have info memo. Will either mover forward with one of these counterparties this week, or will begin formal auction process. Still waiting to hear from NRG. Cinergy has deferred its interest. | ($390/kw)
N/A
Counterparty O/S Legal:
N/A |  | Implied Gain ($MM)
5
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Michigan Power-Motown | Reviewing near-term options with Michigan QF asset. | 45 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | This QF asset has existing restructuring opportunities. This asset is also a candidate for QF Fund or eventual sale. In discussions with Consumers Electric for reverse toll (term sheet sent 4/30/01). Issues exist with Consumers over refund of past capacity changes. Our exposure is approximately $8 million; value is net of $8 million. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
None |  | 52
Counterparty Banker:
N/A
Counterparty O/S Legal: | Update: | Implied Gain ($MM)
N/A | Sent updated term sheet to Consumers 5/08/01. | -8
In conversations with Consumers on reverse toll.
Project Name: | Overview: |  | Don Miller
QF Fund | Evaluating new financing/funding options for existing QF's, and QF's to be purchased. | $400 - $700 | Lisa Bills
ENE Banker: | Action Items:
N/A | Working with ENA Treasury and LJM to determine market for QF Fund (closest proxy is Turbo Park) to hold QF assets off-balance sheet and off-credit for 3 to 5 years. Focus is on flexibility, cost of funds, and term.
ENE O/S Legal:
N/A | Update:
Counterparty Banker: | Met with LJM. Interest in Motown but not Cornhusker. May be able to structure a "fund" to purchase additional QFs. Will be limited in its flexibility.
N/A
Counterparty O/S Legal:
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Don Miller
Mission Bid | Edison Mission is auctioning 8 Non-California QF assets. |  | Chris Calger
ENE Banker: | Action Items: |  | David Marks
None | Included in Mission's assets are Saguaro in which ENA owns a 15% interest, and EcoElectrica, in which EGA and EGM own 50% interest. We are on the bid and offer on these two assets, and are evaluating the other six assets, including Brooklyn Navy Yard. |  | Mike Etringer Mariella Mahan Bill Keeney
ENE O/S Legal:
LeBoeuf, Andrews & Kurth | Update:
Counterparty Banker: | Made round II on all of the assets. Completing site visits and contract review.
CSFB
Counterparty O/S Legal:
N/A
Project Name: | Overview: | Sale Price ($MM) | Ron Tapscott
Doyle | Managing Doyle to maximize value. | $5 - $6
ENE Banker: | Action Items:
None | The value proposition with Doyle includes:
ENE O/S Legal: | 4 Effect Payout of Output Bonus ($1.75 MM) | Basis ($MM)
King & Spalding | 4 Resolve outstanding Unit 1 claim ($2- $6 MM) | N/A
Counterparty Banker: | 4 Selldown of equity ($3 - $4 MM)
N/A
Counterparty O/S Legal: | Update:
N/A |  | Implied Gains ($MM)
N/A