## Cover
Asset Marketing Group
WEEKLY UPDATE
Highly Confidential
PRINT

## Americas
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
Alamac | Sale of 2 coal plants in North Carolina | $20 - $30 | Don Miller
ENE Banker: | Action Items: |  | John Hoff
None | Sold plants to AIG on May 16, 2001. Reliant and Duke are looking at the plants. Will soon be starting formal auction process to capture 90% of upside with sale. |  | Heather Kroll
ENE O/S Legal: |  |  | Steve Van Hooser
Bracewell & Patterson |  | Basis ($MM) | Ozzie Pagan
Counterparty Banker: | Update: | 7.5
N/A | Stuart and Jon have contacted a number of interested parties. Teaser letter with CA's went our last week to 20+ parties. Info Memo will go out this week.
Counterparty O/S Legal: |  | Implied Gain ($MM)
N/A |  | $12.5 - $22.5
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Cornhusker | Sale of our 100% interest in Texas QF plant. | 250 - 260 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | In early discussions with El Paso. Issues on sale include East Coast Power problems with El Paso, and Brazos arbitration. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
Le Boeuf | Update: | 239
Counterparty Banker: | Received early indications of interest from El Paso that are encouraging. El Paso conducted site visits and completing additional due dili. Will continue to work process with them.
N/A |  | Implied Gain ($MM)
Counterparty O/S Legal: | Working on boxing the legal issues surrounding this asset. | $11-21
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Don Miller
Vitro | Sell 50% - 80% of our interest in Mexican project. | $57.66 (80%) | Steve Irvin
ENE Banker: | Action Items: |  | Robert George
Soc Gen |  |  | Maria Elena Garcia Don Miller Jon Hoff
ENE O/S Legal: |  |  | Marc Sabine
Bracewell & Patterson |  |  | Jon Hoff
Counterparty Banker: |  | Basis ($MM)
ENEL (West LB), Tractebel-None |  | 42.16
Counterparty O/S Legal: | Update:
ENEL (Fulbright), Tractebel (Baker) | Signed Purchase and Sale with Tractebel on Monday, the 11th of June for $15.5MM plus up to an additional $1MM from their cost savings. | Implied Gain ($MM)
| Working on completing CP's to reach closure. | 15.5
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
New Albany | Sale of New Albany Peaker | 135 | Don Miller
ENE Banker: | Action Items: | ($365/kw) | John Hoff
None
ENE O/S Legal: |  | Basis ($MM)
Andrews & Kurth | Update: | 140
Counterparty Banker: | Signed PSA with Duke on June 21, 2001; awaiting Duke's BOD approval on Tuesday, the 26th. Target end of Sept. close. | ($378/kw)
N/A
Counterparty O/S Legal:
N/A |  | Implied Gain ($MM)
-5
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Michigan Power-Motown | Reviewing near-term options with Michigan QF asset. | 45 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | This QF asset has existing restructuring opportunities. This asset is also a candidate for QF Fund or eventual sale. In discussions with Consumers Electric for reverse toll (term sheet sent 4/30/01). Issues exist with Consumers over refund of past capacity changes. Our exposure is approximately $8 million; value is net of $8 million. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
None |  | 52
Counterparty Banker:
N/A
Counterparty O/S Legal: | Update: | Implied Gain ($MM)
N/A | Sent updated term sheet to Consumers 5/08/01. | -8
In conversations with Consumers on reverse toll.
Project Name: | Overview: |  | Don Miller
QF Fund | Evaluating new financing/funding options for existing QF's, and QF's to be purchased. | $400 - $700 | Lisa Bills
ENE Banker: | Action Items:
N/A | Working with ENA Treasury and LJM to determine market for QF Fund (closest proxy is Turbo Park) to hold QF assets off-balance sheet and off-credit for 3 to 5 years. Focus is on flexibility, cost of funds, and term.
ENE O/S Legal:
N/A | Update:
Counterparty Banker: | Met again with LJM. Beginning to scope out potential deal for Motown.
N/A
Counterparty O/S Legal:
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Don Miller
Mission Bid | Edison Mission is auctioning 8 Non-California QF assets. |  | Chris Calger
ENE Banker: | Action Items: |  | David Marks
None | Included in Mission's assets are Saguaro in which ENA owns a 15% interest, and EcoElectrica, in which EGA and EGM own 50% interest. We are on the bid and offer on these two assets, and are evaluating the other six assets, including Brooklyn Navy Yard. |  | Mike Etringer Mariella Mahan Bill Keeney
ENE O/S Legal:
LeBoeuf, Andrews & Kurth | Update:
Counterparty Banker: | Submitted $125MM bid on BNY and $57.6MM bid on Saguaro only. Will be moving forward with CSFB and Mission this week on BNY.
CSFB
Counterparty O/S Legal:
N/A
Project Name: | Overview: | Sale Price ($MM) | Ron Tapscott
Doyle | Managing Doyle to maximize value. | $5 - $6
ENE Banker: | Action Items:
None | The value proposition with Doyle includes:
ENE O/S Legal: | 4 Effect Payout of Output Bonus ($1.75 MM) - Received a $1.5MM | Basis ($MM)
King & Spalding | 4 Resolve outstanding Unit 1 claim ($2- $6 MM) | N/A
Counterparty Banker: | 4 Selldown of equity ($3 - $4 MM)
N/A
Counterparty O/S Legal: | Update:
N/A | Walton EMC and OPC are both evaluating a purchase of our 50% interest. | Implied Gains ($MM)
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Derek Davies
Calgary PPA (Redford) | Analyzing options to monetize 50% of Sundance PPA. |  | Don Miller
ENE Banker: | Action Items: |  | Jon Hoff
None | Received information and had conference call with Derek Davies regarding PPAs and efforts thus far to sell down our exposure. Derek is approaching government regarding separating PPAs, allowing us to cleanly sell 353 MWs to a third party.
ENE O/S Legal:
None | Update:
Counterparty Banker: | Having conversations with Derek regarding best next steps; Jon Hoff is reviewing the model.
None
Counterparty O/S Legal:
N/A