## Cover
Asset Marketing Group
WEEKLY UPDATE
Highly Confidential
PRINT

## Americas
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
Alamac | Sale of 2 coal plants in North Carolina | 22.5 | Don Miller
ENE Banker: | Action Items: |  | John Hoff
None | Closed sale to AIG on July 12, 2001. |  | Heather Kroll
ENE O/S Legal: |  |  | Steve Van Hooser
Bracewell & Patterson |  | Basis ($MM)
Counterparty Banker: | Update: | 7.5
N/A | Received 3 bids: 2 at $5-6MM(FPL and Aquila) and 1 at $19MM (Mirant). Mirant has dropped out. Still in discussion with several other parties on
Counterparty O/S Legal: | purchase and/or tolls. NRG and AES are both looking at asset. | Implied Gain ($MM)
N/A |  | 15
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Cornhusker | Sale of our 100% interest in Texas QF plant. | 245* | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | In discussions with El Paso. Issues on sale include East Coast Power problems with El Paso, and Brazos arbitration. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
Le Boeuf | Update: | 239
Counterparty Banker: | Looking at $237.2 million plus September distributions which would put us at approximately $245 million. Intent is to move El Pase to $240.0 + million. Meeting is scheduled with El Paso for August 13, 2001 to discuss PSA.
N/A |  | Implied Gain ($MM)
Counterparty O/S Legal: |  | 6
N/A
*Includes September distribution of $7.8 million.
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Don Miller
Vitro | Sell 50% - 80% of our interest in Mexican project. | $57.66 (80%) | Steve Irvin
ENE Banker: | Action Items: |  | Robert George
Soc Gen | Signed Purchase and Sale with Tractebel on Monday, the 11th of June for $15.5MM plus up to an additional $1MM from their cost savings. |  | Maria Elena Garcia Don Miller Jon Hoff
ENE O/S Legal: |  |  | Marc Sabine
Bracewell & Patterson |  |  | Jon Hoff
Counterparty Banker: |  | Basis ($MM)
Tractebel-None | Update: | 42.16
Counterparty O/S Legal:
Tractebel (Baker) | Working on CPs. Anticipate late August close. | Implied Gain ($MM)
| Received letter from IDB approving transfer; working on documents | $14.0*
*Net of $1.5MM in fees
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
New Albany | Sale of New Albany Peaker | 135 | Don Miller
ENE Banker: | Action Items: | ($365/kw) | John Hoff
None | Signed PSA on June 26, 2001
ENE O/S Legal: |  | Basis ($MM)
Andrews & Kurth | Update: | 136
Counterparty Banker: | Working through CPs with an October 1, 2001 closing. | ($376/kw)
N/A | Looking at HR issues.
Counterparty O/S Legal:
N/A |  | Implied Gain ($MM)
-1
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Michigan Power-Motown | Reviewing near-term options with Michigan QF assets. | $45 and $14.6 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | This QF asset has existing restructuring opportunities. This asset is also a candidate for QF Fund or eventual sale. In discussions with Consumers Electric for reverse toll (term sheet sent 4/30/01). Issues exist with Consumers over refund of past capacity changes. Our exposure is approximately $8 million; value is net of $4 million. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
None |  | 52
Counterparty Banker:
N/A
Counterparty O/S Legal: | Update: | Implied Gain ($MM)
N/A | In conversations with Consumers on reverse toll for Michigan Power. | 7.6
(on going) Delta Power is looking at Michigan Power asset and submitted
a bid of $41.5MM.
Project Name: | Overview: |  | Don Miller
QF Fund | Evaluating new financing/funding options for existing QF's, and QF's to be purchased. | $400 - $700 | Lisa Bills
ENE Banker: | Action Items:
N/A | Working with ENA Treasury and LJM to determine market for QF Fund (closest proxy is Turbo Park) to hold QF assets off-balance sheet and off-credit for 3 to 5 years. Focus is on flexibility, cost of funds, and term.
ENE O/S Legal:
N/A | Update:
Counterparty Banker: | Met again with LJM. Beginning to scope out potential deal for Motown.
N/A
Counterparty O/S Legal: | DEAD
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Don Miller
Mission Bid | Edison Mission is auctioning 8 Non-California QF assets. | Purchase Price ($MM) | Chris Calger
ENE Banker: | Action Items: |  | David Marks
None | Included in Mission's assets are Saguaro in which ENA owns a 15% interest, and EcoElectrica, in which EGA and EGM own 50% interest. We are on the bid and offer on these two assets, and are evaluating the other six assets, including Brooklyn Navy Yard. |  | Mike Etringer Mariella Mahan Bill Keeney Stuart Zisman
ENE O/S Legal:
LeBoeuf, Andrews & Kurth | Update:
Counterparty Banker: | Ended discussions on August 2, 2001.
CSFB
Counterparty O/S Legal:
N/A
Project Name: | Overview: | Sale Price ($MM) | Ron Tapscott
Doyle | Managing Doyle to maximize value. | $5 - $6
ENE Banker: | Action Items:
None | The value proposition with Doyle includes:
ENE O/S Legal: | 4 Effect Payout of Output Bonus ($1.75 MM) - Received a $1.5 MM | Basis ($MM)
King & Spalding | 4 Resolve outstanding Unit 1 claim ($2- $6 MM) | N/A
Counterparty Banker: | 4 Selldown of equity ($5 - $6 MM)
N/A
Counterparty O/S Legal: | Update:
N/A | Met with Walton. Waiting for reply over next several weeks. Requested that we delay conversations with OPC. | Implied Gains ($MM)
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Derek Davies
Calgary PPA (Redford) | Analyzing options to monetize 50% of Sundance PPA. | $250 CDN | Don Miller
ENE Banker: | Action Items: |  | Jon Hoff
None | Received information and had conference call with Derek Davies regarding PPAs and efforts thus far to sell down our exposure. Derek is approaching government regarding separating PPAs, allowing us to cleanly sell 353 MWs to a third party.
ENE O/S Legal:
Blake, Cassets, Graydon | Update:
Counterparty Banker: | Working on due diligence index and IM to take to market by early September.
None | Need to get letter from government soon to stay on track.
Counterparty O/S Legal:
N/A
Project Name: | Overview: |  | Stuart Zisman
Fort Pierce & Midway | Sale of two sites in Florida |  | Jon Hoff
ENE Banker: |  |  | Steve Plauche
None | Action Item: |  | Ben Jacoby
ENE O/S Legal: | Pulling IM together for late August launch.
None
Counterparty Banker: | Update:
None | Team is going to Fort Pierce to resolve open issues. IM should follow the last week of August.
Counterparty O/S Legal:
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Don Miller
Bridgeline | Sale of 40% in Bridgeline JV. |  | Jon Hoff
ENE Banker: |  |  | Brian Redmond
None | Action Item: |  | Jean Mrha
ENE O/S Legal: | Pulling together comps and valuation methodology. Anticipate going to
None | TX with proposal for them to purchase our 40% intrest update.
Counterparty Banker: | Update:
None | EBITDA is way off $56MM budget. Working through accounting, tax, legal
Counterparty O/S Legal: | issues to be able to make determine on sale/no-sale.
N/A
Project Name: | Overview: |  | Don Miller
Bistineau (Koch) | Strategic evaluation of Koch storage facility |  | Jon Hoff
ENE Banker:
None | Action Item:
ENE O/S Legal: | Visit with gas group to determine how asset would fit into business.
None
Counterparty Banker: | Update:
None
Counterparty O/S Legal:
N/A