## Cover
Asset Marketing Group
WEEKLY UPDATE
Highly Confidential
PRINT

## Americas
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
Alamac | Sale of 2 coal plants in North Carolina | 22.5 | Don Miller
ENE Banker: | Action Items: |  | John Hoff
None | Closed sale to AIG on July 12, 2001. |  | Heather Kroll
ENE O/S Legal: |  |  | Steve Van Hooser
Bracewell & Patterson |  | Basis ($MM)
Counterparty Banker: | Update: | 7.5
N/A | Received 3 bids: 2 at $5-6MM(FPL and Aquila) and 1 at $19MM (Mirant). Mirant has dropped out. FPL raised bid to $10.5MM. Still in discussion
Counterparty O/S Legal: | with CP&L, Dominion, Mirant and Electrocities regarding toll. NRG bid | Implied Gain ($MM)
N/A | $10MM and AES passed. | 15
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Cornhusker | Sale of our 100% interest in Texas QF plant. | 245* | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | In discussions with El Paso. Issues on sale include East Coast Power problems with El Paso, and Brazos arbitration. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
Le Boeuf | Update: | 239
Counterparty Banker: | Looking at $237.2 million plus September distributions which would put us at approximately $245 million. Intent is to move El Pase to $240.0 + million. Dash is complete for sale of LP. LP will be signed next several days for $3.2MM.
N/A |  | Implied Gain ($MM)
Counterparty O/S Legal: |  | 6
N/A
*Includes September distribution of $7.8 million.
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Don Miller
Vitro | Sell 50% - 80% of our interest in Mexican project. | $57.66 (80%) | Steve Irvin
ENE Banker: | Action Items: |  | Robert George
Soc Gen | Signed Purchase and Sale with Tractebel on Monday, the 11th of June for $15.5MM plus up to an additional $1MM from their cost savings. |  | Maria Elena Garcia Don Miller Jon Hoff
ENE O/S Legal: |  |  | Marc Sabine
Bracewell & Patterson |  |  | Jon Hoff
Counterparty Banker: |  | Basis ($MM)
Tractebel-None | Update: | 42.16
Counterparty O/S Legal:
Tractebel (Baker) | Working on CPs. Anticipate late August or early September close. | Implied Gain ($MM)
| Received letter from IDB approving transfer; working on documents | $14.0*
*Net of $1.5MM in fees
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
New Albany | Sale of New Albany Peaker | 135 | Don Miller
ENE Banker: | Action Items: | ($365/kw) | John Hoff
None | Signed PSA on June 26, 2001
ENE O/S Legal: | HSR has been received. | Basis ($MM)
Andrews & Kurth | Update: | 136
Counterparty Banker: | Working through CPs with an October 1, 2001 closing. | ($376/kw)
N/A | Looking at HR issues.
Counterparty O/S Legal: | Found rust in generator on August 17, 2001. Plan to fix unit #3 for
N/A | $1.3MM | Implied Gain ($MM)
-1
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Michigan Power-Motown | Reviewing near-term options with Michigan QF assets. | $45 and $14.6 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | This QF asset has existing restructuring opportunities. This asset is also a candidate for QF Fund or eventual sale. In discussions with Consumers Electric for reverse toll (term sheet sent 4/30/01). Issues exist with Consumers over refund of past capacity changes. Our exposure is approximately $8 million; value is net of $4 million. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
None |  | 52
Counterparty Banker:
N/A
Counterparty O/S Legal: | Update: | Implied Gain ($MM)
N/A | In conversations with Consumers on reverse toll for Michigan Power. | 7.6
(on going) Delta Power is looking at Michigan Power asset and submitted
a bid of $41.5MM.
Project Name: | Overview: | Sale Price ($MM) | Ron Tapscott
Doyle | Managing Doyle to maximize value. | $5 - $6
ENE Banker: | Action Items:
None | The value proposition with Doyle includes:
ENE O/S Legal: | 4 Effect Payout of Output Bonus ($1.75 MM) - Received a $1.5 MM | Basis ($MM)
King & Spalding | 4 Resolve outstanding Unit 1 claim ($2- $6 MM) | N/A
Counterparty Banker: | 4 Selldown of equity ($5 - $6 MM)
N/A
Counterparty O/S Legal: | Update:
N/A | Walton bid $3.5MM. Ron countered at $5.25MM. | Implied Gains ($MM)
| Have call into Walton | N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Derek Davies
Calgary PPA (Redford) | Analyzing options to monetize 50% of Sundance PPA. | $250 CDN | Don Miller
ENE Banker: | Action Items: |  | Jon Hoff
None | Received information and had conference call with Derek Davies regarding PPAs and efforts thus far to sell down our exposure. Derek is approaching government regarding separating PPAs, allowing us to cleanly sell 353 MWs to a third party.
ENE O/S Legal:
Blake, Cassets, Graydon | Update:
Counterparty Banker: | Working on due diligence index and IM to take to market by early September.
None | Received letter from government on Friday, August 17, 2001
Counterparty O/S Legal:
N/A
Project Name: | Overview: |  | Stuart Zisman
Fort Pierce & Midway | Sale of two sites in Florida |  | Jon Hoff
ENE Banker: |  |  | Steve Plauche
None | Action Item: |  | Ben Jacoby
ENE O/S Legal: | Pulling IM together for late August launch.
None
Counterparty Banker: | Update:
None | IM is targeted to go out mid September.
Counterparty O/S Legal:
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Don Miller
Bridgeline | Sale of 40% in Bridgeline JV. |  | Jon Hoff
ENE Banker: |  |  | Brian Redmond
None | Action Item: |  | Jean Mrha
ENE O/S Legal: | Pulling together comps and valuation methodology. Anticipate going to
None | TX with proposal for them to purchase our 40% intrest update.
Counterparty Banker: | Update:
None | EBITDA is way off $56MM budget. Working through accounting, tax, and
Counterparty O/S Legal: | legal issues to be able to make determine on sale/no-sale.
N/A
Project Name: | Overview: |  | Don Miller
Bistineau (Koch) | Strategic evaluation of Koch storage facility |  | Jon Hoff
ENE Banker:
None | Action Item:
ENE O/S Legal: | Visit with gas group to determine how asset would fit into business.
None
Counterparty Banker: | Update:
None
Counterparty O/S Legal:
N/A
Other Items:
- Cogentrix
- UAE
- Osceola Plant (FL)
- SIMCO Gas Storage