## Cover
Asset Marketing Group
WEEKLY UPDATE
Highly Confidential
PRINT

## Americas
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
Alamac | Sale of 2 coal plants in North Carolina | 22.5 | Don Miller
ENE Banker: | Action Items: |  | John Hoff
None | Received 3 bids: 2 at $5-6MM(FPL and Aquila) and 1 at $19MM (Mirant). Mirant has dropped out. FPL raised bid to $10.5MM. Still in discussion with CP&L, Dominion, Mirant and Electrocities regarding toll. NRG bid |  | Heather Kroll
ENE O/S Legal: |  |  | Steve Van Hooser
Bracewell & Patterson | $10MM and AES passed. | Basis ($MM)
Counterparty Banker: |  | 7.5
N/A | Update:
Counterparty O/S Legal: | Provided terms of Dominion toll to AIG. Waiting to hear back from AIG. | Implied Gain ($MM)
N/A |  | 15
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Cornhusker | Sale of our 100% interest in Texas QF plant. | $247* | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | Looking at $239 million September distributions which would put us at approximately $247 million. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
Le Boeuf | Update: | 240
Counterparty Banker: | GP was signed Friday, September 7, 2001, with board of directors approval on September 21. Looking to expedite HSR
N/A |  | Implied Gain ($MM)
Counterparty O/S Legal: |  | 7
N/A
*Includes September distribution of $7.8 million.
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Don Miller
Vitro | Sell 50% - 80% of our interest in Mexican project. | $57.66 (80%) | Steve Irvin
ENE Banker: | Action Items: |  | Robert George
Soc Gen | Signed Purchase and Sale with Tractebel on Monday, the 11th of June for $15.5MM plus up to an additional $1MM from their cost savings. |  | Maria Elena Garcia Don Miller Jon Hoff
ENE O/S Legal: |  |  | Marc Sabine
Bracewell & Patterson |  |  | Jon Hoff
Counterparty Banker: |  | Basis ($MM)
Tractebel-None | Update: | 42.16
Counterparty O/S Legal:
Tractebel (Baker) | Working on CPs. Anticipate late September close. | Implied Gain ($MM)
| Received letter from IDB approving transfer; working on documents | $14.0*
*Net of $1.5MM in fees
Project Name: | Overview: | Sale Price ($MM) | Stuart Zisman
New Albany | Sale of New Albany Peaker | 135 | Don Miller
ENE Banker: | Action Items: | ($365/kw) | John Hoff
None | Signed PSA on June 26, 2001
ENE O/S Legal: | HSR has been received. | Basis ($MM)
Andrews & Kurth | Update: | 136
Counterparty Banker: | Comment period ends on September 17th . May target early closing. | ($376/kw)
N/A
Counterparty O/S Legal: | Found rust in generator on August 17, 2001. Repairing unit #3 right now.
N/A |  | Implied Gain ($MM)
-1
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: | Sale Price ($MM) | Chuck Ward
Michigan Power-Motown | Reviewing near-term options with Michigan QF assets. | $45 and $14.6 | Stuart Zisman
ENE Banker: | Action Items: |  | John Hoff
None | This QF asset has existing restructuring opportunities. This asset is also a candidate for QF Fund or eventual sale. In discussions with Consumers Electric for reverse toll (term sheet sent 4/30/01). Issues exist with Consumers over refund of past capacity changes. Our exposure is approximately $8 million; value is net of $4 million. |  | Don Miller Rick Hill
ENE O/S Legal: |  | Basis ($MM) | Chris Coffman
None |  | 52
Counterparty Banker:
N/A
Counterparty O/S Legal: | Update: | Implied Gain ($MM)
N/A | In conversations with Consumers on reverse toll for Michigan Power. | 7.6
(on going) Delta Power is looking at Michigan Power asset and submitted
a bid of $41.5MM.
Project Name: | Overview: | Sale Price ($MM) | Ron Tapscott
Doyle | Managing Doyle to maximize value. | $5 - $6
ENE Banker: | Action Items:
None | The value proposition with Doyle includes:
ENE O/S Legal: | 4 Effect Payout of Output Bonus ($1.75 MM) - Received a $1.5 MM | Basis ($MM)
King & Spalding | 4 Resolve outstanding Unit 1 claim ($2- $6 MM) | N/A
Counterparty Banker: | 4 Selldown of equity ($5 - $6 MM)
N/A
Counterparty O/S Legal: | Update:
N/A | Walton bid $3.5MM. Ron countered at $5.25MM. | Implied Gains ($MM)
| Agreed on $4.85MM | N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Derek Davies
Calgary PPA (Redford) | Analyzing options to monetize 50% of Sundance PPA. | $250 CDN | Don Miller
ENE Banker: | Action Items: |  | Jon Hoff
None | Received information and had conference call with Derek Davies regarding PPAs and efforts thus far to sell down our exposure. Derek is approaching government regarding separating PPAs, allowing us to cleanly sell 353 MWs to a third party.
ENE O/S Legal:
Blake, Cassets, Graydon | Update:
Counterparty Banker: | Working on due diligence index and IM to take to market by mid September.
None | Received letter from government on Friday, August 17, 2001
Counterparty O/S Legal:
N/A
Project Name: | Overview: |  | Stuart Zisman
Fort Pierce & Midway | Sale of two sites in Florida |  | Jon Hoff
ENE Banker: |  |  | Steve Plauche
None | Action Item: |  | Ben Jacoby
ENE O/S Legal: | Pulling IM together for mid September launch.
None
Counterparty Banker: | Update:
None | Teaser and CA's going out this week.
Counterparty O/S Legal:
N/A
Asset Marketing Group
Weekly Update
Americas
Project | Description | Size | Working Group
Project Name: | Overview: |  | Don Miller
Bridgeline | Sale of 40% in Bridgeline JV. |  | Jon Hoff
ENE Banker: |  |  | Brian Redmond
None | Action Item: |  | Jean Mrha
ENE O/S Legal: | Pulling together comps and valuation methodology. Anticipate going to
None | TX with proposal for them to purchase our 40% intrest update.
Counterparty Banker: | Update:
None | EBITDA is way off $56MM budget. Working through accounting, tax, and
Counterparty O/S Legal: | legal issues to be able to make determine on sale/no-sale.
N/A
Project Name: | Overview: |  | Don Miller
Bistineau (Koch) | Strategic evaluation of Koch storage facility |  | Jon Hoff
ENE Banker: |  |  | Jeff Batlett
None | Action Item:
ENE O/S Legal: | Visit with gas group to determine how asset would fit into business.
None
Counterparty Banker: | Update:
None
Counterparty O/S Legal:
N/A
Other Items:
- Cogentrix - Vetters is reviewing book
- UAE - Expect book shortly
- Osceola Plant (FL)
- SIMCO Gas Storage - Jeff Bartlett met with Laura Luce.