## Sheet1
Agave Energy Company
Atoka Loop Measurement Project
Material List
Mark Number | Required Quantity | Description | Date of Order | Unit Cost | Total Cost | Estimated Delivery Date
P001 | 3 | 8" WKM 370D4 24-YFF-24 600# RF FP Ball Valve NACE W/Gear Operator |  | 5951.4 | 17854.2
P002 | 1 | 8" 600# RF FP WKM Ball Valve W/Bettis #G2014-SR3 Actuator Fail Closed |  | 10214 | 10214
P003 | 1 | 8" Fisher 1052K-V200-3610J style 600# FE Flow Control Valve |  | 9050 | 9050
P004 | 1 | 8" WKM Check Valve 600# FE |  | 2599.4 | 2599.4
P005 | 11 | 8" 600# 304SS Flex Gasket w/Dura-Carb Filler |  | 6.18 | 67.98
P006 | 11 | 1 1/8" x 8" B7 Stud w/2-2H Nuts 12 per Set |  | 40.8 | 448.8
P007 | 10 | 8" RFWN Flange Std Bore |  | 147.39 | 1473.9
P008 | 5 | 8" Std LR 900 Weld Ell |  | 41.28 | 206.4
P009 | 2 | 8" Std Weld Tee |  | 60.48 | 120.96
P010 | 20 | 8" Bare Pipe Grade B .312 WT F.50, 1266# MAWP (ft) |  | 13.9 | 278
P011 | 2 | 8" x 12" STD Concentric Weld Reducer |  | 47.36 | 94.72
P012 | 20 | 12" Bare Pipe Grade B .375 WT F.50, ????# MAWP (ft) |  | 26.71 | 534.2
P013 | 1 | 12" RFWN Flange Std Bore |  | 312.46 | 312.46
P014 | 1 | 12" Flex Gasket |  | 11.17 | 11.17
P015 | 1 | 8"x8"x3" Reducing Tee Std |  | 119.36 | 119.36
P016 | 1 | 3"x2" Concentric weld reducer |  | 5.44 | 5.44
P017 | 2 | 2" RFWN Flanges Std Bore |  | 15.13 | 30.26
P018 | 1 | 2" 600# series FE Ball Valve |  | 249.89 | 249.89
P019 | 1 | 2" Closure Tapped to 1/2" |  | 73.1 | 73.1
P020 | 2 | Set of Studs for 2" 600# series 8/set |  | 5.65 | 11.3
P021 | 2 | 2" 600# Flex Gasket |  | 1.63 | 3.26
P022 | 1 | 8" Insullator Kit |  | 32.75 | 32.75
P023 | 1 | 12" Weld ell 90 Std |  | 108.32 | 108.32
P024 | 1 | Set of Studs for 12" 600# series /set |  | 91.1 | 91.1
43990.97
|  | Equipment | Date of Order
E001 | 1 | 8" Meter Tube with Daniels Sr (8'x8'x6') 3 Piece w/ 5-3/4" TOL, Gallagher syst II, With 8" 600# Sch 40 clean out tees & Huber Closures. AGA 14.3 | 2001-09-26 | 15639 | 15639
E002 | 1 | Daniel Model 570 Danalyzer On Line Chromatograph, 4 minute analysis time with Model 2350 Controller | 2001-10-01 | 26187 | 26187
E003 | 1 | Meeco Moisture analyzer with Coalescer and filtering | 2001-09-28 | 6620 | 6620
E004 | 1 | DelMar SulfurAlert 6000 Total Sulfur Monitor | 2001-10-01 | 34555 | 34555
E005 | 1 | DelMar SulfurSmart 1200 H2S analysis system | 2001-10-01 | 15238 | 15238
E006 | 1 | Fisher ROC 364 per TW specs |  | 20000 | 20000
E007 | 1 | Welker Cal gas Hot Box Double | 2001-10-02 | 5220 | 5220
123459
Building
| 1 | Building from 7-Rivers insullated, wired and ready for A/C |  | 0 | 0
| 1 | A/C |  | 1800 | 1800
| 1 | Make any repairs on building |  | 750 | 750
| 1 | Concrete Pad |  | 3000 | 3000
| 1 | Electric Drop and meter can |  | 3000 | 3000
8550
Totals
|  |  |  | Fittings | 43990.97
|  |  |  | Measurement Equipment | 123459
|  |  |  | Building | 8550
|  |  |  | Labor | 24500
200499.97

## Sheet2
Building
1 | Building from 7-Rivers insullated, wired and ready for A/C | 0 | 0
1 | A/C | 1800 | 1800
1 | Make any repairs on building | 750 | 750
1 | Concrete Pad | 3000 | 3000
1 | Electric Drop and meter can | 3000 | 3000