## Objectives
Barney Brasher
2000 Objectives
Status Update 11/15/00
| Objective |  | Measure | Completion | Status Update
Manage 2000 Capital Plan for |  | Monthly Updates |  | Year-end 2000 | On going --> Meeting
GCO to be within plan. |  |  |  |  | Unplanned Needs from
within Approved Plan
Identify Opportunities for |  | a) Complete survey of individual team |  | N/A | Completed Survey and
improved efficiency in the way |  | work requirements and skills |  |  | Compiling Data.
business is conducted in GCO |  | b) Evaluate outsourcing opportunities |  |  | Evaluation, Developing an
|  | and develop action plan |  |  | Action Plan, and
|  | c) Complete implementation of action |  |  | Implementation were given
|  | plan by year-end |  |  | to CAT
Develop procedures addressing |  | Procedures published to all effected |  | Revised to end of 3rd Quarter | Completed 9/30/00
the use of contractors in |  | parties
"emergency" situations
Perform internal review of |  | Audit report and findings |  | Revised to end of 3rd Quarter | Completed HPL/ENA 4/00
all processes related to contract |  |  |  |  | Completed FGT 9/00
inspectors
Develop audit program to |  | Present program proposal to |  | Program approved 1st Qtr. | Initiated late 1999. Worked with
thoroughly review controls in |  | management |  | Review November/December | EY to Initiate Random Audit
place and actions of employees |  |  |  |  | Progam of Field Ops Expense
Accounts. Review will be conducted
November/December Timeframe.
Evaluation of Administrative |  | a) Develop action plan, evaluate findings |  | Rescheduled to 2001 | Based on changing priorities
workload of teams and develop |  | and present recommendations |  |  | rescheduled to 1st Quarter of 2001
systems/processes to alleviate |  | b) Implement recommendations |  |  | And implement 3rd Quarter of 2001
burden
Thorough Evaluation of Overtime |  | a) Review of 1999 Overtime by |  | Rescheduled to 2001 | Based on changing priorities
to identify components and |  | component |  |  | rescheduled to 1st Quarter of 2001
develop strategy |  | b) Evaluate findings,present |  |  | And implement 3rd Quarter of 2001
recommendations and implement
Establish outage report with |  | a) Conduct meetings with stakeholders |  | N/A | No Longer Applicable ---> being
risk factors and associated |  | to determine scope of project |  |  | Handled by Joint Mtgs with Gas
costs |  | b) Evaluate findings and develop course |  |  | Control/Operations (Want to insert
|  | of action |  |  | Obj on Sap Implementation)
Competively bid recurring |  | a) Identify targeted areas for bidding |  | N/A | Information was compiled and
maintenance work where a |  | b) Develop bid package and send to |  |  | data given to CAT for evaluation
single Contractor's invoices |  | prospective contractors |  |  | and use in their outsourcing
exceeded $100,000 in 1999 |  | c) Award and execute agreements |  |  | initiative.
Develop programs/processes |  | Monthly scorecard/financial reports |  | End of January 2000 | Initial Scorecard Complete 1/31
to track the savings created by
the GPG Continuous Improvement
Initiative (FGT's taget $1.3MM)
Conduct Admin Review of the use |  | Present recommendations to |  | End of 1st Quarter | Completed 4/00 Resulting
of contract clerks in Texas |  | Regional Management |  |  | in elimination of All Field
Contract Clerks.
Analyze data from the Mustang |  | Manpower Report |  | End of January 2000 | Initial Report developed, but
Timesheet Program for 1999 to |  |  |  |  | inconsistencey in reporting
develop manpower report relating |  |  |  |  | time within the regions lessened
to productive/non-productive work |  |  |  |  | value. Would like to have same
Objective in 2001 using SAP

## Accomplishments
Barney Brasher
2000 Accomplishments Outside of Objectives
1) Presented ENA Management audit results of HPL Special Projects Team
with recommendations
2) Submitted Bid Proposal to Bridgeline Holdings to operate pipelines and facilities
3) Presented to ENA audit results of third party use by HPL Special Projects Team
4) Completed initiative to offset impact of LRC loss on SE Admin Organization
5) Completed Contractor Survey of Florida, Alabama, Mississippi for CAT
initiative
6) Completed incentive settlement with ENA $300K in November Business
7) Prepared bid proposal to operate Rio Nogales and Gateway Pipelines
for ENA
8) Coordinated audit of inspection costs related to the FGT Ship Channel
Project. Audit resulted in termination of 2 employees and releasing of
2 third party inspectors.
9) Reduced floor space requirement at Brookhollow and Lafayette
10) Assumed lead in in establishing the following with the transition
of EOTT OPS into the ETS Organization:
* Budget guidelines for 2001 (O&M and Capital)
* FAR Orders and Asset Codes for initial payroll
* Approval of Work Order form
* Flow charts on Work Order Flow (Ops, E&C, Environmental)
* Training Book used as a guide for SW and North
* Established Methodology for reporting
* Worked with ISC in providing a proposal for releasing of Capital Funds