## Agenda
NORTHERN NATURAL GAS COMPANY
AGENDA
June 22, 2001
1) | COST CHANGES |  |  |  | AFUDC | 0.184
|  | $7.2 Million in July, 1999 |  |  | Installation | 0.847
|  | $9.8 million in June, 2001 |  |  | Overheads | 1.463
|  | $2.6 million increase |  |  | Gas Loss | 0.322
[5 empty] | Other | -0.221
2.595
(see attached for more detail)
2) | ECONOMICS
Project approved @ $7.2 million in July, 1999 -
Original Inservice date November, 2000
5.6 miles of pipeline
Inservice date changed to November, 2001
[6 empty] | ROE | DCF
|  | Economics @ original $7.2 million |  |  |  | 40.8% | 20.2%
|  | Economics @ new cost level of $9.8 million |  |  |  | 54.98% | 14.18%
|  | Economics w/o overhead increases |  |  |  | 56.87% | 21.4%
|  | Cost reduction needed to meet 15% DCF |  |  |  |  | 300000
3) | NEXT STEPS
ETS & ENE RAC
Horton signature
Skilling signature

## COSTS
BEATRICE TRAILBLAZER TO C LINE
Comparison of Revised PAF with Original PAF
%
| Revised | Original | Variance | Var.
| PAF | PAF
Materials | 166053 | 143712 | 22341 | 15.55%
Freight & Sales Tax | 23263 | 17970 | 5293 | 29.45%
Environmental | 0 | 0 | 0 | #DIV/0!
Construction Support | 20000 | 20000 | 0 | 0%
District Labor | 5000 | 5000 | 0 | 0%
Engineering | 25400 | 24600 | 800 | 3.252%
Contract Installation | 126177 | 90906 | 35271 | 38.8%
Row | 2000 | 2000 | 0 | 0%
Contingency | 76690 | 67991 | 8699 | 12.79%
Gas Loss | 20000 | 0 | 20000
Other General | 0 | 0 | 0
AFUDC | 2491 | 1954 | 537 | 27.48%
Overhead | 72926 | 85867 | -12941 | -15.07%
| 540000 | 460000 | 80000 | 17.39%
Overhead Rate Used | 20% | 30%