## B. Kraft
# | Category | Finding | Action Item | Responsible Person | Target Date | Confirm Reviewer | Completion Date | Comments
PSM
135 | ESMS | #341 Is every floor hole into which a person can accidently walk guarded by a standard toe board and railing or floor hole cover that is held securely in place? | Ensure all floor openings and pits are covered to prevent anyone from accidently stepping into them as required per ETS Safety Procedure guidelines. | Bob Kraft | 2001-08-30 | Don Bishop
147 | ESMS | #320 Do all electrical outlets, switch and junction boxes have cover plates? | Ensure all electrical conduits are sealed and no wiring is exposed. | Bob Kraft | 2001-08-30 | Don Bishop
148 | ESMS | #384 Are all outside electrical outlets for hand tools and outlets in wet areas equipped with ground fault protection or is personal GFI available? | Ensure all electrical outlets in wet areas and within 6 feet of a water source are equipped with ground fault protection or a personal GFCI is used as required per ETS Safety Procedure guidelines. | Bob Kraft | 2001-08-30 | Don Bishop
94 | Operating Procedures | Security fence missing at some locations. | Develop a plan for providing a security fence between owners at this location. | Bob Kraft | 2001-09-30 | Rick Suderman
98 | GMP | 2"-fire water riser valve leaking water on the ground. | Assure that leaking valve on the fire water system south of the maintenance shop is corrected from discharging to the ground. | Bob Kraft | 2001-12-31 | Rick Suderman