## Sheet1
Development Risk
| ENA will be required to sign PPA and commit capital for development prior to acquiring permits | PPA provides regulatory out for permitting
PPA contingent upon ENE board approval
Construction Risk
| Delay damages of $200 per kW per day for COD after 1 July. | Delay damages payable by NEPCo exceed PSCo liability
ENA can avoid paying delay damages by sourcing power in the market
| Gas interconnect outside control of ENA. Anticipate 1 April completion. | Plant COD is no earlier than 60 days after completion of gas spur
| PSCo will not guarantee interconnect before 1 May. | Plant COD is no earlier than 60 days after supply of backfeed power
Operational Risk
| Plant must obtain 60% availability under PPA | Six pack configuration mitigates catastrophic loss of any one unit
| Unscheduled outage reduces capacity payment | ENA can supply replacement power in the event of forced outage or Force Majeure event to maintain availability and capacity payment.
Commodity Risk
| Plant has title to gas and power between respective points of delivery | Proximity of plant to points of delivery diminishes likelihood of transmission loss
Heat Rate Risk
| PPA requires heat rate testing. Plant required to make PSCo whole for degradation in heat rate | 3% buffer between expected and guaranteed heat rate
GE required to pay damages should heat rate degrade further from expected value