## Sheet1
|  |  | Equipment Description | [5 empty] | Approved | Work Orders | Work Orders | Work Orders
System Name | Account Number | System Number | Reciprocating Compressors | Screw Compressors |  |  |  | Pipeline | Capital Cost | Capital Cost | Capital Cost | Capital Cost
[5 empty] | Equipment at Compressor Stations |  |  |  |  | Approved | Spent To-date | Cleared GL
House Creek | 11025 | 100 | See Note 1. | See Note 1. | 1 - Type 2, 1 - Type 7, 1 - Type 8 | 0.87 miles of Type 9 pipe and 4.17 miles of Type 8 pipe. |  |  | 11944234 | 5151501 | 2930353 | 2930352.62
Caballo | 11026 | 200 | 6 ea. - Type B Compressors | 10 ea. - Type D Compressors | 4 - Type 2, 4 - Type 3, 7 - Type 5, 3 - Type 6, 1 - Type 7 | 4.75 miles of Type 10 pipe and 8.23 miles of Type 8 pipe and 5.31 miles of Type 5 pipe. |  |  | 8062497 | 8251400 | 9391074 | 9201767.38
Clydesdale | 11027 |  | 1 ea. - Type B Compressors | 3 ea. - Type D Compressors | 1 - Type 2, 1 - Type 3, 1 - Type 6 | 2.71 miles of Type 8 pipe and 1.76 miles of Type 5 pipe. |  |  | 3254256 | 3370675 | 1184374 | 933169.47
South Kitty | 11028 |  | See Note 2. | See Note 2. | 1 - Type 1, 1 - Type 3, 1 - Type 6 | 6.35 miles of Type 9 pipe and 64.4 miles of Type 1 through Type 5 pipe. |  |  | 7462998 | 9413156 | 3148758 | 1500547.48
Hoe Creek | 11029 |  | See Note 3. | See Note 3. | 1 - Type 2, 1 - Type 3, 1 - Type 6 |  |  |  | 6735882 | 4661220 | 1223740 | 654156.65
Box Draw | 11030 | 400 | 2 ea.- Type A Compressors | 8 ea. - Type D Compressors | 1 - Type 1, 1 - Type 3, 1 - Type 6 | 0.73 miles of Type 9 pipe and 21.43 miles of poly Type 1 through 5 pipe. |  |  | 6707026 | 7053775 | 7748011 | 7402548.64
Maverick | 11030 | 300 | 2 ea.- Type C Compressors | 0 | 1 - Type 4 | 2.89 miles of Type 9 pipe |  |  | 1650000 | See Note 4 | See Note 4 | See Note 4
Kudzu | [8 empty] | 4729128 | 0 | 0 | 0
Fort Union Receipt Points |  |  | 2 Receipt Points installed and inservice; 3rd receipt point installed and material purchased for fourth receipt point | [5 empty] | 676713 | 1194000 | 1213838 | 1104405.84
[8 empty] | Grand Total = | 51222734 | 39095727 | 26840148 | 23726948.08
Compressor Descriptions | [6 empty] | Compressor Descriptions
Type A = | Compressor |  | Driver |  |  |  | Type C = | Compressor |  | Driver
| Type | Recip | Make | Waukesha |  |  |  | Type | Recip | Make | Caterpillar
| Make | Ariel | Model | 7044 GSI |  |  |  | Make | Ariel | Model | 3516 TALE
| Model | JGK-4 | Rated HP | 1680 |  |  |  | Model | JGE-4 | Rated HP | 1265
|  |  | Speed | 1200 rpm | [5 empty] | Speed | 1400 rpm
| Design Ps | 80 psi | [5 empty] | Design Ps | 500 psi
| Design Pd | 650 psi | [5 empty] | Design Pd | 1440 psi
| Design | 11.5 MMSCFD | [5 empty] | Design | 14 MMSCFD
| No. Throws | 4 | [5 empty] | No. Throws | 4
| No. Stages | 2 | [5 empty] | No. Stages | 1
| Stg 1 Dia: | 13.65 in. X 5.5" Stroke | [5 empty] | Stg 1 Dia: | 5.125 in. X 4.5" Stroke
| Stg 2 Dia: | 7.875 in. X 5.5" Stroke | [5 empty] | Stg 2 Dia:
| Stg 3 Dia: | [6 empty] | Stg 3 Dia:
Type B = | Compressor |  | Driver |  |  |  | Type D = | Compressor |  | Driver
| Type | Recip | Make | Waukesha |  |  |  | Type | Rotary Screw | Make | Waukesha
| Make | Ariel | Model | 7044 GSI |  |  |  | Make | Sullair | Model | H24GL
| Model | JGK-4 | Rated HP | 1680 |  |  |  | Model | PDR-25X | Rated HP | 530
|  |  | Speed | 1200 rpm | [5 empty] | Speed | 1800 rpm
| Design Ps | 80 psi | [5 empty] | Design Ps | 5 psi
| Design Pd | 1440 psi | [5 empty] | Design Pd | 100 psi
| Design | 8.7 MMSCFD | [5 empty] | Design | 2.9 MMSCFD
| No. Throws | 4 | [5 empty] | Pipeline Descriptions
| No. Stages | 3 | [5 empty] | Type 1 | 4 inch | Polyethylene Pipe SDR 11or 17
| Stg 1 Dia: | 12.00 in. X 5.5" Stroke | [5 empty] | Type 2 | 6 inch | Polyethylene Pipe SDR 11or 17
| Stg 2 Dia: | 8.375 in. X 5.5" Stroke | [5 empty] | Type 3 | 8 inch | Polyethylene Pipe SDR 11or 17
| Stg 3 Dia: | 5.875 in. X 5.5" Stroke | [5 empty] | Type 4 | 10 inch | Polyethylene Pipe SDR 11or 17
[8 empty] | Type 5 | 12 inch | Polyethylene Pipe SDR 11or 17
Note 1: One Type B compressor was installed initially and then relocated to Haracz Compressor station on the Caballo System. No Screw compressors installed | [7 empty] | Type 6 | 14 inch | Polyethylene Pipe SDR 11or 17
yet. | [7 empty] | Type 7 | 6 inch | API 5L Grade B
Note 2: One Type A compressor and 4 Type D compressors will be installed by 8/1/00. | [7 empty] | Type 8 | 8 inch | API 5L Grade B
[8 empty] | Type 9 | 10 inch | API 5L Grade X-52
Note 3: One Type B compressor and 3 Type D compressors will be installed by 10/30/00. | [7 empty] | Type 10 | 12 inch | API 5L Grade X-52
Note 4: All of Maverick's Capital cost is included in the Box Draw work order. |  |  |  |  | Equipment Descriptions
[5 empty] | Type 1 | Dehy | J.W. Williams 24 MMscf Capacity with Glycol reboiler
Note 5: No cost has been incurred for this project todate. |  |  |  |  | Type 2 | Dehy | J.W. Williams 18 MMscf Capacity with Glycol reboiler
[5 empty] | Type 3 | Separator | J.W. Williams 60 inch. Diameter by 20 feet in length
Note 6: All Separators are Horizontal. |  |  |  |  | Type 4 | Filter/Separator | Q.B. Johnson 20 inch. Diameter by 12.5 feet in length
[5 empty] | Type 5 | Production skid | Hanover - Separator 48 inch. Diameter by 10 feet in length w/ Meter tube
Note 7: All dehys where supplied by J.W. Williams. |  |  |  |  | Type 6 | Compressor Building | Two bay for two compressors.
[5 empty] | Type 7 | Compressor Building | Single bay for one compressor.
[5 empty] | Type 8 | Separator | MIDCO 84 inch. Dia. By 14 feet in length.
Type 9
Type 10