## Summaru
ENRON CAPITAL & TRADE RESOURCES
Enron de Mexico | [5 empty] | Report Date: |  |  | 2000-06-02
Enron Energia Industrial de Mexico S. de R.L. de C.V.
COST SUMMARY ($ thousands) | [5 empty] | Expenditures to date: |  |  | as of 05/31/00
Control Budget
Actuals
|  | Control Budet | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance | %
Project | MW |  | 5/1/00 | 2000-05-31 | 2000-05-31 |  | 2000-06-01 | from CE | Complete
Vitro | 245 | 175891923.1619 | 175891923.1619 | 28223969.394 | 147667953.7679 |  | 175891923.1619 | 0 | 16.05%
TOTAL PROGRAM | 245 | 175891923.1619 | 175891923.1619 | 28223969.394 | 147667953.7679 |  | 175891923.1619 | 0 | 16.05%
Target $$/MW |  | 717926.217 | 717926.217
Changes to Control Budget Explanations
Current Estimate vs Actual Variance Explanations (000s)
Formulas:
Estimate to Complete = +[Actuals to Date]

## EEIM
ENRON NORTH AMERICA
Enron de Mexico
Enron Energia Industrial de Mexico S. de R.L. de C.V. | [7 empty] | 245 | MW
[15 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  | Anticipated |  | 2000-06-01 18:20
[7 empty] | Expense / | ENA |  | Increase / |  | ENA |  | Actuals to Date | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  | Capital | Control Budget |  | (Savings) |  | Current Estimate |  | 2000-05-31 | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | 2000-10-31 |  | 2000-11-30 |  | 2000-12-31 |  | 2001-01-31 |  | 2001-02-28 |  | 2001-03-31 |  | 2001-04-30 |  | 2001-05-31 |  | 2001-06-30 |  | 2001-07-31 |  | 2001-08-31 | Total ProjENA |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
5/1/00
MAJOR EQUIPMENT
| TURBINE UNITS -GE 7FA |  |  |  |  | ENA | Capital | 32316613 |  | 0 |  | 32316613 |  | 25101733.3333 | [10 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 | [9 empty] | 0 | 25101733.3333 |  |  |  | 7214879.6667 |  | 32316613 |  | 0 |  | Assumes August Project Funding
| IDC |  |  |  |  | ENA | Capital | 1729003 |  | 0 |  | 1729003 |  | 1457097.4167 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1457097.4167 |  | 0 |  | 271905.5833 |  | 1729003 |  | 0
0
| Subtotal GE | [6 empty] | 34045616 |  | 0 |  | 34045616 |  | 26558830.75 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 26558830.75 |  | 0 |  | 7486785.25 |  | 34045616 |  | 0
| SPARE PARTS | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
[6 empty] | ENA | [37 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Major and BOP Equipment |  |  |  |  | Mitsui | Capital | 62560000 |  | 0 |  | 62560000 | [31 empty] | 0 |  | 0 |  | 62560000 |  | 62560000 |  | 0
[48 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [6 empty] | 62560000 |  | 0 |  | 62560000 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 62560000 |  | 62560000 |  | 0
| TOTAL MAJOR EQUIPMENT | [6 empty] | 96605616 |  | 0 |  | 96605616 |  | 26558830.75 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 26558830.75 |  | 0 |  | 70046785.25 |  | 96605616 |  | 0
MITSUI SITE CONSTRUCTION COSTS
[14 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
General Provisions
| LABOR |  |  |  |  | Mitsui | Capital | 6408000 |  |  |  | 6408000 | [31 empty] | 0 |  |  |  | 6408000 |  | 6408000 |  | 0
| MATERIALS |  |  |  |  | Mitsui | Capital | 14000000 |  |  |  | 14000000 | [31 empty] | 0 |  |  |  | 14000000 |  | 14000000 |  | 0
| ENGINEERING, PROJECT & CONTRUCTION MANAGEMENT, START-UP |  |  |  |  | Mitsui | Capital | 12600000 |  |  |  | 12600000 | [31 empty] | 0 |  |  |  | 12600000 |  | 12600000 |  | 0
| STORAGE & FINAL FREIGHT TO SITE |  |  |  |  | ENA | Capital | 300000 |  | 0 |  | 300000 | [31 empty] | 0 |  |  |  | 300000 |  | 300000 |  | 0
| IMPORT DUTIES |  |  |  |  | ENA | Capital | 5000000 |  |  |  | 5000000 | [31 empty] | 0 |  |  |  | 5000000 |  | 5000000 |  | 0
| BROKER & CUSTOMS FEES |  |  |  |  | ENA | Capital | 1099000 |  | 0 |  | 1099000 | [31 empty] | 0 |  | 0 |  | 1099000 |  | 1099000
| TOTAL General Provisions | [5 empty] | Capital | 39407000 |  | 0 |  | 39407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39407000 | 0 | 39407000 | 0 | 0
| BOP Procurement | [42 empty] | 0
| A/G PIPING |  |  |  |  | Mitsui |  | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| A/G ELENARICAL |  |  |  |  | Mitsui |  | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| INSTRUMENTATION |  |  |  |  | Mitsui |  | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| EQUIPMENT |  |  |  |  | Mitsui |  | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| TOTAL BOP Procurement | [5 empty] | Capital | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction
| SITE PREPARATION/IMPROVEMENTS - S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| SITE PREPARATION/IMPROVEMENTS - M | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| UNDERGROUND ELENARICAL - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| UNDERGROUND ELENARICAL - M | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| UNDERGROUND PIPING - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| UNDERGROUND PIPING - M | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| CONCRETE - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| CONCRETE - M | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| GROUT - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GROUT - M | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| STRUCTURAL STEEL - L | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| STRUCTURAL STEEL - M | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| ARCHITENAURAL -S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| BUILDINGS -S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| A/G PIPING - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| A/G ELENARICAL - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| INSTRUMENTATION - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| INSULATION & PAINTING -S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| MECHANICAL EQUIPMENT - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| PLANT STARTUP - L & S | [6 empty] | 0 |  |  |  | 0 | [31 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| BACKCHARGE | [42 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL Construction | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Switchyard
| ELECTRICAL INTERCONNECT |  |  |  |  | Mitsui | Capital | 3420000 |  |  |  | 3420000 | [31 empty] | 0 |  |  |  | 3420000 |  | 3420000 |  | 0
| TOTAL SWITCHYARD | [6 empty] | 3420000 |  |  |  | 3420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3420000 | 0 | 3420000 | 0 | 0
| TOTAL Mitsui SITE CONSTRUCTION COSTS | [6 empty] | 42827000 |  | 0 |  | 42827000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42827000 | 0 | 42827000 | 0 | 0 | #REF!
OVERHEADS & FEES
| EE& CC |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Mitsui |  |  |  |  | Mitsui | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| BASE FEE |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
[48 empty] | 0 |  |  |  | 0
| TOTAL OVERHEADS & FEES | [6 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
ADDERS OUTSIDE MITSUI SCOPE
| Other |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
| TOTAL ADDERS | [6 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
ENA PROJECT COSTS
MOBILIZATION OF O&M
| Mobilization Fee OEC |  |  |  |  | ENA | Capital | 2690000 |  | 0 |  | 2690000 | [31 empty] | 0 |  | 0 |  | 2690000 |  | 2690000 |  | 0
| Reimbursble Costs OEC | [5 empty] | Capital | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [6 empty] | 2690000 |  | 0 |  | 2690000 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 2690000 |  | 2690000 |  | 0
SALES TAX ON EQUIPMENT | [5 empty] | ENA | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
SPARE PARTS | [5 empty] | ENA | Capital | 3794995 |  | 0 |  | 3794995 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 3794995 |  | 3794995 |  | 0
LAND ACQUISITION
| Land Option |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 |  | 0 | [29 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| Title Commitment |  |  |  |  | ENA | Capital | 0 |  | 0 |  | 0 |  | 0 | [29 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ENA | Capital | 375000 |  | 0 |  | 375000 |  | 0 | [29 empty] | 0 |  |  |  | 375000 |  | 375000 |  | 0
| Subtotal Land Acquisition | [6 empty] | 375000 |  | 0 |  | 375000 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 375000 |  | 375000 |  | 0
ENVIRONMENTAL PERMITTING
| Air Permitting | [5 empty] | Expense | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Groundwater | [5 empty] | Expense | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Expense | 0 |  | 0 |  | 0 |  | 0 | 0 | [28 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Environmental Permitting | [6 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
POWER INTERCONNECTION | [5 empty] | ENA | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
GAS INTERCONNECTION | [5 empty] | ENA | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
START-UP FUEL
| Power Sales | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [6 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
INSURANCE DURING CONSTR | [6 empty] | Capital | 955000 |  | 0 |  | 955000 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 955000 |  | 955000 |  | 0
CAPITALIZED SALARIES | [6 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [24 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
DEVELOPMENT EXPENSES
| Development | [5 empty] | Expense | 3500000 |  | 0 |  | 3500000 |  | 1222715.444 | [29 empty] | 1222715.444 |  | 0 |  | 2277284.556 |  | 3500000 |  | 0
| Bank's Engineer | [5 empty] | Expense | 500000 |  | 0 |  | 500000 | [31 empty] | 0 |  | 0 |  | 500000 |  | 500000 |  | 0
| Lender's Out of Pocket | [5 empty] | Expense | 100000 |  | 0 |  | 100000 | [31 empty] | 0 |  | 0 |  | 100000 |  | 100000 |  | 0
| Owner's Engineer | [5 empty] | Expense | 100000 |  | 0 |  | 100000 | [31 empty] | 0 |  | 0 |  | 100000 |  | 100000 |  | 0
| Working Capital | [5 empty] | Expense | 250000 |  |  |  | 250000 | [31 empty] | 0 |  | 0 |  | 250000 |  | 250000 |  | 0
[44 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| TOTAL DEVELOPMENT EXPENSE | [6 empty] | 4450000 |  | 0 |  | 4450000 | 0 | 1222715.444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222715.444 | 0 | 0 | 0 | 3227284.556 | 0 | 4450000 | 0 | 0
LEGAL EXPENSES
| Total | [5 empty] | Expense | 2000000 |  | 0 |  | 2000000 |  | 442423.2 | [29 empty] | 442423.2 |  | 0 |  | 1557576.8 |  | 2000000 |  | 0
| Other | [5 empty] | Expense | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
[44 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [6 empty] | 2000000 | 0 | 0 | 0 | 2000000 |  | 442423.2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 442423.2 |  | 0 |  | 1557576.8 |  | 2000000 |  | 0
FINANCING DURING CONSTRUCTION
| Interest During Construction | [5 empty] | Capital | 13758138.2648 |  | 0 |  | 13758138.2648 | [35 empty] | 13758138.2648 |  | 13758138.2648 |  | 0
| Financing Fees | [5 empty] | Capital | 2196151.0696 |  | 0 |  | 2196151.0696 | [35 empty] | 2196151.0696 |  | 2196151.0696 |  | 0
| Commitment Fees | [5 empty] | Capital | 554550.013 |  | 0 |  | 554550.013 | [35 empty] | 554550.013 |  | 554550.013 |  | 0
0
| VAT Expense | [6 empty] | 21517166.0114 |  | 0 |  | 21517166.0114 | [35 empty] | 21517166.0114 |  | 21517166.0114 |  | 0
| VAT Recovery during Construction Draw | [6 empty] | -17331693.197 |  | 0 |  | -17331693.197 | [35 empty] | -17331693.197 |  | -17331693.197 |  | 0
ENA TOTAL PROJECT Costs | [7 empty] | 34959307.1619 |  |  |  | 34959307.1619 | 0 | 1665138.644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665138.644 | 0 | 0 | 0 | 33294168.5179 | 0 | 34959307.1619 | 0 | 0 | 0
CONTINGENCY | [6 empty] | Capital | 1500000 |  | 0 |  | 1500000 | [32 empty] | 2030320 |  | 2030320 | 1500000 | 2030320 | 1500000 | \ | 0
GRAND TOTAL | [7 empty] | 175891923.1619 |  | 0 |  | 175891923.1619 | 0 | 28223969.394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28223969.394 | 2030320 | 0 | 2030320 | 147667953.7679 | 2030320 | 175891923.1619 |  | 0
$/Kw | [7 empty] | 717.9262 |  |  |  | 717.9262 |  | 115.1999 | [29 empty] | 115.1999 |  |  |  | 602.7263 |  | 717.9262