## Cover
Confidential
Project Status / Historical Log
GPG Business Development
|  |  | Printed: | 2025-09-26 22:49
Distribution List:
S. Horton
R. Hayslett
B. Cordes
L. Deroin
R. Meyer
M. Moran
P. Lowry
S. Corman
S. Hotte
D. Schafer

## Active Projects
Active Projects
Project Name | Priority | Start |  | Amt | Working | Outside
(A.K.A.) | (1-5) | Date | Project Description | ($mm) | Group | Groups | Update | Issues
MOPS | 1 | 2000-01-01 | Divestiture - Of non-core offshore pipeline. | 10 | JNG - J. Harvey (NNG) | El Paso, NGPL, Williams, & FGT as owners. Blue Dolphin as prospective buyer. | Need waivers of ROFR from other owners - Proposals outstanding to both El Paso (acquisition of NGPL's MOPS interest pending) and Williams. Responses from both parties promised next week. | Waiver of ROFR from other owners.
Seagull Lateral | 1 | 2000-01-01 | Divestiture - Of non-core offshore pipeline. | 2.1 | JNG - J. Harvey (NNG), MK Miller (NNG) |  | Sales agreement signed, closing is pending non-jurisdictional declaration from FERC. Need withdrawal of protests from Anadarko and BP/Amoco to expedite at FERC. | FERC non-jurisdictional declaration.
Llano | 1 | 2000-05-01 | Acquisition - Invited by Agave to bid on LG&E assets - pipes, processing, gathering, and storage - in Texas, New Mexico, Oklahoma, and Montana. We are interested in the pipes and storage. | 140 | MLR - Storie (GPG), Harris (TW) | Agave | Evaluating information from data room. Seems to be a clean split of potential assets w/ Agave. Agave has good synergies w/ New Mexico assets. Enron re-group 5/15, discussions w/ Agave 5/17, site visit 5/18-19. Bid due June 10. | JV w/ Agave. Enron not invited to bid on its own.
StanCo | 1 | 2000-05-01 | Services - utility services with performance contracting Origination - Utility holding company with services provided by Enron. |  | SWS - Wade (ENA), Lowry (GPG), Hand (GPG) |  | Developing targeting list and operations services products. Determining service products and economics. | PUHCA, financing, contract structure.
Alaska (Arctic) | 2 | 2000-02-01 | Origination - Approx. $6bn pipeline from Prudhoe Bay offshore to Canada, then along the McKenzie River to Northern Alberta. | 6000 | SWS - Galassini (GPG), Junk (EE&CC), various (NBP) | MERC/ARC | Determine producer interest. Evaluate Enron participation in structure presented by ARC, and examine regulatory issues. Consider partnership with El Paso, Duke, or Williams. | Producer involvement, environmental, political.
Viking/Intrastate | 2 | 2000-03-01 | Acquisition - Gas transmission assets. | 95 | JNG - Cordes (NNG), McGowan (NNG) | Viking (Seller) | Model is in RAC for review. Cordes to arrange mtg. w/ Viking (JNG to attend). | Assets not formally offered for sale, but we would like to bid on them.
Sublette | 3 | 1999-02-01 | Divestiture - Of old, unused disposal well (and associated permits). | 0.2 | SWS - Nelson (NNG), Lowry (GPG) |  | Contact specific potential buyers locally. | O/M costs continue, need to sell or P&A soon.
Bimini/Grand Bahama LNG | 3 | 2000-03-01 | Origination - LNG Regas facility off Florida coast w/ pipeline into FGT system. Cost is about $200MM for the plant & $100MM for the pipe. | 300 | JNG - Parker (FGT), Galassini (GPG), Rotenberg (CALME), Detmering (ENA), Koye (CALME) | Aldridge | Six possible sites determined - 2 in Bahamas and 4 in Florida. Koye to preliminarily investigate sites, particularly Florida. JNG to deal w/ Aldridges role once site is narrowed. | OK'd by FGT regulations and corp. FPL has interest.
Market Hub Partners/Tejas Power (MHP/TCP) | 3 | 2000-04-01 | Acquisition - salt dome storage facilities at multiple locations, trading book, & energy management contracts . |  | SWS - Detmering (ENA), Bieniaswski (ENA) | NiSource | ENA is pursuing the analysis | Assets not formally offered for sale, NiSource is distracted with merger.
Volunteer Pipeline | 3 | 2000-05-01 | Origination - new pipeline into Southeastern US. |  | JNG - | Columbia, AGL Resources, MCN Energy | Supply and demand projections suggest that Canadian gas will be consumed in the northern part of the U.S. and will not be available for southeastern markets for atleast another couple of years.
Florabama (I & II) | 4 | 1999-07-01 | Origination - new pipeline across Mobile Bay, interconnecting with FGT at Flomaton, access to Mobile and Pensacola markets. | 200 | JNG - Fairley (ENA), Boatman (FGT), Hayes (FGT) |  | Monitor new developments with new markets identified by ENA/FGT, project may be justifiable in future. | Market used to $.10 transport (no more capacity), Florabama would need $.18-.20.
Farmland Slurry | 4 | 1999-08-01 | Origination - New/refurbished generation, private transmission line, with possible phosphate slurry pipeline. | 41 | JNG - Perisho (Consult), Walton (ENA) | Farmland Industries/Norsk Hydro JV | Perisho/Walton met with Farmland last week. Need to review strategy for going forward. | Farmland interest is uncertain (possible merger, etc).
Montana Power | 4 | 2000-04-01 | Acquisition - Gas transmission & distribution assets in Montana. |  | JNG - McGowan (NNG), Miller (NBP) |  | Need to establish level of interest with ET&S or NBP.
Independence Pipeline | 4 | 2000-05-01 | Origination - Independence is holding open season to attract non-affiliated shippers. ENA may sign up and will work with GPG to consider including a call option on an equity position in the pipe. |  | JNG - S. Miller (ENA), John Hodge (ENA) | ANR Pipeline
NiSource/Columbia | 4 | 2000-05-01 | Origination - Establish service alliance, and/or joint ownership position on Columbia Gulf & Columbia Transmission. |  | JNG - Metts (Corp), Detmering (ENA) | CS First Boston
Note on B3: MLR: 1 is hottest, 5 is dead.
Note on D3: MLR: Descriptions must start w/ Origination, Divestiture, Acquisition, or Investment. This is for organizational reasons.
Note on F3: MLR: These are people inside Enron.

## Admin. Activities
Administrative Activities
2025-09-26 22:49
| Priority | Start |  | Amt | Working | Outside | Due
Project Name | (1-5) | Date | Project Description | ($mm) | Group | Groups | Dates | Update | Issues
Executive Business Review | 1 | 2000-04-01 | Presentation detailing GPG business development activities and strategies. | Time | JNG, SWS, MLR |  | Due June 6. | Gather data on deals lost and what they are reselling for.
Strategic Model Development | 1 | 2000-01-01 | Develop/purchase North American supply demand model for evaluating potential projects, acquisition targets, candidates for divestiture etc. | Time, $$ | SWS - Kaminski & C. Vernon (Research), S. Miller (ENA), Carson (Corp) | Altos, EEA |  | Will undertake a short term project to evaluate various national studies done by NPC, INGAA, GRI, CERA, NEB, etc… to determine a consesus on outlook for industry. Analyze inputs for supply, demand and transportation for each of these studies and apply what is learned to Enron's internal modeling efforts.
Note on D4: MLR: Descriptions must start w/ Origination, Divestiture, Acquisition, or Investment. This is for organizational reasons.
Note on F4: MLR: These are people inside of Enron. The lead initials are from the Bus. Dev. Group.

## Historical Log
Historical Project Log
Project Name | Priority | Start |  | Winner's | Working | Outside |  | Enron | End
(A.K.A.) | (1-5) | Date | Project Description | bid ($MM) | Group | Groups | Conclusions | Bid | Date
Cove Point | 5 | 2000-03-01 | Acquisition - LNG terminal etc. from NiSource/Columbia. | Williams - $150 | JNG - Rotenberg (CALME), Detmering (ENA), Corman (GPG) | Columbia/NiSource (seller), Merrill Lynch | GPG ownership/operation of regulated facitilies, CALME and ENA to sponsor and provide economic justification. |  | Apr.-00
Common Directory | 5 | 2000-04-01 | Create a common directory for projects and documents. | Time | MLR - Tech Support |  | Directory, G:\GPGBusDev, has been set up. |  | 2000-05-01
Cristobol | 5 | 1999-08-01 | Divestiture & origination - pipe and wires (for-profit gas/electric transmission venture). |  | JNG - Maffett (ENA), Tapscott (ENA), Hayslett (GPG), Larson (Corp) | AEP, First Energy, Detroit Edison, Virginia Power, CMS | Little progress from power participants. Project viability in doubt. |  | 2000-05-01
Reliant (EWE2) | 5 | 2000-03-01 | Acquisition - Approx. $1.3bn purchase of 3 assets - REGT, MRT, Field Services (Original EOI for 5 assets were worth about $3 bn, about $1.8bn for REGT, MRT, REFS). | 200 | JNG - Cordes (NNG), Storie (GPG), Larson (Corp), Hayslett (GPG), Miller (NBP) | Reliant (Seller), Merrill Lynch | GPG decided not to bid as it could not justify what it thought was a competitive price, $1.7-1.8 bn. Financing mechanisms such as Condor and JEDI II were considered. Northern Border did not win, probably handicapped in bidding only for Field Services. | Did not bid, could only justify $1.3 bn offer which was not competitive. NBP bid various scenarios around $185-$190 MM. | 2000-05-01
Visual Intelligence | 5 | 2000-03-01 | Origination - Provide developmental funding for new venture invloved in digital aerial photography. | 25 | JNG - M. Lay (Corp), Horn (Corp) | M. Muckleroy sent offering summary to Ken Lay | Not interested. ENE not normally a "first round" investor. JNG referred them to the Houston Technology Center for assistance & funding. |  | 2000-04-01
ARCO (Pacific) | 5 | 2000-01-01 | Acquisition - Purchase of mid-cont. assets. | TEPPCO - $355 | JNG - Larson (Corp), Richards (EOTT), Miller (NBP) | Salomon Smith Barney | Asset package was scaled back midway thru the deal by Arco. Our bid was conservative due to uncertainty over future transported volumes. | $124mm + $50-75mm of upside efficiencies. | 2000-03-01
Bushton/Bushton Lease | 5 | 1999-09-01 | Acquisition - a repurchase of the Bushton plant, associated lease obligation, and various local gathering systems. | Oneok | JNG - Storie (NNG), Herber (NNG), Larson (Corp.) | Merrill Lynch | Did not bid, concluded obligations of lease exceeded value of business by $70-90 MM, therefore a negative net value. | Enron's EOI bid was flat (incl. Lease obligation) | 1999-12-01
Destin Pipeline | 5 | 1999-10-01 | Acquisition - El Paso 33 1/3% interest in offshore pipeline with access to deepwater. Mandated sale due to SoNat merger. | BP/Amoco - $160 | JNG - Saunders (FGT), Farrell (FGT), Burleson (NBP), Soldano (Legal) | DLJ | Did not bid. Concerns over possible conflicting interests with other partners, both major oil producers. |  | 1999-12-01
East Tennessee | 5 | 1999-10-01 | Acquisition - El Paso 100% interest in East Tennessee Natural Gas. | Duke - $386 | JNG - Saunders (FGT), Farrell (FGT), Burleson (NBP), Soldano (Legal) | DLJ | Limited upside, one major power expansion required $200 MM capital investment, could not source from NBPL. | 250 | 1999-12-01
Sea Robin Pipeline | 5 | 1999-10-01 | Acquistion - El Paso 100% interest in mature offshore pipeline. Mandated sale due to SoNat merger. | CMS - $72 | JNG - Saunders (FGT), Farrell (FGT), Burleson (NBP), Soldano (Legal) | DLJ | Did not bid. No viable access to deepwater play, so our valuation was not competitive. | 45 | 1999-12-01
Westar Transmission | 5 | 1999-09-01 | Acquisition - West Texas intrastate system and associated storage at Seymore, Texas. | Oneok | JNG - Storie (NNG), Herber (NNG), Larson (Corp.) | Merrill Lynch | Did not bid, ENA not enthusiastic since storage was fully subscribed, limiting upside potential. | Enron's EOI bid was $300-350 MM | 1999-12-01
Sunniland Storage | 5 | 1999-08-01 | Origination - new gas storage in south Florida in depleted oil reservoir (old Exxon field on Collier land). | 200 | JNG - Wilson (FGT), Tu (GPG) |  | 50 BCF reservoir not highest quality, limiting capacity (25 BCF) and in/out volumes, cost prohibitive in current market, may work in future. |  | 1999-10-01
Shock! | 5 | 1999-07-01 | Origination - Pipe and wires combination with Entergy. |  | JNG - Maffett (ENA), Tapscott (ENA), Hayslett (GPG), Larson (Corp) |  | No real interest from Entergy. |  | 1999-09-01
Kansas Pipeline | 5 | 1999-08-01 | Acquisition - small interstate pipeline into Kansas City market. | MidCoast Energy $180 | JNG - Fossum (NNG), Chandler (GPG) | Friedman, Billing, Ramsey,& Co. | Did not bid due to concerns over likely regulatory outcome of first rate case as a regulated pipe. | Valued at near $90 MM | 1999-08-01
Note on B3: MLR: 1 is hottest, 5 is dead.
Note on D3: MLR: Descriptions must start w/ Origination, Divestiture, Acquisition, or Investment. This is for organizational reasons.
Note on F3: MLR: These are people inside or outside of Enron.