## Sheet1
ReOrg Co Action Plan and Time Table
|  |  |  | Advisor | Enron
Task |  |  | Time Table | Responsibility | Responsibility
ReOrg Co Summary Business Plan
| B&P begins to develop summary Power Point presentation of business plan |  | 2/1 - 2/5 | B&P
| Meet with business unit heads to discuss vision of the future and growth story |  | 2002-02-05 | B&P
| Business Units to supply additional information and data to B&P |  | 2/5 - 2/6 |  | SH/JH/SJ
| Ensure projections for each business unit reflect all recent developments |  | 2002-02-06 |  | SH/JH/SJ
| B&P finish first draft of summary Power Point business plan, circulate to group |  | 2002-02-06 | B&P
| Meet with team, discuss and vet summary presentation |  | 2002-02-06 | B&P | SH/JH/SJ/MK/BB
| B&P to further refine presentation with assistance from business units |  | 2/7 - 2/8 | B&P | SH/JH/SJ/MK/BB
| B&P to distribute revised summary business plan to group/present to Jeff McMahon |  | 2002-02-08 | B&P
ReOrg Co Detailed Business Plan
| B&P to draft business plan detailed outline |  | 2002-02-05 | B&P
| B&P distribute detailed outline to Business Unit heads to begin drafting sections |  | 2002-02-06 | B&P
| Finalize ownership review of assets to be included in ReOrg Co |  | 2002-02-08 |  | Lance Schuler
| B&P to oversee draft of "ReOrg Co Sections" of business plan |  | 2/11 - 3/11 | B&P | SH/JH/SJ/MK/BB
|  | > Need macro energy and energy services trends in relevent markets |  | B&P | MK/BB
|  | > Need competitive SWOT analysis for ReOrg Co's competitors |  | B&P | MK/BB
| Business Unit Heads to complete all sections of business plans |  | 2/11 - 3/11 |  | SH/JH/SJ
| Business Units to complete 5 year financial projections, complete with income statements |  | 2/11 - 3/4 |  | SH/JH/SJ
balance sheets, cash flow statements and assumptions
| Finalize list of all assets within financial structures that impact ReOrg Co assets |  | 2002-02-13 | B&P | SH/JH/SJ/MK/BB
| Gather list of all significant creditors of each financial structure and the creditors' estimated |  | 2/6 - 2/12 |  | Bill Brown
amounts of debt at other Enron entities
| Meet to develop overall strategy for financial structure negotiations |  | 2002-02-14 | B&P/ZC | SH/JH/SJ/MK/BB
| Advisors to assess impediments to approval of ReOrg Co plan arising from inclusion/ |  | 2002-02-19 | B&P/ZC/Blackstone/WG
exclusion of certain assets
| Finalize strategy for financial structure assets / creditors |  | 2002-02-20 | B&P/ZC/Blackstone/WG
| Present desired plan on financial structures to applicable creditor groups |  | 2002-02-27 | Blackstone/ZC
| Begin determination of which assets trapped by financial structures will be available to |  | 2002-03-07 | Blackstone/ZC
ReOrg Co via negotiations with applicable creditor groups
| Business Unit Heads to submit drafts of sections to B&P |  | 3/1 - 3/11 |  | SH/JH/SJ
| Final date for financial projections |  | 2002-03-14 |  | SH/JH/SJ
| B&P accumulate all data, refine and edit |  | 3/11 - 3/17 | B&P
| B&P distribute draft business plan to working group |  | 2002-03-18 | B&P
| Meet with team, discuss and vet business plan |  | 2002-03-22 | B&P | SH/JH/SJ/MK/BB
| B&P incorporates comments from meeting, gathers additional information |  | 3/22 - 4/1 | B&P | SH/JH/SJ/MK/BB
| B&P to distribute revised version of business plan to group |  | 2002-04-01 | B&P
Valuation Analysis
| Determine final proposed assets to be included in ReOrg Co based on financial structure |  | 2002-04-01 | B&P | SH/JH/SJ/MK/BB
and entity review and business unit reviews
| B&P to refine trading and transaction comps used to value ReOrg Co |  | 4/1 - 4/10 | B&P
| Gather financial projections used in business plans for each business unit |  | 2002-04-01 | B&P
| Business unit heads to do final scrub of financial projections |  | 4/1 - 4/5 | B&P | SH/JH/SJ/MK/BB
| Obtain valuation input from Blackstone |  | 2002-04-05 | Blackstone
| B&P to further refine valuation model |  | 4/5 - 4/15 | B&P
| B&P to distribute valuation analysis to working group |  | 2002-04-16 | B&P
| Meet with group to discuss comments, questions |  | 2002-04-19 | B&P | SH/JH/SJ/MK/BB
| B&P to refine valuation analysis |  | 4/22 - 4/29 | B&P
| B&P to circulate valuation analysis to group |  | 2002-04-30 | B&P
Liquidation Analysis
| Determine final proposed assets to be included in ReOrg Co based on financial structure |  | 2002-04-01 | B&P | SH/JH/SJ/MK/BB
and entity review and business unit reviews
| B&P to further refine trading and transaction comps used to value separate businesses |  | 4/1 - 4/10 | B&P
| Gather financial projections used in business plans for each business unit |  | 2002-04-01 | B&P
| Business unit heads to do final scrub of financial projections and valuation estimates |  | 4/1 - 4/5 | B&P | SH/JH/SJ/MK/BB
| Obtain valuation input from Blackstone |  | 2002-04-05 | Blackstone
| B&P to further refine liquidation model |  | 4/5 - 4/15 | B&P
| B&P to distribute liquidation analysis to working group |  | 2002-04-16 | B&P
| Meet with group to discuss comments, questions |  | 2002-04-19 | B&P | SH/JH/SJ/MK/BB
| B&P to refine valuation analysis |  | 4/22 - 4/29 | B&P
| B&P to circulate valuation analysis to group |  | 2002-04-30 | B&P
Development of Capital Structure
| Determine required debt rating based on business needs |  | 2006-05-05 | B&P | SH/JH/SJ/MK/BB
| Analyze debt amount and structure necessary to meet debt rating requirements |  | 5/6 - 5/15 | B&P/Blackstone
| Review most cost efficient equity capital structures for integrated energy companies |  | 5/10 - 5/15 | B&P/Blackstone
based on current capital markets
| Establish proposed capital structure, prepare preliminary term sheets for each security |  | 5/15 - 5/20 | B&P/Blackstone
| Estimate valuation of capitalization components |  | 2002-05-24 | B&P/Blackstone