## Sheet1
Midwest Energy Hub L.L.C.
Business Items
Lead | Project | Description | Status
Legal Documents
| Hub Agency Agreement | MEH - PGL. MEH agent for existing PGL Hub. $50,000/month admin fee, 20% of profits. LLC termination at either Member's election after June 25 if no executed agreement. Needs to be submitted to ICC for approval. | Met 6/14. Made significant progress on legal and commercial issues. Enron counsel turning next draft on behalf of MEH week of 6/19.
| PERC Peaking Agency Agreement | MEH - PERC. MEH agent for PERC Peaking facility. Share profits equally (Enron/Peoples Energy) beyond transfer price. | No draft yet. Peoples will prepare first draft.
| Transfer Price Side Letter | MEH - PEC. Transfer price arrangement for Enhanced Hub Services. | Evaluating multiple alternatives for documenting transfer price.
| Third Party Master Purchase and Sale Agreement | MEH - Third Parties. Preferred agreement for physical transactions. | Peoples and Enron counsel working on form of agreement. Need MEH financial statements and parent guarantee information.
| GISB Agreement | MEH - Third Parties. Agreement for physical transactions with third parties that won't execute Master Purchase and Sale Agreement
| ISDA Agreements | MEH - Third Parties. Agreement for financial transactions. | No draft yet. Peoples and Enron counsel will work on form of agreement.
| Affiliate Master Purchase and Sale Agreement | MEH - PGL. Blanket filing with ICC for physical transactions. Individual transactions will be attached as confirmations. | Draft agreement prepared by Peoples.
| Confidentiality Agreements | CA's for employees working in the LLC. | Enron counsel presented draft CA to Peoples.
Policies and Procedures
| Risk Management Policy | Overriding risk policy establishing limits, notifications, approved traders, etc. LLC termination option at either Member's election until approved. | Turned draft to Peoples. Conference call with Peoples on Wednesday, 6/21. Peoples to turn redraft this week.
| Risk Procedures and Control Guidelines | Transaction process from deal inception to collection of receivable. LLC termination option at either Member's election until approved. | Preparing document for presentation to Peoples. Working with Peoples and Enron support teams to document process.
| Credit Policy | Approved counterparties, credit limits and ongoing credit process management. LLC termination option at either Member's election until approved. | Exchanged drafts with Peoples. Credit meeting set for 6/29 in Houston to discuss procedure and methodology.
Administrative
| Setup and fund bank account | Establish LLC bank account and make initial funding of $100,000 each. | LLC account has been setup at Citibank. Expect funding to occur closer to operational date.
| Cash management | Establish cash management procedure for LLC. Enron to manage working capital needs under revolver arrangement. | Enron cash management proposal being finalized this week to present to Peoples.
| Accounting | Establish financial reporting, including variance explanation, process, resolve any MTM issues, document audit procedures, etc. | Several meetings have been held. Audit process needs clarification. Other items need confirmation.
| Tax | Confirm tax treatment of LLC given anticipated business processes. | Need final tax review once business processes have been established.
| Qualify MEH | Qualify MEH to conduct business in Midwest states. | Completed in Illinois. Need to verify status of Indiana and other any states.
| Marketing materials | Prepare LLC marketing materials describing business, products and potential contracts. | Obtained and reviewing competitor materials. Lynn Pikofsky to coordinate effort with MEH marketing representatives.
| Final name of LLC | Decide if LLC will retain MEH name or change before contracts, marketing materials, etc are prepared. | Evaluating potential options for marketing value and legal availability.
| Marketing representative handout | Section 6.7.2 (c) of MEH Operating Agreement. Restricted activities for marketing reps. | Need to prepare.
SR-CC | Prepare schedules A & B | Section 6.7.2 (d) of MEH Operating Agreement. Grandfathered transations. | Schedule B (Peoples) - accumulating and summarizing deals on PEC side for initial draft. Waiting for PGL response on certain transactions. Schedule A (Enron) - Need to prepare.
| Appoint officers, Commercial Development Manager, Business Development Manager, alternate Board Members. | Need to put names with titles in MEH Operating Agreement. Determine need for officers and appointment of alternate board members. | Need to complete.
RT-SR | Audit existing book of business | Enron review of PGL hub and PERC transactions outstanding to date. Peoples review of Enron MW transactions (NSS). | Summarizing details of existing PERC and Hub deals and proceeding with Enron personel via Houston to input into Enron risk management system.
| Assess value of underlying assets | Examine rights and associated value of underlying assets, MTM issues, limits, etc.
| Initial Budget | Prepare operating budget and related marketing and operating plans by August 1st per MEH Operating Agreement. Determine cash flow requirements of LLC.
KR-PB | Back Office/Booking | Confirm readiness of back office functions to support transaction processes. | Deals are in Enron systems for NSS, ITS and EMW hub activity. Ready to work with the accountants to recognize P&L from our books.