## Sheet1
Midwest Energy Hub L.L.C.
Business Setup Items
Lead | Project | Updated | Description | Status
Legal Documents
RR-GP | Hub Agency Agreement | 2000-09-01 | MEH - PGL. MEH agent for existing PGL Hub. $50,000/month admin fee, 20% of profits. LLC termination at either Member's election after June 25 if no executed agreement. Needs to be submitted to ICC for approval. If satisfactory ICC approval is not received by 12/31/00, either member may elect to terminate the LLC. | Enron counsel draft turned 9/6. Meeting with PGL scheduled for next week.
TH-GP | PERC Peaking Agency Agreement | 2000-09-01 | MEH - PERC. MEH agent for PERC Peaking facility. Share profits equally (Enron/Peoples Energy) beyond transfer price. | No draft yet. Peoples will prepare first draft.
TH-GP | Transfer Price Side Letter | 2000-09-01 | MEH - PEC. Transfer price arrangement for Enhanced Hub Services. | Enron counsel preparing first draft, expected by 9/8.
RR-CC | Third Party Master Purchase and Sale Agreement | 2000-09-01 | MEH - Third Parties. Preferred agreement for physical transactions. | Completed as to general form. Need resolution on financial statements and form of parent guarantee. Prepared list of customers for presentation and mailing.
RR-CC | GISB Agreement | 2000-09-01 | MEH - Third Parties. Agreement for physical transactions with third parties that won't execute Master Purchase and Sale Agreement | Sent 6/21 to PEC legal for review.
RR-GP | ISDA Agreements | 2000-09-01 | MEH - Third Parties. Agreement for financial transactions. | Enron and PEC counsel and credit personnel working on forms for Schedule to Master Agreement and Paragraph 13 to Credit Support Annex.
RR-GP | Affiliate Master Purchase and Sale Agreement | 2000-09-01 | MEH - PGL. Blanket filing with ICC for physical transactions. Individual transactions will be attached as confirmations. | Fully executed. Peoples preparing petition for submission to the ICC.
TH-GP | Confidentiality Agreements | 2000-09-01 | CA's for employees working in the LLC. | Enron counsel presented draft CA to Peoples.
GP | LLC Loan Facility Agreement | 2000-09-01 | Establishment of a revolving credit facility from Enron to MEH. | Legal will prepare draft agreement after structure is determined by Enron RAC. Need Parent Guarantee from Peoples for their portion. Exploring implications of separate funding by Enron and PEC.
GP | Services Agreement | 2000-09-01 | Services Agreement for provision of cash management services from Enron Treasury to MEH. Potential need for global Services Agreement, with addendas for each service (Cash Management, Credit, Accounting, etc.) | Legal evaluating the different structure options.
Policies and Procedures
PB-GP | Risk Management Policy | 2000-09-01 | Overriding risk policy establishing limits, notifications, approved traders, etc. LLC termination option at either Member's election until approved. | Preparing presentation for PEC board. Waiting for PEC board response to latest draft.
PB-GP | Risk Procedures and Control Guidelines | 2000-09-01 | Transaction process from deal inception to collection of receivable. LLC termination option at either Member's election until approved. | Complete.
PB-GP | Credit Policy | 2000-09-01 | Approved counterparties, credit limits and ongoing credit process management. LLC termination option at either Member's election until approved. | Redrafting to clearly define roles and what constitutes an "approved" transaction.
Administrative
GP | Setup and fund bank account | 2000-09-01 | Establish LLC bank account and make initial funding of $100,000 each. | LLC account has been setup at Citibank. Expect funding to occur closer to operational date.
GP | Cash management | 2000-09-01 | Establish cash management procedure for LLC. Enron to manage working capital needs under revolver arrangement. | Exploring implications of separate funding. Enron still to manage daily disbusements. Meeting scheduled 9/8.
PB-GP | Accounting | 2000-09-01 | Establish financial reporting, including variance explanation, process, resolve any MTM issues, document audit procedures, etc. | EMW financials were prepared for 6/30. Kevin working closely with Tim Allen to ensure understanding. Continue discussions on MTM vs accrual.
PB-GP | Tax | 2000-09-01 | Confirm tax treatment of LLC given anticipated business processes. | Need final tax review once business processes have been established.
GP | Qualify MEH | 2000-09-01 | Qualify MEH to conduct business in Midwest states. | Completed in Illinois. Tax opinion that Illinois only state that currently has nexus, therefore no need to qualify in other states.
LP-CC-SR | Marketing materials | 2000-09-01 | Prepare LLC marketing materials describing business, products and potential contracts. | Done. Customer presentations have begun.
RM | Final name of LLC | 2000-09-01 | Decide if LLC will retain MEH name or change before contracts, marketing materials, etc are prepared. | Done. Enovate.
TH-GP | Marketing representative handout | 2000-09-01 | Section 6.7.2 (c) of MEH Operating Agreement. Restricted activities for marketing reps. | Draft prepared.
SR-CC | Prepare schedules A & B | 2000-09-01 | Section 6.7.2 (d) of MEH Operating Agreement. Grandfathered transations. If not approved by 6/25, either member may elect to terminate the LLC . | First draft complete for both. Need PEC to revise Schedule for existing transactions subject to sharing.
GP | Appoint officers, Commercial Development Manager, Business Development Manager, alternate Board Members. | 2000-09-01 | Need to put names with titles in MEH Operating Agreement. Determine need for officers and appointment of alternate board members. Name any designees for risk, credit or other reporting and control needs. | Need to complete.
RT-SR | Existing book of business | 2000-09-01 | Enron review of PGL hub and PERC transactions outstanding to date. Peoples review of Enron MW transactions. | Need to summarize details of existing PERC and Hub deals and input into Enron risk management system.
RT | Assess value of underlying assets | 2000-09-01 | Examine rights and associated value of underlying assets, MTM issues, limits, etc. Review and confirm treatment with PEC. | Need Enron structuring resource to perform this function.
| Initial Budget | 2000-09-01 | Prepare operating budget and related marketing and operating plans by August 1st per MEH Operating Agreement. Determine cash flow requirements of LLC. | First budget numbers due to Laura by 9/5. Aggregating numbers to determine overall business budget.
KR-PB | Back Office Support/Booking | 2000-09-01 | Confirm readiness of back office functions, including risk management, logistics, and accounting, to support transaction processes. | Deals are all in Enron systems. Calculating Daily P&L.