## B. Russell
# | Category | Finding | Action Item | Responsible Person | Target Date | Confirm Reviewer | Completion Date | Comments
PSM
26 | SPILL PLAN Regulation Condition | SPCC Plan does not have proper company name, and may not accurately describe current facility. Also, incomplete documentation of tank and containment inspections. | Update SPCC Plan. Maintain records of tank and containment inspections. | Butch Russell | 2001-03-31 | Rick Suderman
33 | HAZARDOUS WASTE Regulation Condition | An assessment of the area of the pipeline meter located in the northern portion of the Main Plant Area found elevated levels of mercury. | Determine extent of mercury contamination. | Butch Russell | 2001-06-30 | Rick Suderman
35 | HAZARDOUS WASTE Regulation Condition | Unknown whether abandoned concrete surface impoundment has ever been assessed for sub-surface soil contamination. | Verify closure of concrete surface impoundment for presence or absence of sub-surface soil contamination. | Butch Russell | 2001-06-30 | Rick Suderman
36 | HAZARDOUS WASTE Regulation Condition | An assessment documented mercury contamination in vicinity of former meter shop. | Develop plan to address mercury contamination. | Butch Russell | 2001-06-30 | Larry Campbell
37 | HAZARDOUS WASTE Regulation Condition | An assessment of the loading rack documented hydrocarbon levels at concentrations exceeding action levels established by the Kern County Environmental Health Services Department. | Develop plan to address hydrocarbon contamination. | Butch Russell | 2001-06-30 | Larry Campbell