## Sheet1
For Internal Use Only
Interstate Pipeline Capacity to California Report
Revised: 06/14/01
| Date: |  |  |  |  | Contract
Pipeline/ | Announced (A) | Docket | Capacity |  | Estimated | Status | Projected
Project | Filed (F) | No. | (Mmcf/d) | Del. Pt. | Costs (Millions) | (Mmcf/d) | In-Service Date | Status/Comments
Transwestern Pipeline Co. | 03/29/01 (F) | CP01-115 | 150 | Topock, Calpine & | 93.3 | 84.2 | 2002-06-01 | Finalizing contracts, environmental permitting ongoing.
Red Rocks Expansion |  |  |  | Needles
Kinder-Morgan/ | 05/03/01 (A) | N/A | Ph. I 750 | Needles | Ph. I $624 | Ph. I 400 | Summer 2003 | To be filed upon finalizng precedent agreements. Open Season ended June, 1, 2001.
Calpine-Sonoran Pipeline |  |  | Ph II 1000 |  | Ph. II $1.1 billion | Ph. II 500 | Yet TBD
PG&E GT NW | 05/07/01 (A) | N/A | 300-500 | Malin |  | N/A | 2003-11-01 | Open Season ends June 19, 2001.
PG&E GT NW | 04/02/0l (F) | CP01-141 | 211 | Malin | 122 |  | Ph. I Nov-01
2002 Expansion | [6 empty] | Ph. II Sum. 02
El Paso Line No. 2000 | 07/31/00 (F) | CP00-422-000 | 230 | Ehrenberg | 153.1 | None | 2001-08-01 | Certificate Issued 5/7/01. Capacity will be used for system flexiblity and to reduce daily allocations.
| 03/15/01 (F) | CP00-422-001
Kern River 2002 | 11/15/00 (F) | CP01-31-000 | 124 | Wheeler Ridge | 80 |  | 2002-05-01 | KRGT amended its Cert. App. To certificate emergency capacity.
| 05/11/00 (F) | CP01-31-001
Kern River CA Action | 03/15/01 (F) | CP01-106-000 | 135 | Wheeler Ridge | 81 |  | 2001-07-01 | Received Commission Order 4/6/01.
Kern River 2003 | 03/22/01 (A) | N/A | 900 | CA Border | >$1 billion | N/A | 2003-05-01 | Plan to file an application with FERC in June.
Questar - Southern Trails | 01/19/99 (F) | CP99-163-000 | East Zone 87.5 | Topock | 155 |  | 2001-12-01 | Received Commission Order 7/28/00.
|  | CP99-163-001 | West Zone 120 |  |  |  | 2002-07-01
North Baja Pipeline | 11/1/00 (F) | CP01-22 | 500 | Ehrenberg to | 146 |  | 2002-09-01 | Received Preliminary Determination of Non-Env. Issues on 5/18/01.
Ogilby, MX
Otay Mesa Gen. Co. | 4/6/01 (F) | CP01-145 | 110 | MX/CA Border | N/A |  | 2002-09-01 | North Baja Pipeline gas for delivery to Otay Mesa Gen. Plant near San Diego.