## Sheet1
ISSUE | LEVEL OF BUSINESS PRIORTY (1= High, 5 = Low) | OBJECTIVES | ACTIONS | FORUM | TARGET DATE | ENRON VISIBILITY | LIKELIHOOD
REGULATORY/POLITICAL
*****RETAIL*****
1. PUC APPOINTMENT | 1 | Pro-competition commissioner | Find candidates | Governor's Office | Q1/2001 | MEDIUM | 5%
Focus media on importance
Build coalition around candidate
2. RETAIL PRICE FREEZE | 1 | Promote choice & maximize EES book value | Develop proposal to address hydro, undercollect, rate freeze | PUC, Legislature, Media, Governor | Q2/2001 | HIGH | 25%
CTC ROLL OFF |  |  | Work w/coalition & PG&E to support Enron proposal
UNDERCOLLECTION |  |  | Educate PUC and Legislature
HYDRO VALUATION |  |  | Educate the press
Speaking engagements
Target nontraditional consumer groups
Hire PR firm
Get AB 1890 group on our side
3. UTILITY PROCUREMENT | 2 |  |  |  |  | MEDIUM
DEFAULT PROVIDER |  | Competitive Default Provider | Coalition of retailers, wholesalers, IOUs and customers to support | Legislature, PUC, Media, Governor | Q1/2003 |  | 35%
OUT OF MERCHANT FUNCTION |  | IOU out for C&I | Coalition of retailers, wholesalers, IOUs and customers to support | Legislature, PUC, Media, Governor | Q1/2002 |  | 40%
FORWARD MARKET |  | IOU gets unlimited flexibility & 100% at risk under fixed price | Coalition of retailers, wholesalers, IOUs and customers to support | PUC, Media, FERC | Q1/2002 |  | 25%
4. DEMAND RESPONSIVENESS | 3 |  |  |  |  | LOW
ISO PROGRAM |  | Remove all ISO barriers to demand responsiveness (e.g., metering requirements, 10 minute settlements) | Develop a proposal | ISO | Q1/2001 |  | 60%
Shop proposal to ISO staff
Build coalition to support
5. DG | 4 | Remove major regulatory barriers at PUC/ISO | Remain active in CPUC/CEC/ISO/FERC proceedings | CPUC, CEC, ISO, FERC, Legislature | Q2/2001 | LOW | 50%
6. INFORMATION | 4 | Transparent distribution operation (e.g., losses, congestion, maintenance, etc.) |  |  |  | LOW
*****WHOLESALE*****
7. WHOLESALE PRICE CAPS | 1 | 1.Eliminate them | Change governance | ISO, Legislature, FERC, Courts | Q3/2001 | HIGH | 0%
Work w/Wolak
Work w/ISO and PX
Prominent economist papers
Presentations to ISO board
Informal lobbying of board members
Build anti-merger coalitions
AB 1890 Implementation Group
IEP
WPTF
Customers
Speak at conferences
Petition FERC
Educate PUC
Educate Legislature
|  | 2. Raise caps | Same as #1 | ISO, Legislature, FERC, Courts | Q3/2001 |  | 10%
|  | 3. No lower | Same as #1 | ISO, Legislature, FERC, Courts | Q3/2001 |  | 50%
8. ISO/PX GOVERNANCE | 2 | 1. Eastern ISO model | Continue with court case | Legislature, Courts | Q3/2001 | MEDIUM | 15%
Educate/lobby legislature
Work with coalition to propose legislation
Work with utilities
Persuade ISO to petition FERC
Use as chit in SW RTO negotiations
|  | 2. NEEPOOL model | Persuade ISO to petition FERC | Legislature, FERC | Q3/2001 |  | 15%
9. ISO/PX MERGER | 2 | Retain separation | Work w/Wolak | Legislature, FERC | 2001 | HIGH | 50%
Work w/ISO and PX
Prominent economist papers
Presentations to ISO board
Informal lobbying of board members
Build anti-merger coalitions
AB 1890 Implementation Group
IEP
WPTF
Customers
Speak at conferences
Petition FERC
Educate PUC
Educate Legislature
10. INFORMATION | 1 | More, sooner | Presentations to ISO board | ISO, PUC | Q2/2001 | HIGH | 75%
Work w/ISO staff
Informal lobbying of board members
Continue in FERC forums
Work w/Wolak
Educate PUC
Prominent economist papers
11. INVESTIGATIONS | 1 | No Retroactive Payments | Understand Enron trading practices | CA AG; CPUC; EOB; ISO; PX; FERC; CA auditor general | Q4/2000 | HIGH
PR questionning CA focus on investigations (witch hunts)
Gather intelligence
White paper by economist on market behavior
Offensive PR shining light on all participants' behavior?
|  | Get FERC to adopt Enron proposals | Work with Portland and DC | FERC | Q2/2001 |  | 20%
12. INTERCONNECTION |  |  | Educate FERC staff on Enron proposals
DG | 3 | Remove barriers | Stay active at CPUC/CEC | PUC/CEC/Legislature | Q4/2001 | HIGH | 50%
Lobby PUC to adopt CEC recommendations
Educate legislature
LARGE PLANTS | 1 | Get IOUs out | Propose in FERC investigation |  | Q2/2001 | HIGH | 40%
File 203 complaint?
Make proposal to ISO to take IOUs out?
13. PLANT SITING | 1 | Get Enron-proposed changes in clean-up bill | Work with Legislature | Legislature/CEC | Q2/2001 | HIGH | 50%
Develop coalition (IEP)
Develop PR strategy
Get CEC on our side and out in front
14. FORWARD MARKETS | 2 | Keep ISO out | Stay active at HEPG | HEPG, FERC, PUC, Legislature, ISO, PX | Q4/2001 | MEDIUM | 40%
|  | Get IOUs in | Fight Amendment 30 at FERC
|  | Promote alternatives to PX | Educate FERC Comm's and staff
See actions under "PX/ISO Merger"
Work PUC OII to permit alternative exchanges & end PX buy requirement
Educate legislature
15. TRANSMISSION
CONGESTION MANAGEMENT | 2 | Get ISO CM plan approved by FERC; prevent LMP | Lobby ISO Board; work with ISO staff; build coalition; educate FERC staff;meet with FERC Comm's; | FERC, ISO, EOB | Q1/2001 |  | 60%
FTRS | 2 | Finish the job | Lobby ISO Board; work with ISO staff; build coalition; educate FERC staff;meet with FERC Comm's; | FERC, ISO, EOB | Q1/2001 |  | 60%
RTOS | 3 | Fight ISO's contention at FERC that it is an RTO | Lobby ISO Board and staff; work with FERC team | FERC, ISO, EOB | Q3/2001 |  | 50%
NATIVE LOAD (imports into CA) | ? | Get rid of it | Work with Portland and DC and Houston | FERC/Congress | Q4/2001 |  | 20%
COMMERCIAL
1. UTILITY OUTSOURCE DEALS
2. RETAIL SWAT TEAMS
3. QF BUYOUTS
4. EES BOOK RISK MANAGEMENT
5. EES CURVE SUPPORT
6. POWER PLANT DEALS
7. MARKET INTELLIGENCE