## Sheet1
ISSUE | LEVEL OF BUSINESS PRIORTY (1= High, 5 = Low) | OBJECTIVES | ACTIONS | FORUM | TARGET DATE | ENRON VISIBILITY (*) | LIKELIHOOD (Achieve 100% of objective by target date)
HIGHEST PRIORITY ISSUES
***WHOLESALE PRICE CAPS*** | 1 | 1.Eliminate them | a. Change governance | ISO, Legislature, FERC, Courts | Q3/2001 | HIGH | 0%
b. Work w/Wolak
c. Work w/ISO and PX
d. Prominent economist papers
e. Presentations to ISO board
f. Informal lobbying of board members
g. Build anti-merger coalitions
AB 1890 Implementation Group
IEP
WPTF
Customers
h. Speak at conferences
i. Petition FERC
j. Educate PUC
k. Educate Legislature
|  | 2. Raise caps | Same as #1 | ISO, Legislature, FERC, Courts | Q3/2001 |  | 10%
|  | 3. No lower | Same as #1 | ISO, Legislature, FERC, Courts | Q3/2001 |  | 50%
***INVESTIGATIONS*** | 1 | 1. No Retroactive Ratemaking | a. Understand Enron trading practices | CA AG; CPUC; EOB; ISO; PX; FERC; CA auditor general | Q4/2000 | HIGH | 75%
b. PR questionning CA focus on investigations (witch hunts)
Gather intelligence
c. White paper by economist on market behavior
d. Ensure that behavior of all market participants' is scrutinized
|  | 2. Get FERC to adopt Enron proposals | a. Work with Portland and DC | FERC | Q2/2001 |  | 20%
***SOLUTIONS FOR PG&E & EDISON*** | 1 | Promote choice, maximize EES book value & pursue deals | a. Develop proposal to address hydro, undercollect, rate freeze | PUC, Legislature, Media, Governor | Q2/2001 | HIGH | 25%
CTC ROLL OFF, OUTSOURCE, UNDERCOLLECTION & HYDRO |  |  | b. Approach PG&E w/proposal
c. Work w/coalition & PG&E to support Enron proposal
d. Educate PUC and Legislature
e. Educate the press
f. Speaking engagements
g. Target nontraditional consumer groups
h .Get AB 1890 group on our side
***INFORMATION*** | 1 | Get more released to the market, sooner | a. Presentations to ISO board | ISO, PUC, FERC | Q2/2001 | HIGH | 75%
b. Work w/ISO staff
c. Informal lobbying of board members
d. Continue in FERC forums
e. Work w/Frank Wolak
f. Educate PUC
g. Prominent economist papers
***PUC APPOINTMENT*** | 1 | Pro-competition commissioner | a. Find candidates (x-leg; semi-retired biz folks) | Governor's Office | Q1/2001 | LOW | 10%
b. Work w/Lynch-Kahn-Wood
c. Build coalition around candidate
OTHER IMPORTANT ISSUES
***PROVIDE REGULATORY INTELLIGENCE/EXPERTISE TO SUPPORT COMMERCIAL DEALS*** | 1 | Add value to & minimize regulate risk of deals | Continue deal and rate curve support. | Stay abreast of activities of CPUC, FERC, ISO, PX, EOB, CEC, etc. | On-going | NA | NA
RETAIL ISSUES
***UTILITY PROCUREMENT*** | 3 |  |  |  |  | MEDIUM
DEFAULT PROVIDER |  | 1. Competitive Default Provider | Coalition of retailers, wholesalers, IOUs and customers to support | Legislature, PUC, Media, Governor | Q1/2003 |  | 35%
OUT OF MERCHANT FUNCTION |  | 2. IOU out for C&I | Coalition of retailers, wholesalers, IOUs and customers to support | Legislature, PUC, Media, Governor | Q1/2002 |  | 40%
FORWARD MARKET FOCUS |  | 3. IOU gets unlimited flexibility & 100% at risk under fixed price | Coalition of retailers, wholesalers, IOUs and customers to support | PUC, Media, FERC | Q1/2002 |  | 25%
***DEMAND RESPONSIVENESS*** | 5
ISO PROGRAM |  | Remove all ISO barriers to demand responsiveness (e.g., metering requirements, 10 minute settlements) | a. Develop a proposal | ISO (Staff and Board) | Q1/2001 | LOW | 60%
b. hop proposal to ISO staff
c. Build coalition to support
***DISTRIBUTED GENERATION*** | 5 | Remove major regulatory barriers at PUC/ISO | a. Remain active in CPUC/CEC/ISO/FERC proceedings | CPUC, CEC, ISO, FERC, Legislature | Q2/2001 | LOW | 50%
b. Need consultant for ISO?
***INFORMATION*** | 5 | Transparent distribution operation (e.g., losses, congestion, maintenance, etc.) | Finish up DG proceeding at PUC on distribution wheeling | CPUC | Q2/2001 | HIGH | 35%
WHOLESALE ISSUES
***ISO/PX GOVERNANCE*** | 3 | 1. Eastern ISO model | a. Continue with court case | Legislature, Courts, FERC | Q3/2001 | MEDIUM | 15%
b. Educate/lobby legislature
c. Work with coalition to propose legislation
d. Work with utilities
e. Persuade ISO to petition FERC
f. Use as chit in SW RTO negotiations
|  | 2. NEEPOOL model | g. Persuade ISO to petition FERC | Legislature, FERC | Q3/2001 |  | 15%
***ISO/PX MERGER*** | 3 | Retain separation | a. Work w/Wolak | Legislature, FERC | 2001 | HIGH | 50%
b. Work w/ISO and PX
c. Prominent economist papers
d. Presentations to ISO board
e. Informal lobbying of board members
f. Build anti-merger coalitions
AB 1890 Implementation Group
IEP
WPTF
Customers
g. Speak at conferences
h. Petition FERC
i. Educate PUC
j .Educate Legislature
***INTERCONNECTION***
DISTRIBUTED GENERATION | 4 | 1. Remove barriers | a. Educate FERC staff on Enron proposals | PUC/CEC/Legislature | Q4/2001 | HIGH | 50%
b. Stay active at CPUC/CEC
c. Lobby PUC to adopt CEC recommendations
LARGE PLANTS | 2 | 2. Get IOUs out; get ISO in; standardize interconnection | a. Propose in FERC investigation |  | Q2/2001 | HIGH | 15%
b. File 211 or 202 b request?
c. Make proposal to ISO to take IOUs out?
***PLANT SITING*** | 2 | 1. Get Enron-proposed changes in clean-up bill | a. Work with Legislature | Legislature/CEC | Q2/2001 | HIGH | 50%
b. Develop coalition (IEP)
c. Develop PR strategy
d. Get CEC on our side and out in front
***FORWARD MARKETS*** | 3 | 1. Keep ISO out | a. Stay active at HEPG | HEPG, FERC, PUC, Legislature, ISO, PX | Q4/2001 | MEDIUM | 40%
|  | 2. Get IOUs in | b. Fight Amendment 30 at FERC
|  | 3. Promote alternatives to PX | c. Educate FERC Commission and staff
d. See actions under "PX/ISO Merger"
e. Work PUC OII to permit alternative exchanges & end PX buy requirement
f. Educate legislature
***TRANSMISSION***
CONGESTION MANAGEMENT | 3 | Get ISO CM plan approved by FERC; prevent LMP | Lobby ISO Board; work with ISO staff; build coalition; educate FERC staff;meet with FERC Comm's; | FERC, ISO, EOB | Q1/2001 |  | 60%
FTRS | 3 | Finish the job | Lobby ISO Board; work with ISO staff; build coalition; educate FERC staff;meet with FERC Comm's; | FERC, ISO, EOB | Q1/2001 |  | 60%
RTOS | 4 | Fight ISO's contention at FERC that it is an RTO | Lobby ISO Board and staff; work with FERC team | FERC, ISO, EOB | Q3/2001 |  | 50%
NATIVE LOAD (imports into CA) | 2 | Get rid of it | Work with Portland and DC and Houston | FERC/Congress | Q4/2001 |  | 10%