## Active Plogs
Plog# | Function | Description of Problem/Enhancement | Reported By/Date | Assigned To/Date | Priority | Comments | Release Date | Retested | by
83 | Reports | Not looking at Point date ranges | Perry 01/18 | Lori |  | In Model Office | 2002-02-04
84 | Evaluation | When reducing quantity at a point causes groups r/d adj. To be reduced also | Don | Benito
85 | Timeout | Receiving error message | Perry 01/30 |  |  | Need screen print of error message - timeout is set at 12 hours
86 | Date range selection | Year selection set at 365 days | Perry 01/30 | Steven |  | Remove limitation of 1 Year on Inquiry
87 | Reports | Default date to current date | Perry 2/1
88 | Post Capacity | Allow for on-demand schedule to post Capacity to the Web | Perry 2/1 |  |  | Interim Solution-Setup procedures with DBA, impl permanent solution with FGT CAS
89 | Evaluation | Bi-Directional/ in/out thru a segment | Mktrs 2/1 |  |  | Meeting to be scheduled to discuss impact
90 | Testing | Speed up testing when changes made | Don 2/1 |  |  | Create test scripts for evaluation and calculation of groups and points

## Completed Plogs
Plog# | Function | Description of Problem | Reported By/Date | Assigned To/Date | Priority | Comments | Release Date | Retested | by
1 | Display | Company name Mis-spelled | Ramona 1/26 | Steven 1/26 |  | Scheduled for next release | 2001-02-05 | 2001-02-21 | LT
2 | Backhaul Selection | Backhaul selection should not display on Operational or Design header frame | Ramona 1/26 | Jerry 1/26 |  | Will be corrected when PLE interface complete |  | 2001-02-21 | LT
3 | Retrieve | When retrieve depressed, nothing happens on Point Operational Capacity | Ramona 1/26 | Jerry 1/26 |  | Depress again, get focus corrected, scheduled for next release | 2001-02-05 | 2001-02-21 | LT
4 | Delete | Deletes all date ranges on Point Operation Capacity, should not apply deletes on historical data | Ramona 1/29 | Jerry 1/29 |  | Developer cannot duplicate, Get with User to re-create scenario |  | 2001-02-21 | LT
5 | Display | Start/End month not valid on frame for Operational or Design | Ramona 1/29 | Jerry 1/29 |  | Scheduled for next release | 2001-02-05 | 2001-02-21 | LT
6 | Maint | Cannot add Group in Group/Poi Maintenance | Ramona 1/29 | Jerry 1/29 |  | re-test | 2001-03-14 | 2001-03-21 | Ramona
7 | Delete | Database error displayed when attempt to delete comments | Ramona 1/29 | Benito 1/29 |  | Store Procedure Corrected ,re-test |  | 2001-02-21 | LT
8 | Add | Termed previous comments, added new comments - Database error permission denied | Linda 1/31 | Benito 1/31 |  | DBA granted access - re-test |  | 2001-02-21 | LT
9 | Entry | Have to enter / when entering dates, request to have system format date | Darrell 2/1 | Jerry 2/1 |  | Same as PLOG #28 | 2001-02-05 | 2001-02-21 | LT
10 | Display | Change field names to be consistent with GISB and TMS | Mary Draemer 2/6 |  |  | Same as PLOG #30 |  | 2001-02-28 | LT
11 | Function | Received error when keying in a group number and pressing the enter key on the group oper. Cap. Screen | Mary Draemer 2/6 | Jerry 2/6 |  | Re-tested by M. Draemer - okay |  | 2001-02-06 | LT | Mary | 2001-02-06
12 | Entry | Applied and saved volume date range with role of delivery - saved with role of receipt. | Mary Draemer 2/6 |  |  | Re-test | 2001-03-04 | 2001-03-19 | Mary
13 | Display | Duplicate lines displaying | Mary Draemer 2/7 |  |  | Re-test | 2001-03-04 | 2001-03-19 | Mary
14 | Display | Need error message for invalid date entry | Mary Draemer 2/7 |  |  | Re-test | 2001-03-04 | 2001-03-19 | Mary
16 | Delete | Can't delete multiple lines at the same time | Mary D. 2/7 |  |  | Not available due to current design structure- Close
17 | Entry | Pressed enter key and received the message below. | Mary D. 2/15 | Benito 2/15 |  | Re-test |  | 2001-02-11 | Closed | Mary | 2001-02-11
18 | Display | Duplicate lines displaying | Mary D. 2/15 | Benito 2/15 |  | Re-test | 2001-02-14 | LT
19 | Error | Tried to delete line items, received error message | Mary D. 2/15 | Benito 2/15 |  | Re-test | 2001-02-14 | LT
20 | Display | Received error message | Mary D. 2/15 | Benito 2/15 |  | Re-test | 2001-02-14 | LT
21 | Entry | Duplicate of P-log #12 | Mary D. 2/16
22 | Entry | Submitted a line without applying first | Mary D. 2/16 |  |  | Item not applied, system does not know about them - you have to hit apply and then submit | 2001-02-26 | LT | Closed
23 | Delete | Deleted several lines and then clicked on menu items - hit okay on message and received error message | Mary D. 2/16 |  |  | Re-test | 2001-02-26 | LT | Closed
24 | Display | Keyed in data, then deleted, then hit submit - received update sucessful when nothing was saved. | Mary D. 2/16 |  |  | System is processing changes that you applied - will look into changing message | 2001-02-26 | LT | Closed
25 | Error | Not recog. Duplicate lines | Mary & Linda 2/20 |  |  | Migrated to model office - ready to retest | 2001-02-26 | LT | Closed
26 | Error | Added split record, hit submit and received error message | Linda 2/20 |  |  |  | 2001-02-26 | LT | Closed
27 | Entry | Terminated record in future, received error | Linda 2/20 |  |  | Not error - operator error | 2001-02-20 | LT | Closed
28 | Date | Does not take 02202001 | Linda 2/20 |  |  | Have to put in /, a space or mm dd yyyy - working on other ways | 2001-02-20 | LT | Closed
29 | Error | Received error message when retrieving point 10487 - script error | Mary D. - 2/26 |  |  | User had version 4.0 of Internet Explorer - upgraded to 5.0 | 2001-02-26 | LT | Closed
31 | Reports | Users request select criteria before running report | Gerry 2/26 |  |  | Re-test | 2001-02-27 | 2001-03-19 | Gerry
32 | Entry | User requests removal of 2 step entry process - doesn't want add, change, delete and then submit buttons | Darrell 2/26 |  |  | The system was designed this way in order to minimize the number of times the front end updates the backend and maximize response time.
33 | Error | Received error message when deleting items and then switching to another menu item | Mary 2/26 |  |  | Re-test | 2001-03-01 | 2001-03-19 | Mary
34 | Error | Error received when saving associated group | Gerry 2/27 |  |  | The associate function is for NNG. Not to be tested at this time. | 2001-02-27 | LT | Closed
35 | Entry | Point and group oper. Capacity will not accept '0' | Darrell 2/28 |  |  | Migrating to model office the evening of 3/1 | 2001-03-01 | 2001-03-19 | Darrell
36 | Wizard | Does not clear previous search criteria on wizard | Mary 2/27 |  |  | Migrating to model office the evening of 3/1 | 2001-03-01 | 2001-03-19 | Mary
37 | Error | While looking up a name contains on wizard received error | Mary 2/27 |  |  | Migrating to model office the evening of 3/1 | 2001-03-01 | 2001-03-19 | Mary
38 | Wizard | Performing lookup on point range where there were no valid points, received error | Mary 2/27 |  |  | Migrating to model office the evening of 3/1 | 2001-03-01 | 2001-03-19 | Mary
39 | Entry | Cursor should auto be highlighted in the box for typing | Darrell 2/28 |  |  | Migrating to model office the evening of 3/1 | 2001-03-01 | 2001-03-21 | Darrell
40 | Entry | Need ablility to change historical operational data | Darrell 2/28? |  |  | Migrating to model office the evening of 3/1
41 | Display | Cannot scroll down the list of operational groups | Ramona 2/28 |  |  | Migrated to Model Office 3/14 | 2001-03-14 | 2001-03-20 | Ramona
42 | Display | Only show operation groups from TCI | Ramona 2/28 |  |  | Common groups will be utilized where possible- Closed
43 | Display | Dates are cut off on screens - enlarge date box | Ramona 2/28 |  |  | Migrated to Model Office 3/14 | 2001-03-14 | 2001-03-19 | Ramona
44 | Data | Check conversion data | Ramona 2/28 |  |  | Reloaded data from TCI system - closed
45 | Display | Scroll bar not showing on point operational capacity | Ramona 2/28 |  |  | Re-test | 2001-03-04 | 2001-03-21 | Ramona
46 | Interface | Received ORB in TMS allocation | Ramona 3/2 |  |  | Re-test |  | 2001-03-20 | Ramona
47 | Interface | Show user ID, not conversion ID, when entering oper. Cap from TMS side | Ramona 3/2 |  |  | Migrated to Model Office 3/14 | 2001-03-14 | 2001-03-21 | Ramona
48 | Data | Able to pull up NNG on drop down box for TSP | Maggie 3/2 |  |  | You cannot select other companies in production - only TW. Closed
49 | Entry | When closing app the first attempt to re-open by clicking "Enter CAS application" you get a blank screen | Maggie 3/2 |  |  | This only occurs in model office - you do not get this screen in production
50 | Data | TW & NNG points showing up | Maggie 3/2 |  |  | Migrated to Model Office 3/14 | 2001-03-14 | 2001-03-21 | Linda
51 | Wizard | When trying to pull a point in a group in the wizard it should give you a message telling the user the group number does not exist | Maggie 3/2 |  |  | The system returned a message "no record found" - closed
52 | Entry | Updated capacity in TMS - should update CAS oper. Cap with the new capacity for that date only | Ramona 3/2 |  |  | User entered the same operation capacity for a date that already existed. The system did what is was suppose to do. Closed.
54 | Entry | Tried to change a capacity for a month without selecting a specific day - received a saved successfully message | Maggie 3/2 |  |  | System acknowledges the apply even though you did not pick anything - closed.
55 | Entry | Should not be able to change history | Ramona 3/2 |  |  | Migrated to Model Office 3/14 | 2001-03-14 | 2001-03-21 | Ramona
56 | Error | Received error message when trying to retrieve poi 10487 | Ramona 3/2 |  |  | Re-test, Could not re-create in model office - error was Internet Explorer message |  | 2001-03-19 | Ramona
57 | Interface | Amendments for alternate points are going to CAS for approval - they should not be | Linda 3/5 |  |  | Re-test, migrated to Model Office | 2001-03-16 | 2001-03-21 | Dale
58 | Interface | Voided requests from CBS are not backing out volumes in CAS | Don 3/5 |  |  | Re-test
59 | Wizard | Error-failed getting PLE point | Ramona 3/12 |  |  | Re-test - Sybase Server problem | 2001-03-12 | 2001-03-19 | Ramona
60 | View | Pool Points & Zone Points can be updated for operational capacity | Mary 3/6 |  |  | Would not set a capacity,TMS does not use Operational values at Pools/Zones - CLOSE
61 | Remove | Removed Poi 56698 from group-get error message | Ramona 3/7 |  |  | Re-test,migrated to Model Office | 2001-03-19 | 2001-05-03 | Ramona
62 | Display | See both Receipt/Delivery Groups on Operational | Ramona 3/7 |  |  | Common groups to be used where possible - Close
64 | Display | Cannot see history for Operational Groups | Ramona 3/7 |  |  | Migrated to Production | 2001-04-16
65 | Add | Add Poi in Group- received error-Point has been already added for current group | Ramona 3/7 |  |  | Re-test | 2001-05-09
66 | Update | Removed point in group,Still allowed allocation | Ramona 3/8 | Hendra |  | Migrated to Model Office
67 | Display | Group wizard display too long | Ramona 3/8 | Steven |  | Migrated to Production | 2001-04-16
68 | Update | Allow points to be added to group and term points in group(s) as one function | Jeanne 4/1 | Team |  | Migrated to Production | 2001-04-16
69 | Display | Add ability to Rename group | Jeanne 4/1 | Team |  | Migrated to Production | 2001-04-16
70 | Display | Add detail for R/D adjustment | Perry 4/2 | Team |  | Migrated to Production | 2001-04-16
71 | Update | Double Dippping on R/D | Perry 4/2 | Don |  | Complete
72 | Function | Added What IF Evaluation for Marketers | Jeanne 4/1 | Team |  | Migrated to Production | 2001-04-16
73 | Reports | New Link for Reports thru Business Objects | Shelly 4/11 | Steven |  | New link alows User to access reports without having to sign on again to Business Objects - Users must be on Windows 2000- Migrated to Production | 2001-04-16
75 | Update | CBS system does not automatically track ROFR contracts | Don 4/7 | David |  | Add ROFR flag to CBS system,automatically entend end date to 2999 so capacity is committed/contracted until terminated- Migrated to Production | 2001-04-16
76 | System | Contracted Volumes showing volumes after contract termed | Perry 4/12 | David |  | Stored Procedure not looking at Contract term date when pulling Point volumes | 2001-04-20
77 | System | Contracted Volumes showing Cap Rlse volumes when permanently released | Perry 4/12 | David |  | Stored Procedure not looking at Contract term date when pulling Point volumes | 2001-04-20
78 | Report | Problem netting | Perry 5/1 | Don |  | Researching- Closed Point was not set up in Receipt Group | 2001-05-03
79 | Convert | Farm Taps Points that do not have Operational Capacity,load with Design capacity | Darrell 5/7 | Hendra |  | Completed, No data to Load all had Capacity
80 | Display | NNG Points show in wizard | Darrell 5/7 | Hendra |  | Change logic if TW as transporter terminated do not show
81 | Reports | Reports not recognizing months | Perry 12/28 | Lori |  | 5 reports | 2002-01-28
82 | Evaluation | Incorrectly calculating date ranges on the point groups | Perry 01/18 | Don
87 | Reports | Summer and Winter Volumes not correct | Perry 1/22 | Lori |  | Moved to Production | 2002-01-25

## Post Impl Items
Plog# | Function | Description of Problem | Reported By/Date | Assigned To/Date | Priority | Comments | Release Date | Retested | BY
15 | Delete | Need error message for invalid delete process | Mary D. 2/7 |  |  | Defer to post implementation
30 | Display | GISB compliance recommendations | Mary & Ramona 2/26 |  |  | Post - implementation item
53 | Entry | How much data should be retrieved and how much history should be stored | Maggie 3/2 |  |  | Active/History filter to be placed on Point Wizard, Date range capability to be put on Operational Capacity view to default to 1st day of month that is current
63 | Display | Scroll down on Relationship view, keep text box in view | Ramona 3/7
74 | Update | Comments truncated | Perry 4/7 | Jerry |  | Data deleted after single quote detected in Comments
87 | Comments | Create separate view to capture Operational comments |  |  |  | Will redesign with FGT CAS project