## Up to FERC
SUN DEVIL PIPELINE PROJECT | [22 empty] | Enron Asset Management Resources
(Preliminary Estimate) | [22 empty] | 2025-09-26
COST ESTIMATE TO FERC FILING
Based on 450 miles of 36"
Bloomfield C/S to Phoenix Cavern
Does Not Include Phoenix Cavern to Panda Tie-In)
PREPARED BY: |  |  |  |  | DC/SSK/DH
DATE: |  |  |  |  | 2001-09-19
| Months |  |  |  | STAFFING | [6 empty] | MAN | [9 empty] | GRAND | Total | Expended | Forecast | Control
FUNCTION | Sep 95 | Oct | Nov | Dec | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01 | 2002-01-01 | 2002-02-01 | 2002-03-01 | MONTHS | Hrs/Month | Total Hrs | $'s/Hr | Burdens | OH Rate | Sal+Burden | OH $ | SubTotal | Mult | TOTAL | w/o Ovh | ToDate | w/o Ovh | Budget
Project Management (ETS)
Project Manager (Cebryk/Eisenstein) | 0 | 0 | 0 | 0 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 9.5 | 173.3333 | 1646.6667 | 50 | 0% | 80% | 82333.3333 | 65866.6667 | 148200 | 1.8 | 148200
Project Secretary | 0 | 0 | 0 | 0 | 0.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.1 | 173.3333 | 537.3333 | 25 | 0% | 80% | 13433.3333 | 10746.6667 | 24180 | 1.8 | 24180
Project Est. Dir. (Smith) | 0 | 0 | 0 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 173.3333 | 520 | 48 | 0% | 80% | 24960 | 19968 | 44928 | 1.8 | 44928
Project Est. (Davis/Thomas) |  |  |  |  | 0.24 | 1 | 1 | 1 | 1 | 1 | 1 | 6.24 | 173.3333 | 1081.6 | 44 | 0% | 80% | 47590.4 | 38072.32 | 85662.72 | 1.8 | 85662.72
P.Controls Mgt (Hubbard) | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 6.5 | 173.3333 | 1126.6667 | 43 | 0% | 80% | 48446.6667 | 38757.3333 | 87204 | 1.8 | 87204
Cost Engineer (Kalmus) | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | 173.3333 | 606.6667 | 45 | 0% | 80% | 27300 | 21840 | 49140 | 1.8 | 49140
Dept Manager (Mathews) |  |  |  |  | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1.3 | 173.3333 | 225.3333 | 48 | 0% | 80% | 10816 | 8652.8 | 19468.8 | 1.8 | 19468.8
Procurement (ETS) | [11 empty] | 0
Purchasing Agent | 0 | 0 | 0 | 0 | 0.1 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 2.5 | 173.3333 | 433.3333 | 40 | 0% | 80% | 17333.3333 | 13866.6667 | 31200 | 1.8 | 31200
Expeditor/Logistics | [5 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 2.4 | 173.3333 | 416 | 36 | 0% | 80% | 14976 | 11980.8 | 26956.8 | 1.8 | 26956.8
Clerical/Admin Support | [5 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1.2 | 173.3333 | 208 | 22 | 0% | 80% | 4576 | 3660.8 | 8236.8 | 1.8 | 8236.8
Other (ETS) | [11 empty] | 0
Contracts Manager |  | 0 | 0 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 173.3333 | 520 | 40 | 0% | 80% | 20800 | 16640 | 37440 | 1.8 | 37440
Clerical/Sec.Support |  | 0 | 0 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 173.3333 | 520 | 22 | 0% | 80% | 11440 | 9152 | 20592 | 1.8 | 20592
Environmental |  | 0 | 0 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | 173.3333 | 520 | 42 | 0% | 80% | 21840 | 17472 | 39312 | 1.8 | 39312
[12 empty] | 48.24 |  | 8361.6 |  |  |  | 345845.0667 | 276676.0533 | 622521.12 |  | 622521.12
Project Management Expenses (ETS)
Project Management Travel |  |  |  |  | 8000 | 3000 | 3000 | 3000 | 3000 | 5000 | 5000 | [10 empty] | 30000
Subtotal Project Management | 0 | 0 | 0 | 0 | 2.04 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 48.24 |  | 8361.6 |  |  |  | 345845.0667 | 276676.0533 | 622521.12 |  | 652521.12 |  |  |  |  | 652521.12
Engineering Pipeline & Compression (Contract)
Project Managers | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 173.3333 | 2080 | 110 | 0% |  | 228800 | 0 | 228800 |  | 228800
Project Engineering Managers | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 13 | 173.3333 | 2253.3333 | 110 | 0% |  | 247866.6667 | 0 | 247866.6667 |  | 247866.6667
Project Engineers | 0 | 0 | 0 | 0 | 0.5 | 4 | 4 | 4 | 4 | 4 | 4 | 24.5 | 173.3333 | 4246.6667 | 100 | 0% |  | 424666.6667 | 0 | 424666.6667 |  | 424666.6667
Elect Engineers | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 173.3333 | 4160 | 100 | 0% |  | 416000 | 0 | 416000 |  | 416000
Civil Engineers | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 173.3333 | 4160 | 100 | 0% |  | 416000 | 0 | 416000 |  | 416000
Pipeline Engineers | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 173.3333 | 4160 | 100 | 0% |  | 416000 | 0 | 416000 |  | 416000
Lead Designers | 0 | 0 | 0 | 0 |  | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 173.3333 | 4160 | 100 | 0% |  | 416000 | 0 | 416000 |  | 416000
Designers | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 173.3333 | 8320 | 100 | 0% |  | 832000 | 0 | 832000 |  | 832000
Engr Secretary | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 173.3333 | 2080 | 50 | 0% |  | 104000 | 0 | 104000 |  | 104000
Estimator/Scheduler | 0 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 173.3333 | 2080 | 100 | 0% |  | 208000 | 0 | 208000 |  | 208000
Documentation | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 173.3333 | 1040 | 50 | 0% |  | 52000 | 0 | 52000 |  | 52000
[12 empty] | 223.5 |  | 36660 |  |  |  | 3532533.3333 | 0 | 3532533.3333 |  | 3532533.3333
Engineering Expenses (Contract)
Engineering Travel |  |  |  |  | 3000 | 3000 | 5000 | 5000 | 5000 | 5000 | 5000 | [10 empty] | 31000
Reproduction | [5 empty] | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | [10 empty] | 12000
Computer Charges | [5 empty] | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | [10 empty] | 18000
Field Survey --- 450 miles @ $3,000/mile | [21 empty] | 1350000
Subtotal Engineering | 0 | 0 | 0 | 0 | 1.5 | 37 | 37 | 37 | 37 | 37 | 37 | 223.5 |  | 36660 |  |  |  | 3532533.3333 |  | 3532533.3333 |  | 4943533.3333 | 4943533.3333 | 0 | 4943533.3333 | 130000 | 4943533.3333
Environmental (Contract)
Environmental Engineer --- See attachment for details | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 1115000
Agent (Contract Field) --- See attachment for details | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
Expenses --- See attachment for details | [21 empty] | 0
Subtotal Environmental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 1115000 | 1115000 | 0 | 1115000 | 42000 | 1115000
Regulatory (ETS)
Regulatory | 0 | 0 | 0 | 0 | 0.2 | 0.6 | 0.5 | 0.5 | 0.6 | 1 | 1 | 4.4 | 173.3333 | 762.6667 | 50 |  | 80% | 38133.3333 | 30506.6667 | 68640 | 1.8 | 68640
Legal | [5 empty] | 0 | 0 | 0 | 0.2 | 0.2 | 0.3 | 0.7 | 173.3333 | 121.3333 | 65 |  | 80% | 7886.6667 | 6309.3333 | 14196 | 1.8 | 14196
Financial | 0 | 0 | 0 | 0 |  |  |  |  | 0.2 | 0.2 | 0.4 | 0.8 | 173.3333 | 138.6667 | 50 | 0 | 80% | 6933.3333 | 5546.6667 | 12480 | 1.8 | 12480
[12 empty] | 5.9 |  | 1022.6667 |  |  |  | 52953.3333 | 42362.6667 | 95316 |  | 95316
Regulatory Expenses (ETS)
Reprodution & Postage | [10 empty] | 7500 | [10 empty] | 7500
Newspaper Advertising | [10 empty] | 25000 | [10 empty] | 25000
Meetings with FERC | [5 empty] | 5000 |  |  |  | 5000 | [11 empty] | 10000
Open Houses | [8 empty] | 10000 | 1000 | 5000 | [10 empty] | 16000
0
Subtotal Regulatory/Legal/Financial | 0 | 0 | 0 | 0 | 0.2 | 0.6 | 0.5 | 0.5 | 1 | 1.4 | 1.7 | 5.9 |  | 1022.6667 |  |  |  | 105906.6667 | 84725.3333 | 190632 |  | 153816 |  |  |  |  | 153816
Right of Way (ETS)
ROW Direct | 0 | 0 | 0 | 0 | 0.1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1.6 | 173.3333 | 277.3333 | 65 |  | 80% | 18026.6667 | 14421.3333 | 32448 | 1.8 | 32448
ROW Project Manager |  | 0 | 0 | 0 | 0.3 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 4.5 | 173.3333 | 780 | 47 | 0 | 80% | 36660 | 29328 | 65988 | 1.8 | 65988
ROW Specialists |  |  |  |  | 0.5 | 0.5 | 0.6 | 0.55 | 0.65 | 0.65 | 0.5 | 3.95 | 173.3333 | 684.6667 | 40 | 0 | 80% | 27386.6667 | 21909.3333 | 49296 | 1.8 | 49296
Titles, Permits, Survey (Lead) |  |  |  |  | 0.67 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 9.37 | 173.3333 | 1624.1333 | 43 | 0 | 80% | 69837.7333 | 55870.1867 | 125707.92 | 1.8 | 125707.92
Titles, Permits, Survey |  |  |  |  | 0.25 | 4.7 | 4.7 | 4.7 |  |  |  | 14.35 | 173.3333 | 2487.3333 | 40 | 0 | 80% | 99493.3333 | 79594.6667 | 179088 | 1.8 | 179088
Secretarial Support |  |  |  |  | 0.25 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 3.85 | 173.3333 | 667.3333 | 25 |  | 80% | 16683.3333 | 13346.6667 | 30030 | 1.8 | 30030
[12 empty] | 37.62 |  | 6520.8 |  |  |  | 268087.7333 | 214470.1867 | 482557.92 |  | 482557.92
Right of Way Expenses (ETS) | [21 empty] | 0
ROW Agent Expenses, Per Diem, Office Exp. | [5 empty] | 56650 | 56650 | 56650 | 26500 | 26500 | 22112 | [10 empty] | 245062
Acquiring ROW, Land Acquisition & | [5 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | [10 empty] | 150000
Titles, Permits, Survey | [21 empty] | 0
0
Subtotal Right of Way | 0 | 0 | 0 | 0 | 2.07 | 8.2 | 8.3 | 8.25 | 3.65 | 3.65 | 3.5 | 37.62 |  | 6520.8 |  |  |  | 268087.7333 | 214470.1867 | 482557.92 |  | 877619.92 | 663149.7333 | 0 | 663149.7333 | 7400 | 877619.92
Aerial Photography --- 450 miles @ $500/mile | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | 0 | 0 | 0% |  | 0 | 0 | 0 |  | 225000 |  | 0 | 0 |  | 225000
Construction Mgmt | [26 empty] | 7967490.3733
Construction Manager | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | 173.3 | 606.55 | 60 | 0 | 80% | 36393 | 29114.4 | 65507.4 | 1.8 | 65507.4
Start-up / Commissioning | 0 | 0 | 0 | 0 | [5 empty] | 0.5 | 0.5 | 1 | 173.3 | 173.3 | 50.9815 | 0 | 80% | 8835.094 | 7068.0752 | 15903.1691 | 1.8 | 15903.1691
[14 empty] | 779.85 |  |  |  | 45228.094 | 36182.4752 | 81410.5691 |  | 81410.5691
Subtotal Construction Mgmt | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 4.5 |  | 779.85 |  |  |  | 45228.094 | 36182.4752 | 81410.5691 |  | 81410.5691 | 45228.094 | 0 | 45228.094 | 45228.094
Total Man-Months & Without Contingency | #REF! | #REF! | #REF! | #REF! | 6.31 | 54 | 54 | 53.95 | 49.85 | 50.75 | 50.9 | 319.76 |  | 53344.9167 | [7 empty] | 8048900.9424 | 45228.094 | 0 | 45228.094 | 45228.094
Contingency --- 10% | [21 empty] | 804890.0942
Total | [21 empty] | 8853791.0367

## Total Project
TOTAL FOR SUN DEVIL | [32 empty] | Enron Asset Management Resources
(Preliminary Estimate) | [32 empty] | 2025-09-26
ESTIMATE OF PROJECT MANPOWER
PREPARED BY: |  |  |  |  | SSK
DATE: |  |  |  |  | 2001-08-13
| Months |  |  |  | STAFFING | [16 empty] | MAN | [9 empty] | GRAND | Total | Expended | Forecast | Control
FUNCTION | Sep 95 | Oct | Nov | Dec | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01 | 2002-01-01 | 2002-02-01 | 2002-03-01 | 2002-04-01 | 2002-05-01 | 2002-06-01 | 2002-07-01 | 2002-08-01 | 2002-09-01 | 2002-10-01 | 2002-11-01 | 2002-12-01 | 2003-01-01 | MONTHS | Hrs/Month | Total Hrs | $'s/Hr | Burdens | OH Rate | Sal+Burden | OH $ | SubTotal | Mult | TOTAL | w/o Ovh | ToDate | w/o Ovh | Budget
Engineering
Dept Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 48 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Project Engr Mgr | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 45 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Project Engr | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 42 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Lead Elect Engineer | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 40 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Lead Civil Engineer | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 40 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Lead Designer | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Designer (C) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 40 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Engr Secretary | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Engr Secretary | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 38 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
[22 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0
Subtotal Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 130000
Project Management
Project Manager | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 50 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Project Secretary | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Project Estimator | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 38 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
P.Controls Mgt | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 43 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Cost Engineer | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 45 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Schedule Engineer | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 43 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Dept Manager | [18 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 48 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Procurement
Purchasing Agent | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Expeditor/Logistics | [18 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Clerical/Admin Support | [18 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Other
QA/QC Inspection | [18 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Start-up Comissioning | [18 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Contracts Manager |  | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Clerical/Sec.Support |  | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
[22 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0
Subtotal Project Mgmt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 129200
Environmental
Environmental Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 26 | 0.35 | 0 | 0 | 0 | 0 | 1.35 | 0
Agent (Contract Field) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Expenses | [31 empty] | 0
Subtotal Environmental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 42000
Right of Way
Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 35 | 0.35 | 0 | 0 | 0 | 0 | 1.35 | 0
Agent (Contract Field) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Secretarial Support | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 173.3333 | 0 | 20 | 0.35 | 0 | 0 | 0 | 0 | 1.35 | 0
[17 empty] | Labor Subtotals | Labor Subtotals | Labor Subtotals | Labor Subtotals | Labor Subtotals | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0
Expenses | [31 empty] | 0
Acquiring ROW | [31 empty] | 0
Land Acquisition | [31 empty] | 0
Titles, Permits, Survey | [31 empty] | 0
Subtotal Right of Way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 7400
Engineering Expenses
Travel | [30 empty] | Travel
As-Built Drawings | [31 empty] | 0
Design Engineering | [30 empty] | Design Engineering Contractor | 0
Total | [31 empty] | 0 | 0 | 0 | 0
Project Mgt Expenses
Project Management Travel | [30 empty] | Project Management Travel | 0
[31 empty] | Other-Travel | 0
Total | [31 empty] | 0 | 0 | 0 | 0
Total Expenses | [30 empty] | Total Travel & Expenses | 0 | 0 | 0 | 0
Equip.Inspection Expenses | [30 empty] | Third Party Inspection | 0 | 0 | 0 | 0
Design Engineering
Design Engineering | 0 | 0 | 0 | 0 | [17 empty] | 0 | 173.3333 | 0 | 0 | 0% | 80% | 0 | 0 | 0 | 2.46 |  |  | 0 | 0
Total Home Office Man-Months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 308600
Construction Mgmt
Construction Manager (Field) | 0 | 0 | 0 | 0 | [17 empty] | 0 | 173.3 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Inspector | 0 | 0 | 0 | 0 | [17 empty] | 0 | 173.3 | 0 | 50.9815 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Start-up / Commissioning | 0 | 0 | 0 | 0 | [17 empty] | 0 | 173.3 | 0 | 50.9815 | 0 | 0 | 0 | 0 | 0 | 1 | 0
[24 empty] | 0 |  |  |  | 0 | 0 | 0 |  | 0
NON PAYROLL EXPENSES
Field Office Expenses | [31 empty] | 0
Surveys | [31 empty] | 0
Radiography | [31 empty] | 0
Vendor Commissioning | [31 empty] | 0
Field Staff Per Diem | [31 empty] | 0
Subtotal Construction Mgmt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total Man-Months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 308600
0
[26 empty] | Spent EECC Ovh : |  |  | 0
[26 empty] | Forecasted Ovh : |  |  | 0

## Pipeline
PIPELINE | [32 empty] | Enron Asset Management Resources
(Preliminary Estimate) | [32 empty] | 2025-09-26
ESTIMATE OF PROJECT MANPOWER
PREPARED BY: |  |  |  |  | SSK
DATE: |  |  |  |  | 2001-08-27
| Months |  |  |  | STAFFING | [16 empty] | MAN | [9 empty] | GRAND | Total | Expended | Forecast | Control
FUNCTION | Sep 95 | Oct | Nov | Dec | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01 | 2002-01-01 | 2002-02-01 | 2002-03-01 | 2002-04-01 | 2002-05-01 | 2002-06-01 | 2002-07-01 | 2002-08-01 | 2002-09-01 | 2002-10-01 | 2002-11-01 | 2002-12-01 | MONTHS | Hrs/Month | Total Hrs | $'s/Hr | Burdens | OH Rate | Sal+Burden | OH $ | SubTotal | Mult | TOTAL | w/o Ovh | ToDate | w/o Ovh | Budget
Engineering
Dept Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 48 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Project Engr Mgr | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 2.2 | 173.3333 | 381.3333 | 45 | 0% | 80% | 17160 | 13728 | 30888 | 1.8 | 30888
Project Engr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 42 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Lead Elect Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 40 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Lead Civil Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 40 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Lead Designer | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 173.3333 | 34.6667 | 35 | 0% | 80% | 1213.3333 | 970.6667 | 2184 | 1.8 | 2184
Designer (C) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 40 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Engr Secretary | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Engr Secretary | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 38 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
[22 empty] | 2.4 |  | 416 |  |  |  | 18373.3333 | 14698.6667 | 33072 |  | 33072
Subtotal Engineering | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 33072 | 18373.3333 | 0 | 18373.3333 | 130000
Project Management
Project Manager | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 173.3333 | 433.3333 | 50 | 0% | 80% | 21666.6667 | 17333.3333 | 39000 | 1.8 | 39000
Project Secretary | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 173.3333 | 86.6667 | 20 | 0% | 80% | 1733.3333 | 1386.6667 | 3120 | 1.8 | 3120
Project Estimator | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 173.3333 | 43.3333 | 38 | 0% | 80% | 1646.6667 | 1317.3333 | 2964 | 1.8 | 2964
P.Controls Mgt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 43 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Cost Engineer | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 1.1 | 173.3333 | 190.6667 | 45 | 0% | 80% | 8580 | 6864 | 15444 | 1.8 | 15444
Schedule Engineer | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0.55 | 173.3333 | 95.3333 | 43 | 0% | 80% | 4099.3333 | 3279.4667 | 7378.8 | 1.8 | 7378.8
Dept Manager |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 48 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Procurement
Purchasing Agent | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 173.3333 | 69.3333 | 35 | 0% | 80% | 2426.6667 | 1941.3333 | 4368 | 1.8 | 4368
Expeditor/Logistics |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 173.3333 | 69.3333 | 35 | 0% | 80% | 2426.6667 | 1941.3333 | 4368 | 1.8 | 4368
Clerical/Admin Support |  |  |  |  | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 173.3333 | 52 | 20 | 0% | 80% | 1040 | 832 | 1872 | 1.8 | 1872
Other
QA/QC Inspection |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Start-up Comissioning |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Contracts Manager |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 35 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
Clerical/Sec.Support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.3333 | 0 | 20 | 0% | 80% | 0 | 0 | 0 | 1.8 | 0
[22 empty] | 6 |  | 1040 |  |  |  | 43619.3333 | 34895.4667 | 78514.8 |  | 78514.8 | 43619.3333
Subtotal Project Mgmt | 0 | 0 | 0 | 0 | 0.25 | 0.45 | 0.7 | 0.7 | 0.5 | 0.5 | 0.7 | 0.7 | 0.45 | 0.45 | 0.45 | 0.15 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 78514.8 | 43619.3333 | 0 | 43619.3333 | 129200
Environmental
Environmental Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 26 | 0.35 | 0 | 0 | 0 | 0 | 1.35 | 0
Agent (Contract Field) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Expenses | [31 empty] | 0
Subtotal Environmental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 42000
Right of Way
Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 35 | 0.35 | 0 | 0 | 0 | 0 | 1.35 | 0
Agent (Contract Field) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 173.3333 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Secretarial Support | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 173.3333 | 0 | 20 | 0.35 | 0 | 0 | 0 | 0 | 1.35 | 0
[17 empty] | Labor Subtotals | Labor Subtotals | Labor Subtotals | Labor Subtotals | Labor Subtotals | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  | 0
Expenses | [31 empty] | 0
Acquiring ROW | [31 empty] | 0
Land Acquisition | [31 empty] | 0
Titles, Permits, Survey | [31 empty] | 0
Subtotal Right of Way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 7400
Engineering Expenses
Travel | [30 empty] | Travel | 14000
As-Built Drawings | [31 empty] | 0
Design Engineering | [6 empty] | 10000 | 10000 | [22 empty] | Design Engineering Contractor | 20000
Total | [31 empty] | 34000 | 34000 | 0 | 34000
Project Mgt Expenses
Project Management Travel | [30 empty] | Project Management Travel | 0
[31 empty] | Other-Travel | 0
Total | [31 empty] | 0 | 0 | 0 | 0
Total Expenses | [30 empty] | Total Travel & Expenses | 34000 | 34000 | 0 | 34000
Equip.Inspection Expenses | [30 empty] | Third Party Inspection | 0 | 0 | 0 | 0
Design Engineering
Design Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 1.4098 | 1.4098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8197 | 173.3333 | 488.7448 | 0 | 0% | 80% | 0 | 0 | 0 | 2.46 |  |  | 0 | 0
Total Home Office Man-Months | 0 | 0 | 0 | 0 | 0.25 | 0.65 | 2.4098 | 2.4098 | 0.7 | 0.7 | 0.9 | 0.9 | 0.65 | 0.65 | 0.65 | 0.35 | 0 | 0 | 0 | 0 | 0 | 11.2197 |  | 1944.7448 | [7 empty] | 145586.8 | 95992.6667 | 0 | 95992.6667 | 308600
Construction Mgmt
Construction Manager (Field) | 0 | 0 | 0 | 0 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 7 | 173.3 | 1213.1 | 60 | 0 | 0 | 72786 | 0 | 72786 | 1 | 72786
Inspector | 0 | 0 | 0 | 0 | [17 empty] | 0 | 173.3 | 0 | 50.9815 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Start-up / Commissioning | 0 | 0 | 0 | 0 | [17 empty] | 0 | 173.3 | 0 | 50.9815 | 0 | 0 | 0 | 0 | 0 | 1 | 0
[24 empty] | 1213.1 |  |  |  | 72786 | 0 | 72786 |  | 72786
NON PAYROLL EXPENSES
Field Office Expenses | [31 empty] | 0
Surveys | [31 empty] | 0
Radiography | [31 empty] | 0
Vendor Commissioning | [31 empty] | 0
Field Staff Per Diem | [31 empty] | 0
Subtotal Construction Mgmt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1213.1 |  |  |  |  | 0 |  |  | 72786 | 72786 | 0 | 72786 | 72786
Total Man-Months | 0 | 0 | 0 | 0 | 0.25 | 0.65 | 2.4098 | 3.4098 | 1.7 | 1.7 | 1.9 | 1.9 | 1.65 | 1.65 | 0.65 | 0.35 | 0 | 0 | 0 | 0 | 0 | 11.2197 |  | 3157.8448 | [7 empty] | 218372.8 | 168778.6667 | 0 | 168778.6667 | 381386
[26 empty] | Spent EECC Ovh : |  |  | 0
[26 empty] | Forecasted Ovh : |  |  | 0
Note on F80: David W. Hubbard: 173 hrs x 41 = 7093
Note on G80: David W. Hubbard: 173 hrs x 41 = 7093
Note on H80: David W. Hubbard: 173 hrs x 41 = 7093
Note on I80: David W. Hubbard: 173 hrs x 41 = 7093
Note on J80: David W. Hubbard: 173 hrs x 41 = 7093
Note on K80: David W. Hubbard: 173 hrs x 41 = 7093
Note on L80: David W. Hubbard: 173 hrs x 41 = 7093
Note on M80: David W. Hubbard: 173 hrs x 41 = 7093
Note on N80: David W. Hubbard: 173 hrs x 41 = 7093
Note on O80: David W. Hubbard: 173 hrs x 41 = 7093
Note on P80: David W. Hubbard: 173 hrs x 41 = 7093
Note on Q80: David W. Hubbard: 173 hrs x 41 = 7093
Note on R80: David W. Hubbard: 173 hrs x 41 = 7093
Note on S80: David W. Hubbard: 173 hrs x 41 = 7093
Note on T80: David W. Hubbard: 173 hrs x 41 = 7093
Note on U80: David W. Hubbard: 173 hrs x 41 = 7093
Note on V80: David W. Hubbard: 173 hrs x 41 = 7093