## CRITICAL PATH PHASE I
|  |  | SENIOR MANAGEMENT | OPERATIONS | LEGAL | CUSTOMER | ACCT. MGMT. | EXTERNAL | REGULATORY AFFAIRS | RAC/ CREDIT | RISK
|  |  | Dan Leff | Wanda Curry | Mike Smith | Scott Gahn | Eric Melvin | Peggy Mahoney | Jeff Dasovich | Denise Furey | Don Black
TASK | CRITICAL STEPS | EXECUTION DATE | Marty Sunde | Evan Hughes | Jim Keller | Eric Melvin | Scott Gahn |  |  |  | Meredith Eggleston
1 | Establish Active PG&E Account List (by book, by customer) | 2001-01-24 |  | YES
2 | Establish Active SCE Account List (by book, by customer) | 2001-01-24 |  | 1
3 | Analyze Financial Exposure with PG&E (by book, by customer) | 2001-01-24 |  |  |  | YES |  |  |  | YES | YES
4 | Analyze Financial Exposure with SCE (by book, by customer) | 2001-01-24 |  |  |  | 2 |  |  |  | 2 | 1
5 | Coordinate State and Federal Regulatory Issues | 2001-01-24 |  |  | 2 |  |  |  | 1
6A | Prepare Disconnect DASRs (D-DASR) for PG&E | 2001-01-24 |  | YES
6B | Prepare Disconnect DASRs (D-DASR) for SCE | 2001-01-24 |  | 1
7A | Establish Transmission Protocols (Send & Confirm Receipt) for PG&E | 2001-01-24 |  | YES
7B | Establish Transmission Protocols (Send & Confirm Receipt) for SCE | 2001-01-25 |  | 1
8 | Draft Customer Communication Letter | 2001-01-24 |  |  | YES | YES |  | YES | 2
9 | Approve Customer Communication Letter | 2001-01-25 | 1 |  | 2 | 2 | 2 | 2 | 2
10 | Establish Confidentiality with PG&E | 2001-01-24 |  | 2 | 1
11A | Segment Customers into Opportunity Categories for PG&E | 2001-01-24 |  |  | YES | YES |  |  |  | 2 | 2
11B | Segment Customers into Opportunity Categories for SCE | 2001-01-24 |  |  | YES | YES |  |  |  | 2 | 2
12 | Define Customer Specific “new” Products/Strategies | 2001-01-24 |  | 2 | 2 | 1 | 2 |  |  | 2 | 2
13 | Approve Customer Specific “new” Products/Strategies | 2001-01-24 | 2 |  |  | 1 | 2 |  |  | 2 | 2
14 | Coordinate Switching, Metering, Billing & Settlement Logistics with PG&E (negotiate transition plan) | 2001-01-24 |  | 1 | 2 |  |  | 2 | 2 |  | 2
15 | Document PG&E Accountability for all active accounts as of 02/01/01 (in writing) | < 2/1/2001 |  | 2 | 1 |  |  |  | 2
16 | Coordinate Switching, Metering, Billing & Settlement Logistics with SCE (detail transition plan) | 2001-01-26 |  | 1 | 2 |  |  |  | 2
17A | Final Decision to D-DASR all PG&E non-residential Accounts | 2001-01-24 | 1
17B | Send D-DASR Transmission to PG&E | 2001-01-24 |  | 1
18A | Final Decision to D-DASR all SCE non-residential Accounts | 2001-01-25 | 1
18B | Send D-DASR Transmission to SCE | 2001-01-25 |  | 1
19 | Send Customer Communication Letters | 2001-01-26 |  |  |  | 1 |  | 2
20A | Confirm PGE D-DASR Receipt | 2001-01-24 |  | 1
20B | Confirm SCE D-DASR Receipt | 25-Jan-01 Pending Step 20A |  | 1
21 | Implement Transition Plan w/PG&E | 2001-01-24 |  | 1 | 2 |  |  | 2 | 2 |  | 2
22 | Schedule Customer Contact Meetings | 2001-01-24 |  |  |  | 1 | 2
23 | Propose Customer Specific Contract Amendments/Changes | 2001-01-24 |  | 2 | 2 | 2 |  |  |  | 2 | 2
24 | Document Customer Specific Contract Amendments/Changes | 2001-01-24 |  | 2 | 1 | 2 |  |  |  | 2 | 2
% OF TOT | RESPONSIBILITY MATRIX | Total
27.85% | PRIMARY RESPONSIBILITY | 22 | 3 | 10 | 3 | 4 | 0 | 0 | 1 | 0 | 1
58.23% | DIRECT INVOLVEMENT | 46 | 1 | 5 | 7 | 4 | 4 | 4 | 6 | 7 | 8
2.532% | PARTICIPATORY INVOLVEMENT | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
11.39% | TASK COMPLETE | 9 | 0 | 2 | 3 | 3 | 0 | 1 | 0 | 0 | 0
79
NOTE: Goal of 100% TASK COMPLETE by each deadline.
RESPONSIBILITY MATRIX LEVEL 1 PRIMARY RESPONSIBILITY
LEVEL 2 DIRECT INVOLVEMENT
LEVEL 3 PARTICIPATORY INVOLVEMENT TASK COMPLETE YES