## Sheet1
Support Type | Deal Name | Responsible Person | Impact ($MM) | Background/Key Issues | Updated | Strategies/Comments/Next Actions
Regulatory Risk | Marketing Affiliate Rule NOPR | Lawner/Cantrell | 58 | The NOPR was issued on September 27. A team, lead by Lisa Yoho and Leslie Lawner, will develop comments. | 2001-10-04 | Team is holding initial meeting 10/5.
Advocacy | FERC Reporting for Natural Gas Sellers into California | Becky Cantrell |  | FERC is requiring reporting of natural gas sales into California, initially for a six-month period beginning 8/1/01 with the intention of extending until 9/30/02. | 2001-10-04 | The report for ENA was submitted on the October 1 due date. Information for the EES report has to be obtained from the third-party vendor, CSC, and the report will not be completed until at least 10/15. A letter was sent to FERC advising of the delay.
Deal Support | Regulatory Updates | Cantrell | UK | Background: Project is the development and implementation of an electric regulatory reporting system that could be linked to the Fundamentals web sites used by the traders to replace the current system of distributing paper copies. | 2001-10-04 | Meetings have been held with the IT development team and Elizabeth Linnell. We are scheduling meetings with commercial personnel to review specific approaches.
| EL Paso Block II Turnback | Cantrell | $2.0/Month, or $120.00 for remainder of term | Bckground: ENA has a TSA on El Paso with an MDQ of 195,503 Mcf/day (200,000 dth) that will terminate on 5/31/2006. The TSA is subject to El Paso's maximum FT-1 rate. | 2001-10-04 | This is being handled on a regulatory basis through participation in the El Paso System Reallocation proceeding.
| El Paso System Reallocation | Cantrell | UK, but will also affect the way the West Desl trades gas. | Background: El Paso does not assign primary receipt point rights for firm transportation. All shippers have equal rights and each nomination cycle requires a pro rata allocation if capacity is constrained. Full requirements service complicates this beca | 2001-10-04 | Comments have been drafted to be filed on 10/15. The comments argue for rationalization and turnback of unneeded capacity.
| FERC Reporting Requirements for Gas to California | Cantrell | UK | Background: FERC issued an order requiring sellers of natural gas to California to report details of their transactions. Key Issues: ENA/EES filed a request for h | 2001-10-04 | See "Advocacy" item above.
Regulatory Ventures
Legal Issues