## TW Capacity Auction
Due Date | Action Item | Key Approvals | Responsible Person | Comments
| Initial Customer Letter |  | Julia White/Steve Harris
2000-05-17 | Draft Customer Letter Out for Comments |  | Jeff Fawcett
2000-05-23 | Comments Due Back |  | Distribution List
2000-06-01 | TW Post to EBB & Mail Customer Letter |  | Julia White
(43 Target Customers w/ Package)
| Internal Letter |  | Julia White/Steve Harris
2000-05-23 | Draft Internal Letter Out for Comments |  | Julia White
2000-05-26 | Comments Due Back |  | Distribution List
2000-05-31 | E-mail GPG Employees |  | Julia White
| Press Release |  | Dave Schafer
2000-05-26 | Draft TW Press Release |  | Dave Schafer/Julia White/Steve Harris | Based on customer letter.
2000-05-30 | Comments Due Back |  | Distribution List
2000-06-01 | Release Final Press Release to Public |  | Dave Schafer
| External Communications |  | Stan Horton/Shelley Corman/Drew Fossum/Mary Kay Miller
May 31/June 1? | FERC/Reg. Communication |  | Shelley Corman/Drew Fossum/Mary Kay Miller | Names & agencies to be determined.
May 31/June 1? | Other State Agencies(?) |  | Shelley Corman/Drew Fossum/Mary Kay Miller
| EOL Web Site |  | Steve Hotte
2000-05-12 | Web Text Due |  | Tony Pryor/Maria Pavlou
2000-05-15 | Finalized Web Text to be given to EOL |  | Tony Pryor/Maria Pavlou
2000-06-02 | Web Design Complete for TW Auction |  | Steve Hotte/Bob Schults (EOL)
June/5-9/2000 | User Acceptance Testing:
| Navigation |  | Julia White/Steve Harris
| Information Accuracy |  | Julia White/Steve Harris/ Tony Pryor/Maria Pavlou
June/10-14/2000 | Changes due to User Testing (If Applicable) |  | Steve Hotte
Completion Date | Action Item | Key Approvals | Responsible Person | Comments
| EOL Web Site - Cont'd |  | Steve Hotte
June/15-19/2000 | Final User Acceptance Test
| Navigation |  | Julia White/Steve Harris
| Information Accuracy |  | Julia White/Steve Harris/ Tony Pryor/Maria Pavlou
June/19-23/2000 | Internal Training on Capacity Auction Web |  | Steve Hotte/TK Lohman
| Customer Training Manual Capacity Auction |  | Julia White/Steve Harris
2000-06-02 | Draft Customer Training Manual |  | MarySusan Banavali
2000-06-07 | Approval of Customer Training Manual |  | Julia White/Steve Harris
2000-06-12 | Distribute Manual to 43 Target Customers |  | Steve Harris
2000-06-27 | EOL Opens for Bidding 8:00 a.m. CST |  | Steve Hotte
| Technical |  | Steve Hotte
| Commercial |  | Steve Harris/TK Lohman
| Legal Support |  | Tony Pryor/Maria Pavlou
| Credit Support |  | Paul Cherry
| Market Services Support |  | Julia White/Rick Dietz
2000-06-29 | EOL Bid Deadline 2:00 p.m. CST |  | Steve Hotte
| Technical |  | Steve Hotte
| Commerical |  | Steve Harris/TK Lohman
| Legal Support |  | Tony Pryor/Maria Pavlou
| Credit Support |  | Paul Cherry
| Market Services Support |  | Julia White/Rick Dietz
June 29, 2000 (2-4 p.m.) | EOL Award Bids 4:00 p.m. CST |  | Steve Harris/Rick Dietz/Paul Cherry
| Confirmation of Awards |  | Steve Harris
| Call Award Winners |  | Steve Harris
| Written Confirmation |  | Rick Dietz
| Post Capacity Award on TW EBB? |  | Tony Pryor/Maria Pavlou/ Toby Kuehl
| Execute FT Contract |  | Rick Dietz
Completion Date | Action Item | Key Approvals | Responsible Person | Comments
2000-06-30 | Nominations to TW Pipeline (TMS) 11:30 a.m. CST
Area | Point People
Contracts | Rick Dietz
Credit | Rick Dietz/Paul Cherry
Legal | Tony Pryor/Maria Pavlou
Capacity Receipt Point Availability | Perry Frazier
Internal/External EOL Auction - Commercial | TK Lohman
EOL - Technical | Steve Hotte/Bob Schults

## Distribution List
Distribution List for TW Customer Letter, Internal Letter, Press Release:
FGT | ET&S | NBPL | GPG
Rock Meyer | Bill Cordes | Larry DeRoin | Stan Horton
Fraizer King | Mary Kay Miller | Ray Neppl | Shelley Corman
Bob Hall | Tony Pryor | Eva Neufeld | Rod Hayslett
Bob Hayes | Maria Pavlou | Bill Fonda | Dave Schafer
Rachel Cady | Steve Harris | Scott Coburn | Steve Hotte
Rob Kilmer | Julia White | Bob Hill
Dave Neubauer