## EPE-Approved
APPROVED CHANGE ORDER RECONCILIATION ANALYSIS
EMPRESA PRODUTORA DE ENERGIA LTDA
Cuiaba 480 MW Power Plant
2000-11-11
Approved Change Orders in Model |  |  |  | Status as of | Detail on when approved
|  |  | Total | 2000-04-06
PCO-003 | Fuel System Low Flash Consultant |  | 26.393 | Approved
PCO-004 | Step-Up Transformer Design Changes |  | 447 | Approved
PCO-005 | Effluent Discharge Line |  | 355.834 | Approved
PCO-009 | Separate Site Access For Operations |  | 96.263 | Approved
PCO-012 | Cascading Blowdown |  | 34.474 | Approved
PCO-016 | Water Treatment Chemicals & Safety Equipment |  | 49.442 | Approved
PCO-023 | Credit To EPE For 8 Water Reducing Stations |  | -450 | Approved
PCO-025 | Operating Accords - Engineering Support |  | 109.722 | Approved
PCO-026 | Salvage Association Costs Trhough August 1999 |  | 237.998 | Approved
PCO-029 | Power Supply For River Water Intake |  | 298.132 | Approved
PCO-030 | Water Treatment Intake, Pipeline And Treatment Plant |  | 10012.339 | Approved
PCO-031 | WTP-SCC Project Mgmt./Geotech. Investigation |  | 509.464 | Approved
PCO-033 | C/T Return Lube Oil Pump Contro Logic |  | 29.88 | Approved
PCO-034 | Pressure Switch For Lube Oil Pump Control Logic |  | 47.648 | Approved
PCO-035 | Additional Equip. For Coxipo Phase III Substation Bay |  | 125.626 | Approved
PCO-036 | Implementation Of Motor Hour-Meters Within The Teleperm |  | 21.873 | Approved
PCO-038 | SCC Extended Overheads For 7/15/99 PPL RFS |  | 1085 | Approved
PCO-041 | Supply & Installation Of 3rd Grit Chamber For Water Intake |  | 50.67 | Approved
PCO-050 | Redesign Of Effluent Lagoons by ETEP |  | 100 | Approved
PCO-052 | Additional Road Design |  | 9.462 | Approved
PCO-064 | Installation Of Additional HICOM Card |  | 3.238 | Approved
|  | Sub Total as of 4-6-00 | 13200.458
PCO-006 | Training of Operations & Maintenance Personel |  | 391.582 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval
PCO-008 | I&C Mod's Open Cycle Operation (Teleperm. Reprog.) |  | 18.217 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval
PCO-017 | Additional 0.625 Km Phase 1 Tranmission Line (Re-Route) |  | 149.385 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval and netted against Amper credits
PCO-018 | Relocate 34.5 kV Line for Phase 2 Line to Utilize ROW |  | 61.7 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval and netted against Amper credits
PCO-021 | Supply&Installation of 3 Bays at Varxea Grande Substation |  | 30.222 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval and netted against Amper credits
PCO-028 | Provide Conductivity Probe for Oil Water Separator |  | 51.616 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval
PCO-039 | Relocation of 2 CEMAT 138 kV Structures-Phase II T/L |  | 50.975 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval and netted against Amper credits
PCO-040 | Relocation of CEMAT 13.8 kV Structures - Phase III T/L |  | 10.57 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval and netted against Amper credits
PCO-055 | Study of Fuel Flash Point |  | 88.733 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval
Settlement for Efluent System (PCO-20,27,53,56,57) (PCO-50 separately) |  |  | 1450 | Forecasted | Settlement made in April this year with knowledge of Owners
PCO-065 | CT Trips Signals at Coxipo Substation, Schlumberger Telemetering |  | 52.006 | Non-existent | Agreed in Houston 12/13 June with Owners' knowledge & approval
|  | Sub Total as of 6-22-00 | 15555.464
|  | Delta | 2355.006
PCO-013 | Siemens Ltda. Cancellation Charge, Phase II design |  | 115.34 | Forecasted | On 12/13 June meeting sent to dispute resolution; settled at 75/25 Owner / Contractor
PCO-014 | Relay protection duplication |  | 44.129 | Forecasted | On 12/13 June meeting sent to dispute resolution; settled at 50/50 Owner / Contractor
PCO-015 | T&D Communication Tower at Coxipo Substation |  | 35.512 | Forecasted | On 12/13 June meeting sent to dispute resolution; settled at 50/50 Owner / Contractor
PCO-048 | Water Treatement Facility escalation - Inflation adjustment factor |  | 733.966 | Forecasted | In accordance with Contract
PCO-049 | Design of sludge lagoons |  | 138.995 | Forecasted | Requested by Owner
PCO-063 | Change in IPI Tax Law |  | 125.595 | Forecasted | Required further review after meeting 12/13 June; in accordance with contract
PCO-066 | Supply and Installation of Precast ladders at RWL & TWL |  | 10.579 | Non-existent | Agreed on 28 Apr-00
PCO-067 | Design and installation of rope safety ladders at lagoon |  | 7.85 | Non-existent | Agreed on 28 Apr-00
PCO-068 | Supply and installation of smoke detectors at WTP & electrical rooms |  | 23.154 | Non-existent | Agreed on 28 Apr-00
PCO-071 | Refund to Siemens for portion of Ph I LD's after re-measure and re-calculation |  | 300 | Non-existent | Approved on 17-Aug-00; In accordance with contractor having right to improve, took out 10% markup
PCO-073 | Supply and install fence at river water intake structure for safety |  | 16.888 | Non-existent | Approved on 17-Aug-00; Owner requested for safety precautions
PCO-074 | Supply and install shielded control cables at Coxipo substation |  | 18.334 | Non-existent | Approved on 17-Jul-00. Owner requested
PCO-075 | inflation adjustment for Amper's Pahse III scope of work for T&D contract |  | 43.704 | Non-existent | According to contract, Owner picked-up 2/3 because different dates in contracts
PCO-076 | Settlement for Amper Claim related to additional costs of the Phase III scope of work |  | 158.428 | Non-existent | Approved on 17-Jul-00. Close out between SCC/Amper/Owner on increased scope
PCO-077 | Credir to owner for reduction in Amper's Phase III substation scope |  | -40.128 | Non-existent | Approved on 17-Aug-00
PCO-078 | Recover additional charges invoiced by salvage foundation after August 1999 |  | 40.404 | Non-existent | Approved on 17-Aug-00; Marine transportation insurance inspection
PCO-079 | Design, Procurement, Installation, Config. & Commiss. Of Automation at Varzea grande |  | 15.873 | Non-existent | Agreed on 21-Aug-00. Requested by Owner
PCO-080 | Supply and Install Mono-Channel Radio System connecting EPE Control Room to CEMAT |  | 16.186 | Non-existent | Approved in Oct-00. Requested by Owner
|  | Sub total as of 11-11-00 | 17360.273
|  | Delta 11-11 and 04-06 | 4159.815
|  | Delta 11-11 and 06-22 | 1804.809
|  | Total | 17360.273

## GasMat-Approved
APPROVED CHANGE ORDER RECONCILIATION ANALYSIS
GasOcidente do Mato Grosso Ltda.
278 km natural gas pipeline
2000-11-11
Approved Change Orders in Model |  |  |  |  | Detail on when approved
Total
PCO-001 | Survey / Engr For Addit'l Length |  | 37.214 | Approved
PCO-002 | Survey / Engr For Reduced Length |  | 123.453 | Approved
PCO-003 | Pipe Laydown And Storage Yard |  | 180 | Approved
PCO-009 | Geotech. Investigation For River Crossing |  | 66.15 | Approved
PCO-010 | Reroute Due To Landowner |  | 47.72 | Approved
PCO-011 | Home Office Support For Survey Work |  | 8.034 | Approved
PCO-014 | Eliminate Compressor Stations |  | 9.105 | Approved
PCO-015 | Roberto Ibatta (IPE) Visit For ROW Changes |  | 5.284 | Approved
PCO-016 | Inspect Piraputenga & Santana Ridges |  | 7.383 | Approved
PCO-017 | Ridges Core Samples |  | 32.128 | Approved
PCO-018 | Reroute Pipeline In Ridges |  | 19.01 | Approved
PCO-019 | Survey Land For Metering Station |  | 9.535 | Approved
PCO-021 | Extended Overheads (42% Of $300) |  | 125.999 | Approved
PCO-022 | Additional Inspection Staff (42% Of $1,650) |  | 693 | Approved
PCO-023 | Brazil Pipeline Contractor Standby Expenses |  | 1260 | Approved
PCO-024 | Brazil Pipeline Contractor Acceleration Expenses |  | 1310.4 | Approved
PCO-026 | Ridges - Pipe Purchase And 13 KM Reroute |  | 1319.247 | Approved
PCO-027 | SCC Overheads (42% Of $1,085) |  | 455.7 | Approved
PCO-049 | Credit Owner For Camp Accomodations |  | -77.417 | Approved
|  | Sub-Total as of 4-6-00: | 5631.945 |  | Settlement referred to below was made by including Owners Rep in negotiation between SCC
and Conduto / Preussag
PCO-006 | Modifications to ENFAB separator Skid |  | 168.427 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-029 | Change in Brazilian Tax Legislation |  | 419.937 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, per contract
PCO-030 | Increased Length of Directional Drilled Crossings (Cuiaba, Jauru & Paraguay) |  | 460.93 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-031 | Directional drill of Padre Ignacio River |  | 1091.537 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-032 | Powercrete Coating of Pipes for Directional Drilled Crossings |  | 35.75 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-033 | Installation of Separator Skid Unit at KP-626 Facility |  | 40 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-035 | Additional Width of Shrink Sleeves |  | 72.105 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-036 | Support Services for Geological Investigation for Re-routes within the ridges |  | 49.124 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-037 | Relocate Ditching Crew Around Archaeological area at KP-385+900 |  | 80.343 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-038 | Replace FBE Coated Pipe with Concrete Coated Pipe at KP-424 to KP-427 |  | 20.9 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-039 | Increase in Concrete Coating requirements within Brazil |  | 796 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-041 | Pipeline Re-route from KP-523+850 tp KP-524-960 |  | 8.269 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-053 | Replace FBE coated Pipe with Concrete Coated at KP 389 |  | 51.704 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-054 | Material Casing - Road Crossing |  | 23.829 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-055 | Extra Bored Road Crossings |  | 75.75 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-058 | Relocate Stringing crew KP 619 |  | 8.108 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-064 | Brasil Ridges Re-route Survey & Alignment Sheets, Flagging Re-route, & Survey |  | 208.504 | Non-existent | Approved on 25-April-00; Requested and approved by M. Schulze
|  | Sub Total as of 6-22-00 | 9243.162
|  | Delta | 3611.217
PCO-065 | Purchase additional pipe material for directional drilling |  | 1274.496 | Non-existent | Pipe purchase was necessary for drilling and to avoid delays
PCO-066 | Purchase additional pipe material - Mud return lines |  | 152.445 | Non-existent | Pipe purchase was necessary for drilling and to avoid delays
|  | Sub total as of 11-11-00 | 10670.103
|  | Delta 11-11 and 04-06 | 5038.158
|  | Delta 11-11 and 06-22 | 1426.941
|  | Total | 10670.103

## GasBol-Approved
APPROVED CHANGE ORDER RECONCILIATION ANALYSIS
GasOriente Boliviano Ltda.
362.1 km natural gas pipeline
2000-11-11 |  |  |  | Status as of
Approved Change Orders |  |  | Total | 2000-04-06 | Detail on when approved
PCO-001 | Survey / Engr For Addit'l Length |  | 10.337 | Approved
PCO-002 | Survey / Engr For Reduced Length |  | 94.846 | Approved
PCO-003 | Pipe Laydown And Storage Yard |  | 180 | Approved
PCO-004 | Reroute Near San Matias |  | 39.902 | Approved
PCO-005 | Reroute Near Indig. Peoples |  | 35.103 | Approved
PCO-006 | Eliminate Compressor Station |  | 8.516 | Approved
PCO-007 | Hydraulic Calcs For Pipeline Volumes |  | 0.899 | Approved
PCO-008 | Provide Master File Copies |  | 1.777 | Approved
PCO-009 | Produce Maps And Drawings |  | 9.867 | Approved
PCO-010 | Produce Master File Of ROW |  | 3.632 | Approved
PCO-011 | Meeting - La Paz 10/27/98 |  | 2.563 | Approved
PCO-012 | Meeting - La Paz 9/10/98 |  | 2.879 | Approved
PCO-013 | Meeting - La Paz 6/16/99 |  | 2.229 | Approved
PCO-014 | Prepare Master File For Transredes |  | 1.839 | Approved
PCO-015 | Relocation Of Compressor Station From Protected Area |  | 14.18 | Approved
PCO-017 | Extended Overheads |  | 173.998 | Approved
PCO-018 | Additional Inspection Staff |  | 957 | Approved
PCO-019 | Contractor Standby Expenses |  | 1740 | Approved
PCO-020 | Pipeline Acceleration Expenses |  | 1809.6 | Approved
PCO-022 | IPE Reroute Survey |  | 352.632 | Approved
PCO-023 | Helicopter For Environmental Survey |  | 180.138 | Approved
PCO-024 | SCC Overheads (Restated Agreement) |  | 629.3 | Approved
PCO-059 | Credit Owner For Camp Accomodations |  | -77.418 | Approved
|  | Subtotal as of April 6: | 6173.819 |  | Settlement referred to below was made by including Owners Rep in negotiation between SCC
and Conduto / Preussag
PCO-026 | Stand-by Changes due to Lack of Forestry Permits, 3 Days |  | 60.894 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-027 | Lock-out from KP-113 to KP-290 |  | 135.797 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-028 | Lock-Out from KP-352+744 to KP-353+222 |  | 10.149 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-029 | Lock-Out at KP-344+867 |  | 15.224 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-030 | Additional Length due to Re-Routes |  | 225.894 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-033 | Additional Width of Shrink Sleeves, Bolivia |  | 131.491 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-035 | Archaeological Investigation at KP-109 |  | 26.767 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-036 | Archaeological Investigation from KP-134+102 to KP-134+273 |  | 4.729 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-037 | Archaeological Investigation from KP-147+050 to KP-147+480 |  | 5.107 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-038 | Archaeological Investigation from KP-150+545 to KP-150+660 |  | 0.817 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-039 | Archaeological Investigation from KP-153+195 to KP-153+310 |  | 1.634 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-040 | Archaeological Investigation from KP-147+105 to KP-147+416 |  | 0.817 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-041 | Archaeological Investigation from KP-147+080 to KP-147+138 |  | 1.351 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-042 | Archaeological Investigation from KP-147+239 to KP-147+416 |  | 1.372 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-043 | Archaeological Investigation from KP-147+417 to KP-147+450 |  | 1.007 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-044 | Archaeological Investigation at San Juan Camp |  | 0.817 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-045 | Archaeological Investigation at KP-134 |  | 0.817 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-046 | Archaeological Investigation from KP-155+148 to KP-156+800 |  | 0.817 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-047 | Archaeological Investigation at KP-169 |  | 1.089 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-048 | Archaeological Investigation from KP-154 to KP-174 |  | 3.365 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-049 | Archaeological Investigation at KP-155 |  | 10.913 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-050 | Archaeological Investigation at Santa Helena Camp |  | 1.77 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-051 | Archaeological Investigation from KP-357+850 to KP-357+950 |  | 0.693 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-052 | Archaeological Investigation from KP-340+100 to KP-340+350 |  | 0.26 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-056 | Stand-by KP-187, ROW and Grade Crews |  | 20.298 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-057 | Landowner Lock-out at KP-345+200, Tie-in Crew |  | 20.58 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-058 | Disruption of Work at Santa Clara Community |  | 13.352 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-060 | Stand-by Charges due to lack of access from KP 113 - KP 221 |  | 2346.822 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-061 | Negative Bouyancy Lump Sum - See PCO-034 |  | 2000 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-062 | Clear Runway ext. San Matias |  | 1.228 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-063 | Stby Civil Unrest San Matias |  | 2649.096 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-068 | Provide Assistance for Archeological |  | 56.947 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
PCO-072 | Drill Water Wells at San Miguelito |  | 366.883 | Forecasted | Agreed in Houston 12/13 June with Owners' knowledge & approval, part of big settlement
|  | Sub Total as of 6-22-00 | 14292.616
|  | Delta | 8118.797
PCO-097 | Place Signs Delineating Archaeological Sites |  | 2.424 | Non-existent | Approved 11-Oct-00; Owner responsibility per contract
PCO-112 | Provide Support for Owner’s Welding Auditors in Caceres |  | 12.685 | Non-existent | Approved 11-Oct-00; Owner welding inspectors (costs of Parsons reps)
PCO-114 | Topographical Survey at KP 75+902 |  | 4.704 | Non-existent | Approved 11-Oct-00
PCO-123 | Road Work at Spreads 3 & 4 as part of Owner Community Works |  | 119.295 | Non-existent | Approved 11-Oct-00; Owner requested
|  | Sub total as of 11-11-00 | 14431.724
|  | Delta 11-11 and 04-06 | 8257.905
|  | Delta 11-11 and 06-22 | 139.108