## Research Members
Name | Initials
Alex Huang | AH
Amitava Dhar | AD
Bob Lee | BL
Ben Parsons | BP
Charlie Weldon | CW
Chonawee Supatgiat | CS
Clayton Vernon | CV
Gwyn Koepke | GK
Hector Campos | HC
Iris Mack | IM
Jaesoo Lew | JL
Joe Hrgovcic | JH
Jose Marquez | JM
Kate Lucas | KL
Kenneth Parkhill | KP
Kevin Kindall | KK
Kirstee Hewitt | KH
Krishnarao Pinnamaneni | KP
Lance Cunningham | LC
Li Sun | LS
Martin Lin | ML
Maureen Raymond | MR
Mike Roberts | MR
Mathew Williams | MW
Nelson Neale | NN
Osman Sezgen | OS
Paulo Issler | PI
Praveen Mellechavuru | PM
Rabi De | RD
Rakesh Bharati | RB
Roman Zadorozhny | RO
Seksan Kiatsupaibul | SK
Sevil Yaman | SY
Shane Green | SG
Stinson Gibner | SG
Stephen Bennet | SB
Steve Leppard | SL
Tom Barkley | TB
Tom Halliburton | TH
Tanya Tamarchenko | TT
Vince Kaminski | VK
Vasant Shanbhogue | VS
Yana Kristal | YK
Youyi Feng | YF
Zimin Lu | ZL
Bold Font: Top Priority
Regular Font: Medium Priority
Italics: Low Prioroty

## Projects
Credit Group
| Current Tasks | People | Enron Units | Customer | Status | Comments
2001-03-30 | Background Materials | VS,VK,AD,IM | Research |  | Ongoing | Documents in O:\Research\Dropbox
"Actively Managing Corporate Credit Risk" (Punchline = estimate probability of default from data)
2001-04-02 | Meeting w/ EnronCredit - 23rd Floor | VS,AD,IM | Credit, Research | Craig Chaney | Ongoing | * Craig's goal is to develop a "private firm model" to estimate the probability of bankruptcy for firms w/o publicly traded debts and equities.
* Cast of Players (Scott Salmon, Mike Mumford, Ben Parsons, Eric Patrick, Craig Chaney)
[5 empty] | Ongoing | * VK's commitment to EnronCredit - deliver a pricing model by August
[5 empty] | Ongoing | * AD's says biggest obstacle is DATA
[5 empty] | Ongoing | * Craig Chaney wants a Gant Chart (Detailed outline of the milestones. What are the contexts? What are the boundaries? How long? Short term or long term tenors? Bankruptcy? Data requirements for private firms? What kind of data? Number of names? How much data?? Best data sources - e.g., Amadeus (Europe), Bloomberg, Compustat, D&B, Equifax, Experian, FAME (Europe), Transunion, TRW, etc.? Confidence Levels? Existing Models - e.g., "Credit to Be", Placement Model, Movement Model, Neural Nets model, etc.? Software requirements - e.g., Eviews, SPSS, etc.? When is it productive for IM to go to London? Her "go to" person in London? When will the model be completed?
[5 empty] | Ongoing | * VK says IM should plan trip to UK in 3-4 weeks
2001-04-03 | Conference with London Credit Group | AD,IM,VS | Credit, Research | London Credit |  | * Neural net version of model created by Ben Parsons is most effective at higher dimensional/nonlinear end
* Private Models for July: ( Interim pushes) improve existing models, quality of existing names, and accuracy of pricing
* Private Firm Model: (Longer Term goal) London/US Research Partnership; Ramp up data acquisition
* Initial Model Focus - Europe first - e.g., price 75% of European counterparty by end of July. US later - e.g., leverage off European model to price 75% of Enron's US counterparties by year end? OR, both, simultaneously - Craig Chaney's empahsis?
* Parent/Subsidiary Scope: Price both parent (may be public) & subsidiary (may be private) individually and then do analysis on the "gap". AD suggested distinguishing between the parent and subsidiary via an indicator variable in the model.
* Mike Mumford is expanding his team & freeing up some of his time so that he can work w/ IM on the private firm model
* Craig thinks partnership w/ S&P to purchase model & data is what market is most interested in.
|  | IM |  |  |  | * IM will do data research: Initially will request static dump; Later will seek data feed on a regular basis. She will initially focus on US data sources and Mike Mumford will focus on European sources.
* Use web, etc. in data research. For example, will ask Experian to come to Houston to give us a presentation on what available data sources, costs, etc. (Note: "Credit-to-Be" uses Experian data sources.) Hopefully the UK guys can attend this presentation. In addition, IM will go to London to learn about European data sources.
2001-04-03 | Order software packages | AD,IM,Anita |  | Craig Chaney | Done | SPSS 10 for Windows, Eviews, Neural Network package (Neuralshell by Ward Systems Group - http://www.wardsystems.com/products.asp?p=neuroshell2&page=7)
2001-04-04 | Basic Data Analysis | IM |  |  |  | Do some basic industry analysis on data. Other preliminary analysis has also been done. Further info can be found in O:\Research\Common\From_adh\Scoring Model and O:\Research\Common\From_adh\CREDITDOTCOM\CDS.… (see notes on 4/3/01 for more details).
2001-04-10 | Selection of Data Vendor(s) | AD,IM | Credit, Research |  | 1-week goal | Conference call with the UK to discuss IM's Web-based research and phone discussions with various data vendors: Amadeus (Europe), Bloomberg, Compustat, D&B, Equifax, Experian (http://www.experian.com/catalog_us/tec.html), FAME (Europe), Transunion, TRW, etc.
Whenever | Study Moody's RiskCalc Product (http://www.moodysqra.com/pubfirm/ |  |  |  |  | Moody's uses "RiskCalc" to determine the PD (Probability of default) on numerous public and private companies. They offer 1 year and 5 year historical PDs and then discuss "driving factors" which helped them reach their decision - such as, Total Liablities/Total Assets, ROE, ROA, etc.. RiskMetrics has a partnership with Moody's whereby they have integrated RiskMetrics' portfolio credit application with Moody's public and private RiskCalc models. This allows users of RiskMetrics to automatically upate the PDs for anything in their portfolio that RiskCalc covers. User ID and PW in (4/3/01) email from David P. Dupre and Mike Mumford.
2001-04-24 | Decide on data vendor | VS,VK,AD,M | Credit, Reserch |  | 3-week goal
??? | Professor Darrell Duffie | VS,VK,AD,IM | Research, Stanford |  | New | Compile model documentation to be sent to Professor Duffie. Refer to info in email from Ben Parsons on 4/4/01.