## Sheet1
NETCO Start Up Plan
Credit Risk Management
|  | Task | Duration | Start | Finish | Responsibility
Estabish NETCO counterparty base |  |  | 3 days | 2002-01-07 | 2002-01-10 | Credit
| Create master list of potential CPs from CAS, including criteria: |  | 2 days | 2002-01-07 | 2002-01-09 | Credit
Entities ENA, ECC and EPMI only
Products of Gas and Power only
Status of Active
| Combine and analyze above results with EOL CP list |  | 1 day | 2002-01-09 | 2002-01-09 | Credit
| Circulate list to Credit, GCP and desks for final approval to upload |  | 1 day | 2002-01-10 | 2002-01-10 | Credit
| Cleanse resulting counterparty list |  | 10 days | 2002-01-11 | 2002-02-11 | Credit
| Integrate GCP data set with new owner to ensure reporting consistency |  | 1 month | launch |  | GCP
Continue to perform credit reviews for NETCO counterparties (top 50 done) |  |  | 1 month | launch |  | Credit
Perform counterparty analysis if not within last six months
Assign credit score
Determine appropriate credit limits (dollar, tenor, term & potential exposure)
Input results of above into NETCO CAS
Populate EOL profile and limits
Execute trading contracts |  |  | 2 months | launch
| Identify initial target contract customers |  | in progress |  |  | Commercial
| Specify contracts to be put in place (EEI, ISDA, Master Firm) |  | in progress |  |  | Legal
| Develop credit terms |  | 2 months | launch |  | Credit
| Send drafts to counterparties |  | 2 months | launch |  | Legal
| Negotiate terms as necessary |  | 2 months | launch |  | Credit / Legal
Guarantys - outgoing and incoming |  |  | 1 month | 2002-01-10 | 2002-02-10
| Identify customers which require credit support |  |  | 2002-02-01 | 2002-02-28 | Credit
| Draft form of guaranty |  |  |  |  | Legal
| Send draft of guaranty to counterparties |  |  |  |  | Credit
| Negotiate format as necessary |  |  |  |  | Legal
Credit Reserve
Coordinate process with new owners
Models migrated via IT transition
Transaction model - Excel
Transaction model - RisktRAC
Establish credit support procedures for NETCO |  |  | 7 days | 2002-01-11 | 2002-01-21 | Credit
Obtain legal input as to access to ESTATE credit hard copy files
|  | Hard copy credit files by counterparty | 4 days | 2002-01-11 | 2002-01-16 | Credit
Keep any files or components thereof
Create new files for any information not retained from ESTATE
| Develop procedures for contract briefings, name changes and assignments |  | 2 days | 2002-01-17 | 2002-01-18 | Credit / GCP
| Establish new procedure for setting up new counterparties which credit reviews first |  | 1 day | 2002-01-18 | 2002-01-21 | Credit / GCP
| Develop procedures for internal GCP / Credit interface with regard to relationships |  | 1 day | 2002-01-18 | 2002-01-21 | Credit / GCP
Policy
| Incorporate credit policy within NETCO Risk Management Policy |  | 24 days | 2002-01-21 | 2002-02-21 | Credit / MRM
Separate CAS systems into NETCO and ESTATE |  |  | 5 days | 2002-01-15 | 2002-01-20 | Credit / IT
| ESTATE systems scenario testing |  | 5 days | 2002-01-07 | 2002-01-12 | Credit / IT
Determine completeness of feeds from ERMS, EnPower, Sitara, CPR and Unify
Create dummy CPs, books, contracts, deals, etc
Test each through systems to ensure flow
| NETCO CAS systems testing |  | 5 days | 2002-01-15 | 2002-01-20 | Credit / IT
Determine which data fields to be copied over from ESTATE
Copy specified fields for specified counterparties into NETCO version
Determine proper Canadian interface
Test NETCO CAS systems
|  | Determine interfaces required by new owners | 1 month | 2002-02-01 | 2002-02-28
Separate RMS (RisktRAC) systems into NETCO and ESTATE
ESTATE systems scenario testing
| NETCO systems testing |  | 10 days | 2002-01-07 | 2002-01-18 | Credit / MRM
Set up new risk books
Set up portfolio heirarchy structure
Copy all new curves from ESTATE to NETCO version
Determine which books not applicable for Credit and exclude
SEE MARKET RISK / RESEARCH PROJECT PLAN
Define process to reconcile DPR, Accounting and Risk Systems |  |  | undetermined
Set up new credit reporting procedures and interface with accounting for NETCO |  |  | undetermined
Subscriptions to place
S&P
Moody's
D&B
DBRS, Fitch??
Credit Scoring Model
Coordinate process with new owners
Moody's RiskCalc potential purchase
Training of analysts
People |  |  | 39 days | 2002-01-07 | 2002-02-28
| Retention Plan |  | 10 days | 2002-01-07 | 2002-01-18
| Finalize |  | 1 day | 2002-02-28 | 2002-02-28