## Sheet1
DEAL PIPELINE REPORT
October 22, 2001
|  |  |  | Mgr/ | [8 empty] | Potential | Risk Adj
|  |  |  | Assoc/ | Type of | Deal | Location of |  |  |  | Expected | Probability | Earnings | Earnings
New Projects | Originator | Engr | Geol | Anal | Deal | Description | Properties | $MM | Status | Action Plan | Close | of Closing | [$MM] | [$MM]
Alpine | Eubank | BP |  | BO | VPP/Debt | Refinance debt, provide development capital | Gulf Coast | 15 | Technical review underway, small PDP component and large undeveloped component | Evaluate VPP and sub. Revolver structure | 4Q | 10% | 1 | 0.1
Aurora | Thompson/Ballard | CF | CC | KY | EQ/Mezz | Equity to redevelopment | Alaska | 20 | Met with Enron Business Plan | Evaluate reserves; develop proposal |  | 10%
CGAS | Melendrez | CF |  | JH | Sale/VPP | Sell CGAS and have VPP with new owner. | Ohio | $52.5/$40 | Met with CGAS 9/26 to review marketing issues. |  | 2001-11-30 | 60%
Cuba Project | Eubank/Ballard | CF/TM |  | BO | VPP | Monetize reserves | Gulf Coast | 50 | Engineering review complete | Meeting on 10/22 to discuss proposal. | 2001-12-15 | 25% | 4 | 1
ECA | Kalb |  |  | KY/AR | VPP/Equity | Monetize PDP | West Virginia | $15mm/yr | Structure s.t. LJM | Present structure to ECA this week | 4Q | 20% | $3.5 /year | $0.70/ year
EEX | Ballard | CF/BP | KD | KY | VPP | Expanding existing onshore facility | STX, Panhandle | 160 | Technical review complete; documents sent to EEX - waiting on comments. | Complete due diligence; close in December | December | 60% | 6.5 | 3.9
[12 empty] | Total: | #REF! | #REF!
[5 empty] | Deal |  | Location of
Monitoring Projects | Commercial | Engr | Geol/Gph |  | Description |  | Properties |  | Status |  | Action Plan
Andex | CJT/Ballard | CF | KD | BO | VPP/Sub Rev and monetize reserves |  | Various
Ameritex | Melendrez | CAF/AGM | CKC/GS |  | Prospect Generation Program |  | TX |  | Advised General Partner on 5/01 of our intent to enter into 6 mos partnership wind-down beginning 7/01. Will continue to drill/develop existing inventory of prospects until dissolution process begins at year end. Red Horse now sold and is drilling. |  | Get Patt. Ranch, S. Roleta, W. Lyford drilled by year end. New Narciso locations under review.
Bonne Terre | Melendrez | CAF/AGM | KD/GS |  | Exploration and Development of 200,000 acre position |  | Cameron Parish, LA |  | Dissolution finalized. Black Bayou Field reactivation underway by RIMCO. Evaluating locations to offset Pines Ridge discovery. Completed Blue Racer prospect as discovery. Will spud a 8,000' Discorbis test from Sabine Lake bottoming on Texaco fee to satisfy our 2nd 2001 well obligation. Partners met with Manti on 10/11 to discuss development strategy. Presented other Odom prospects at Lafayette Expo with good response from industry. |  | Working with Nexus & Resource Solutions to market additional Camerina Prospects. Will market Camerina prospects at Lafayette Expo. 9/18 & 9/19. Pursue new offers for Saturday Island property.
CGAS | Melendrez | CF | CKC/GS |  | Exploration Program |  | Ohio, PA & NY |  | Negotiating sale of CGAS which would include a VPP. |  | Have finalized details of Severance Plan and Annual Incentive Plan. Finalizing the Enterprise Value Plan.
Crescendo Energy |  | AGM | CKC |  | Equity & VPP |  | Utah & Colorado |  | Expect plant start-up in December [16 MMcf/d plant project]. Wildhorse gathering system acquired by Cantera Resources. Cantera has agree to install additional compression that will increase production by 500 MCF/D from 15 wells. |  | Evaluating additional drilling opportunities with low risk. Continue to work with gathering system operator to install additional compression.
Cypress | Melendrez | CAF/AGM | KD/GS |  | Exploration Program |  | S LA |  | Received DASH approval for $14.1MM. AFE received from Denbury. Agreed to participate for 1/8th interest in Saints/Brenda prospect. Jalapeno is ready except for Amerada Hess farmin. ECR will promote its 50% down to 25%. Vikings needs additional leasing before it is ready to go. Approved reprocessing of Greater Parcperdue area and acquisition of new data between Lakeside and Sweetlake areas. |  | Evaluating taking options on leases to protect position on potential prospects. Rozel to make recommendations. Offered Cowboys prospect leases under AMI to partners. TMR has rejected participation.
EEX | Melendrez |  |  |  | Forward sale contract |  | Various |  | Performing as planned. |  | Evaluating follow-on prepay - $130 MM.
Hanson | CJT/Eubank | CF | CKC |  | Develop E Sour Lake field |  | S TX |  | TP Ranch #3 - currently flowing 3.0 mmcfd & 185 Bopd. DASH completed for Adobe equity purchase. |  | Pursuing legal options.
Juniper | Melendrez | CAF/AGM | KD/GS |  | 3-D Shelf Exploration Program |  | GOM |  | Received one bid from Newfield for EI 57, currently evaluating offer. |  | Phase II extension of JV appears unlikely, explore dissolution scenario.
KCS Energy | Eubank |  |  | BO | VPP |  | Various |  | VPP meeting requirements.
Mariner |  |  |  |  | Equity |  | Various |  | Reviewing property base and exploration inventory. Currently evaluating Swordfish prospect. |  | Will complete review in September
NuTech Energy | Kalb |  |  | BO | Joint Ventures; Reserve Acquisition; Sale of Business |  |  |  | Discussions on salvage JV's with Superior and TriC and JTex sale continuing. Corp restructuring underway, s.t. final approval. Funded Joquin acquisition. |  | Close salvage JV. Obtain Enron restructuring approval and close. Continue funding WI acquisitions.
Preston Equity | Josey | [7 empty] | Met with Preston on 7/27 to discuss use of Enron 3D in the Cypress program. |  | Work with Preston to make data available to JV.
St. Mary's Prod | Josey | CF | KD |  | VPP |  | S LA |  | VPP meeting requirements.
Tarpon Equity |  |  |  | BO |  |  |  |  | Offer to Ocean/WT for EI 386 interest. |  | Operations to begin 4th quarter.
Texland Petroleum | Melendrez | CAF/AGM | KD/GS |  | Exploration Program |  | W TX |  | Will initiate flood operations at Hobb waterflood this month. |  | Complete Hobbs waterflood. Additional infill drilling investments being considered for Stockyard and E Hobbs.
Tri - C | Thompson |  |  |  | Equity |  | S TX |  | Agreed to participate in Badlands and Scott Field prospects in Lafayette Parish. |  | Review Pele prospect AFE.
Vastar | Melendrez | CAF/AGM | KD/CKC/GS |  | Exploration Program |  | S TX/S LA/ WY |  | Remaining leasehold interests in Kenosha & Midland may be prospective. Kenosha partner's meeting held on September 25. AFE received this week, engineering preparing economics.. |  | Attempt to farm in Vastar's 50% interest and drill a Hayes/Marg Tex attic shot w/Rozel.
Westwin | Melendrez |  |  | BO | Acquire & develop corporate equity |  | Permian Basin |  | Expect to have Indian Mesa production on by Sept. 1. Will be reviewing 7-8 projects with a total capital requirement of $3.5MM |  | Evaluate drilling programs - if successful, expand the programs & increase the borrowing base.