## Day7
Date | 2000-08-29
Well | San Arroyo #1 |  |  |  | TD | 5030
County/St. | Grand/Utah |  |  |  | Formation Completing |  | Entrada
Well Service Co, |  |  |  |  | Perfs | upper 4851-4923 4923-93 Lower 5009-15
Daily Cost |  |  |  | Daily Cost
Supervision |  |  | 450
Workover |  |  | 1500
Weathford BOP |  |  | 145
Packer |  |  | 1170
[6 empty] | total | 3265
[6 empty] | Cumulative cost | 15876
Details | FCP 5 psi on a 2" valve
Pumped 10 bbls of fluid
Picked up 7" big bore test packer
TIH Tag up bottom at 5007 Picked up 8' to 4999 ( bottom perf from 5009-15)
Set packer with 15pt of tension NU wellhead
Shut in 1 hour sitp 80 psi sicp 150
Open up well kick off flowed for 10 mins died.
Left tubing open to frac tank
45mins to frac tank well kicked off flowed for 10mins
Shut for a 30min build up sitp 0 sicp270
Open to frac tank left open fro 1 hour well kicked of flowed for 15mins.
Caught sample Load water KCl
5pm RU swab unit sicp 370
6pm SICP 450 tubing lite blow. Well kicked off flowed for 15 mins died
First fluild level at 3500' sicp 470
Started out of hole with swab got hung up at 3000 ft.
Working swab won't come free
SCIP 500 psi
Total fluid recovered today 5 bbls of load water
Pull tension on swab and left open to frac tank.
Caught gas sample N2 22% CO2 22% did not flow enough to get a good sample
| Jts 2 3/8 | Tbg FT |  | Packer Model |  | Arrow | Set at: | 4805
| Rods | Ft |  | Tubing Anchor Model |  |  | Set at:
Pump Size
Present Operation
Rig Operator |  | Red |  | Consultant | Ralph Baker
Co. Supervisor |  | Dan Reineke