## Sheet1
ENA East Originations - IPP Group
Project Development Status Report
NEW MERCHANT PROJECT DEVELOPMENTS
Resp.
Project Name / Target Operations Date |  | Milestone | Party | Comments / Status
Chicago / '01 |  | 800 MW Project Development Agreement | Mitro | Executed
| Calumet - 2 ABB 11N2 turbines | Provide participation notice | Stevens | Notice provided; need to negotiate LLC and Contribution Agreements
| Pontiac - 345kV | Develop for LM 6000 "Proposed Project" under PDA |  | 345kV interconnect will be more costly for LM 6000 deployment
| Torrance - 138kV | Develop for LM 6000 "Proposed Project" under PDA |  | Environmental remediation may be an issue (see site bank)
| Wilton 2 | Advise PERC of Wilton 2 cost over runs |  | PERC to install at Elwood
| Plano - 345kV | Develop for LM 6000 "Proposed Project" under PDA |  | 345kV interconnect will be more costly for LM 6000 deployment
Florida / '01 - '02 |  |  |  | All - GE 7FA, dual fuel, peak or baseload permit flexibility.
| Ft. Pierce / Vero Beach | Ft. Pierce to RFP | Fairley | Will respond to Ft. Pierce RFP; not likely '01 development potential
| Greenfield Merchant | Identify and option feasible sites for peaking and CC operation | Jacoby | Negotiating options in Homestead and Midway. Have submitted interconnection requests to FPL.
| Corbett Joint Venture | Negotiate agreement with Quixx | Krause | ENA to submit interconnect request to FPL.
|  | All - Supreme Court Order Clarification | Grube | Will seek standing to have order clarified to allow peakers - may take two months.
|  | All - FPL interconnect requests |  | FPL queue is 240 days. Need to expedite to make June '01 start.
4 interconnect requests submitted to FPL - Homestead, Broward, Midway, Corbett
Iowa / '01 |  | Site selection / research | Moore | 2 MidAm sites optioned (see site bank).
|  | Certificate of Convenience and Necessity | Plauche | Will submit CCN application by April 28. Estimated time to complete is 4 months.
|  | Interconnection request |  | Submitted for multiple turbine configurations
|  | MAPP accreditation |  | Poses significant risk to '01 development optionality
|  | Non-PSD air permit applications |  | To be submitted week of May 1 for multiple turbine configurations.
|  | Water availability |  | ENSR released to prep. permits and evaluate water & other site resource and environmental issues
Entergy Louisiana / Texas / '01 - '02 |  | Site selection / research | Moore | Two sites optioned, additional site to be optioned shortly. (see site bank)
Plauche
|  | Interconnection queue spot |  | Will submit interconnect requests by April 28. Entergy's current queue is 18 months.
|  | Evaluation of Cogentrix sites |  | 2 sites potentially can be acquired from Cogentrix for an '01 start.
ENSR released on permitting activities.
United Illuminating - '01 |  | Site selection / research | Krimsky | Two potential '01 brownfield development options identified for UI.
| Pratt & Whitney | Execute site lease and LOI |  | Will need to use P&W twin pack turbines if option exercised
| Sprague Paper | Execute site lease and LOI |  | Will develop as an LM 6000 site
ECAR - AEP or Cinergy / '01 |  | Site selection / research | Chance | Two sites to be optioned and permitted. Three sites previously optioned being evaluated.
VEPCO - '01 |  | Site selection / research | Keenan | Will either option former Electricities site or nearby
SPP - Missouri / '01 |  | Site selection / research | Chance | Will option sites at Ameren / AEC interface
Georgia - '01 |  | Site selection / research for '01 merchant LM 6000 plant | Keenan | Four sites being evaluated in Hart, Washington, Jefferson, and Richmond counties.
Will develop as a 6 - LM6000 facility
Y2K MERCHANT PROJECT DEVELOPMENTS
Resp.
Project Name / Target Operations Date |  | Milestone | Party | Comments / Status
Gleason |  | Execute TVA interconnect, manage Shelby upgrade costs | Jacoby | IFA executed; awaiting final signatures from TVA.
|  | Switchyard energization | Jacoby | Energized
|  | Westinghouse compressor diaphragms | Miller | June 1 commercial ops risk on CTG #3
|  | Interconnect agreement commercial ops compliance | Simmons | Commercial ops check list completed. Soderquist to manage commercial ops acceptance.
Soderquist
Wheatland |  | Execute IPL / Cinergy interconnect, manage interconnect costs | Dowd | Both IPL and Cinergy executed.
|  |  | Jacoby | Cinergy has dropped pursuit of the Facilities Const. Agreement.
|  | Switchyard energization | Jacoby | Energized
|  | Interconnection queue spot management | Jacoby | Engaging independent developer to approach Parke County
|  | Interconnect agreement commercial ops compliance | Soderquist | Commercial ops check list completed. Soderquist to manage commercial ops acceptance.
Simmons
Wilton Center |  | Execute ComEd interconnect, manage interconnect costs | Mitro | Executed
|  | Gas pipeline permit / construction / Northern Border interconnect | Mitro / Meyers | Complete
|  | Interconnect agreement commercial ops compliance | Soder. / Simmons | Commercial ops check list completed. Soderquist to manage commercial ops acceptance.
CUSTOMER PROJECT DEVELOPMENTS |  |  | Resp.
Project Name / Target Operations Date |  | Activity | Party | Comments / Status
ConEd |  | Development support for origination | Ader | 2-LM6000s
Bernstein
City of Austin / '01 |  | EPC, development, 3 year toll | McDonald | 4-LM6000s
|  |  | Keenan | Fixed price of $93.2M; requires SCR installation
PROJECT DEVELOPMENT SITE BANK
Calvert |  | Sell development asset / TVA settlement | Jacoby | Will push for TVA settlement after Gleason commercial ops.
Negotiating sale to AES
East Fork |  | Retain for continued evaluation of development potential | Chance | Three sites under option. Will keep options active.
Fulton |  | Sell development asset | Jacoby | Can terminate lease through August with $25k payment
Plano |  | Retain for continued evaluation of development potential | Mitro | Need to negotiate option renewal.
May use for Peoples JV.
Arpin, Wisconsin |  | Develop for '02 merchant application | Chance | Site jointly optioned; need to buy out Great River Energy.
Jefferson Davis Parish, LA |  | Develop for '01 merchant application | Moore | 120 acres @ $1k/ acre. FGT pipe w/ 500kV Entergy. Wetland determination underway.
|  |  | Plauche | Interconnect queue may push to '02
Calcasieu Parish, LA |  | Develop for '01 merchant application | Moore | 60 acres @$5k/acre. FGT pipe w/ 500kV & 230kV Entergy.
|  |  | Plauche | Interconnect queue may push to '02
St. Charles Parish, LA (south of New Orleans) |  | Develop for '01 merchant application | Moore | 45 acres @ $19k / acre. Acadian pipe w/ 230kV and 500kV Entergy.
|  |  | Plauche | Interconnect queue may push to '02
Chicago, Il - Torrance |  | Develop for '01 merchant application under PDA with Peoples | Mitro | Site controlled by Peoples. Site remediation may be an issue.
Stevens
Washington County, IA |  | Develop for '01 merchant application | Moore | 80 acres @ $10k / acre. NGPL pipe w/ 345kV MidAm.
|  |  | Plauche | MAPP accreditation may push to '02
Louisa County, IA |  | Develop for '01 merchant application | Moore | 80 acres @ $5k / acre. NGPL pipe w/ 345kV MidAm.
|  |  | Plauche | MAPP accreditation may push to '02