## Phase 2
|  | Done |  | Responsibility | Resources | Date | Status Notes
Garden
| Customer Training/Brochures Functional/Content Spec |  |  | Mike Danielson | Kal/Bob | 23/6/00 | Providing Content to Viant and awaiting Viant materials. Ongoing efforts.
| Functional Construction - Project Management |  |  | Mike Danielson | Bob/Rahil | 23/6/00 | See above
| Look and Feel - Project Management |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Quotes screen Interface
| Functional Specification |  |  | Dave Forster | Mark Dilworth | 23/6/00 | Developing as content comes together
| Functional Construction |  |  | Jay Webb | Mike B./ Theresa | 23/6/00 | Developing as content comes together
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Filtering
| Functional Specification |  | Y | Team |  | 23/6/00 | Completed.
| Functional Construction |  |  | Jay Webb | Mike B. | 23/6/00 | s/b combined with Quotes screen and available for testing week of 26/6/00.
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Real Time News
| Contract Negotiation |  | Y | Dave Samuels | Rahil | 30/5/00 | Reuters (News and Stock Quotes) and Dow Jones - done. TDN appears unlikely for Phase 2
| Functional Specification (incl Preferences) |  | Y | Dave Samuels | Rahil | 2000-02-06 | First draft out for comments. Comments due for signoff 5/6/00
| Functional Construction |  |  | Jay Webb | Theresa | 13/6/00 | Reuters in test for week of 19/6/00. Dow Jones feed expected in 1-2 weeks
| Preferences Architecture Construction |  |  | Jay Webb | Dave Samuels/Rahil/Theresa | 23/6/00 | Initial specification done. Needs to be discussed and refined.
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Newsletters
| Contract Negotiation |  |  | Dave Samuels | Rahil | 2000-08-06 | Pete Argus, Fieldstone, NGI signed. Scudder close to completion. Heren and Platts officially "dead". FT unlikely. Formats to include pdf and html
| Functional Specification (incl Preferences) |  | Y | Dave Samuels | Rahil | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb |  | 23/6/00 | Low Development time anticipated to complete.
| Preferences Architecture Construction |  |  | Jay Webb | Dave Samuels/Rahil | 23/6/00 | Initial specification done. Needs to be discussed and refined.
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Enron Generated Content (Lagrasta newsletter, Tlapek tech analysis)
| Functional Specification (incl Preferences) |  | Y | Dave Samuels | Rahil | 23/6/00 | Completed.
| Functional Construction |  |  | Jay Webb |  | 19/5/00 | Dave S. writing functional spec for week of 15/5/00. Low Development time anticipated to complete
| Preferences Architecture Construction |  |  | Jay Webb | Dave Samuels/Rahil
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Charting
| Functional Specification |  | Y | Dave Samuels | Kevin Montagne | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb | Kevin Montagne | 23/6/00 | Searching for best solution.
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Weather
| Contracts Negotiation |  | Y | Dave Samuels | Rahil | 2000-10-05 | Accuweather done.
| Functional Specification |  | Y | Dave Samuels | Rahil | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb | Kevin/Theresa | 13/6/00 | data feed should be in place in week of 12/6/00
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Chat
| Functional Specification |  | Y | Dave Forster | Dave S/Dave F/Bob | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb | Mike B/Mike G | 23/6/00 | ETA: Week of July 9
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Enron Indeces
| Functional Specification |  | Y | David Samuels | Rahil | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb |  | 23/6/00 | Basically Complete - just needs final hooks into rest of website
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Customer Transaction Data Feeds (XML interface)
| Functional Definition |  | Y | Mark Dilworth |  | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb | Mike G. | 13/6/00 | Server side complete. Client side not started
Stock Quotes
| Functional Specification |  | Y | David Samuels | Rahil | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb | Theresa | 19/5/00 | In test week of 19/6/00
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Messaging
| Functional Definition |  | Y | Dave Forster |  | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb |  | 13/6/00 | Engine in place. Publisher and Client to be written. Not much time expected to be required.
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Conversion Calculator
| Functional Definition |  |  | David Samuels | Rahil | 16/5/00 | First draft due 5/6/00
| Functional Construction |  |  | Jay Webb | Theresa | 19/5/00 | Initial Application done. Further refinements to come.
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Help Guide
| Functional Definition |  | Y | Dave Forster |  | 23/6/00 | Completed
| Functional Construction |  |  | Laura Johnson | Jay Webb | 22/5/00 | Use Standard Windows Help Guide functionality
| Look and Feel |  |  | n/a |  | 22/5/00 | Use Standard Windows Help Guide functionality
Administration Screens
| Functional Definition |  | Y | Dave Forster | Savita Puthigai | 23/6/00 | First draft circulated for comments
| Functional Construction |  |  | Jay Webb | Theresa | 22/5/00
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Getting Started Guides |  |  |  | Kal Shah |  | 22/5/00 | Awaiting Site Development
Price Limit Orders
| Functional Definition |  |  | Dave Forster | Savita Puthigai | 23/6/00 | Functional Specification being drafted. Awaiting trader feedback
| Functional Construction |  |  | Jay Webb |  | 23/6/00 | Awaiting Functional Spec
| Look and Feel |  |  | Mike Danielson |  | 23/6/00 | Style Sheets expected 23/6/00
Position Report
| Functional Definition |  |  | Dave Forster | Savita Puthigai | 23/6/00 | Functional Specification being drafted. Report to be very simple.
| Functional Construction |  |  | Jay Webb |  | 23/6/00 | Awaiting Functional Spec
| Look and Feel |  |  | Mike Danielson |  | 23/6/00 | Style Sheets expected 23/6/00
Update of "Old Site" into new Look and Feel
| Functional Construction |  |  | Jay Webb |  | 23/6/00 | Not Started Yet
| Look and Feel |  |  | Mike Danielson |  | 23/6/00 | Style Sheets expected 23/6/00

## Phase 2.x
|  | Done |  | Responsibility | Resources | Date | Status Notes
New Auction Engine
| Functional Definition |  | Y | Dave Forster |  | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb | Kevin M. | 23/6/00 | No ETA yet.
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Soft Transactions (RFQ)
| Functional Definition |  |  | Savita Puthigai |  | 23/6/00 | Completed
| Functional Construction |  |  | Jay Webb |  | 23/6/00 | No ETA yet
| Look and Feel |  |  | Mike Danielson | Kal/Bob/Dan/Rahil | 23/6/00 | Style Sheets expected 23/6/00
Wireless Applications
| Functional Definition |  | Y | Theresa Smith |  | 23/6/00 | High level specification completed. Further Specs required
| Functional Construction |  |  | Jay Webb | Theresa | 23/6/00 | To be done by outside Agency. Aethernet and Outer Curve being considered
| Look and Feel |  |  | Theresa Smith |  | 23/6/00 | Style Sheets expected 23/6/00
Price Alarms
| Functional Definition |  |  | Dave Forster | Savita Puthigai | 23/6/00 | Functional Specification being drafted.
| Functional Construction |  |  | Jay Webb |  | 23/6/00 | Awaiting Functional Spec
| Look and Feel |  |  | Mike Danielson |  | 23/6/00 | Style Sheets expected 23/6/00

## Launch To-do
|  | Done | Responsibility | Resources | Date | Status Notes
Brochures mailed to Existing Customers |  |  | Kal Shah
| Brochure Design |  | Kal Shah
| Brochure printing |  | Kal Shah
| Mailing List identification |  | Bob Shults/Nick Mooney
Brochures mailed to new (potential) customers |  |  | Kal Shah
| Brochure Design |  | Kal Shah
| Brochure printing |  | Kal Shah
| Mailing List identification |  | Bob Shults/Nick Mooney
Press Release sent |  |  | Kal Shah
| Drafted |  | Kal Shah
| Approved |  | Kal Shah
Getting Started Guide sent to customers |  |  | Kal Shah
| Drafted |  | Kal Shah | Laura Johnson
| Printed |  | Kal Shah
FAQ's for PCG, Call Center and Marketing |  |  | Laura Johnson
| Drafted |  | Laura Johnson
Call Center Training on new website functionality |  |  | Frank Davis?
Marketing training on new website functionality |  |  | Bob Shults/Bob Schorr
Marketing presentations/calls to promote website functionality |  |  | Bob Shults/Bob Schorr
Trader/ internal user Info pack - What's new with phase 2? |  |  | Kal Shah
| Drafted |  | Kal Shah | Savita Putigai
| Printed |  | Kal Shah | Savita Putigai

## Speclist
Not Drafted
Position Management
Being Drafted
Price Limit Orders
Administration
Price Alarms
First Draft Complete - Awaiting Discussion
Wireless
RFQ
Enron Indices
Help Guide
Conversions Calculator
Charting
Auctions
Awaiting Final Comments
Chat
Messaging
News
Publications
Stock Quotes
Transaction Data Feeds
Weather
Completed

## Stack Manager
|  | Done | Responsibility | Resources | Date | Status Notes
Power Interface
| Functional Specification |  | Simon Hastings
| Functional Construction |  | Bryan Hudson | Stephen Simons/Jay Webb
Spreads Interface
| Functional Specification |  | Andy Zipper
| Functional Construction |  | Jay Webb
Configuration Settings Saving |  |  | Jay Webb |  | 2000-10-05 | Expected Construction Completion week of 8/5/00
Price and Volume Delta Saving |  |  | Jay Webb |  | 2000-10-05 | Expected Construction Completion week of 8/5/00
Grandparents |  |  | Jay Webb |  | 2000-10-05 | Expected Construction Completion week of 15/5/00
Advanced Options
| Functional Specification |  | Andy Zipper
| Functional Construction |  | Jay Webb
Intermediate Options
| Functional Specification |  | Andy Zipper
| Functional Construction |  | Jay Webb
Advanced Sorting
| Functional Specification |  | Andy Zipper/Dave Forster
| Functional Construction |  | Jay Webb
Grouping of Products
| Functional Specification |  | Andy Zipper/Dave Forster
| Functional Construction |  | Jay Webb
Formula Pricing
| Functional Specification |  | Andy Zipper
| Functional Construction |  | Jay Webb
Floating "Other Products" Window |  |  | Jay Webb
Autotrader/autoarbitrager
| Functional Specification |  | Andy Zipper
| Functional Construction |  | Jay Webb
Mixed Basis and Syncopated Links |  |  | Jay Webb
Autohedge |  |  | Jay Webb |  | 2000-10-05 | Done & tested, but needs to be officially rolled out to Traders

## Website
|  | Done | Responsibility | Resources | Date | Status Notes
Advanced Options Interface
| Functional Specification |  | Andy Zipper
| Functional Construction |  | Jay Webb
| Look and Feel |  | Mike Danielson | Kal/Bob/Dan/Rahil
Spreads Interface
| Functional Specification |  | Andy Zipper
| Functional Construction |  | Jay Webb
| Look and Feel |  | Mike Danielson | Kal/Bob/Dan/Rahil

## Other
|  | Done | Responsibility | Resources | Date | Status Notes
Connectivity
AT&T Line Install |  |  | Jay Webb/Dave Forster | Anchi Zhang | 2000-10-05 | Preliminary work to be done week of 8/5/00. Updated timeframe requested from Anchi.
Additional Line Install |  |  | Dave Forster/Jay Webb | Frank Davis/Anchi Zhang | 2000-10-05 | Initial results not showing a conclusive winner. Additional information being gathered by HelpDesk. Awaiting Results.
Direct Lines
| Espeed? |  | Louise Kitchen
Reuters?
| EBS |  |  | Arshak Sarkissian

## Life Support
These items are close to "dead" - not being pursued for the time being
|  | Done | Responsibility | Resources | Date | Status Notes
Analytics (this may be dropped)
| Functional Specification |  | Dave Samuels | Kevin Montagne
| Functional Construction |  | Jay Webb | Kevin Montagne
| Look and Feel |  | Mike Danielson | Kal/Bob/Dan/Rahil | 2000-11-05 | Selected Viant as outside agency. Scope definition and project comencement begins 12/5/00. Project deadline 29/06/00
Price Data Feeds
| Functional Specification |  | Dave Samuels |  | 19/5/00 | Available feeds include Nymex, IPE, CME
| Functional Construction |  | Jay Webb |  | 2000-10-05 | Awaiting Functional Spec
| Look and Feel |  | Mike Danielson | Kal/Bob/Dan/Rahil | 30/5/00 | Selected Viant as outside agency. Scope definition and project comencement begins 12/5/00. Comps decision on June 1/00