## STATS
Facility | Audit Date | Complete Action Items | Open Action Items | Total | Scheduled for Later | Late | Actual Percent Complete | Most Recent Update | Notes
ASIA/PACIFIC
Subic | 1999-05-01 | 53 | 10 | 63 | 1 | 4 | 84.13% | 2000-12-11
Guam | 1999-11-01 | 65 | 65 | 130 | 19 | 45 | 50% | 2000-07-26
Daehan City | 1999-12-01 | 69 | 93 | 162 | 88 | 5 | 42.59% | 2000-07-26
Pusan City | 1999-12-01 | 84 | 49 | 133 | 19 | 29 | 63.16% | 2000-07-26
SK Ulsan | 1999-12-01 | 124 | 75 | 199 | 39 | 36 | 62.31% | 2000-07-26
Batangas | 1999-05-01 | 55 | 3 | 58 | 0 | 2 | 94.83% | 2000-12-11
SOUTHERN CONE
Elektro | 1999-09-01 | 6 | 19 | 25 | 0 | 19 | 24%
Ventane | 1999-08-01 | 9 | 169 | 178 | 12 | 157 | 5.056% | 2000-07-01
Calife | 1999-09-01 | 5 | 43 | 48 | 0 | 43 | 10.42%
Pantanal Energia (Cuiaba) | 2000-05-01 | 0 | 139 | 139 |  |  |  |  | No updates received to-date
GTB (Gas TransBoliviana) BBPL |  | 0 | 252 | 252 |  |  |  |  | Data being processed
Transredes |  | 0 | 396 | 396 |  |  |  |  | Data being processed
CARIBBEAN
Centragas | 1999-05-01 | 32 | 30 | 62 | 0 | 29 | 51.61% | 2000-07-26
PQPC | 1999-10-01 | 12 | 6 | 18 | 3 | 2 | 66.67% | 2000-07-31
Procaribe | 2000-02-01 | 240 | 0 | 240 | 0 | 0 | 100% | 2000-07-25
Progasco | 2000-02-01 | 38 | 251 | 289 | 87 | 159 | 13.15% | 2000-12-11
San Juan Gas | 2000-02-01 | 42 | 145 | 187 | 4 | 141 | 22.46% | 2000-12-11
TGS | 2000-04-01 | 0 | 198 | 198 |  |  | 0% |  | No updates received to-date
TGS Cerri | 2000-04-01 | 0 | 144 | 144 |  |  | 0% |  | No updates received to-date
IGL - Ferry Road | 2000-05-01 | 0 | 423 | 423 |  |  | 0% |  | No updates received to-date
IGL - Spanish Town Road | 2000-05-01 | 0 | 414 | 414 |  |  | 0% |  | No updates received to-date
Smith Enron Cogen | 1998-10-01 | 73 | 38 | 111 |  |  | 65.77%
EUROPE
Teesside Gas Processing Plant | 2000-06-01 |  |  | 211 |  |  |  | 2000-12-14 | Please note that this number is a raw count of Total Action Items. Updated numbers will be provided on next month's report.
Teesside Power Plant | 2000-06-01 | [7 empty] | Have not received tracking report from facility
Trakya Marmara Plant | 2000-08-01 | 0 | 393 | 393 |  |  |  |  | Report sent 12/8/00
INDIA
Dabhol Power Plant | 2000-08-01 | 0 | 294 | 294 |  |  |  |  | Report sent 12/8/00
USA
New Albany Peaker | [8 empty] | Data being processed
Brownsville Peaker | [8 empty] | Data being processed
TOTAL ACTION ITEMS |  | 907 | 3649 | 4767