## 2001
4Q 2001 Doorstep Schedule for planned visits
Week | Group | Location | Days (guide only) | Energy ops | MRM RAC | Deal tester | Timing discussed with EO | Cleared with EO, RAC, EAS Team | Notes | Date Edited | Change Per | P&L YTD 8/30/01 In 000's | GRMO personnel | RAC personnel | Deal Tester
1st Q 2001
2001-01-10 | EEL | New York - Metals |  | Shona Wilson | [5 empty] | 2001-04-10 | Beth Apollo
2001-02-02 | EEL | Germany - Recycling (Frankfurt, Hamburg, Essen, Nurenburg), Brokerage | 2 | Shona Wilson |  | AA Deal Tester
2001-02-23 | E Americas | Monterrey (Mexico) | 2 | Beth Apollo | Mechelle Atwood (EAS) | EAS - Juan Camarillo
2000-03-12 | EES | London/Oxford - EES | 3 | Sheila Glover | Vlady Gorny | Veronica Valdez |  |  |  | 2001-04-10 | Beth Apollo
2000-03-12 | EEL | Madrid - Enron Direct | 2 | Sheila Glover | Vlady Gorny | NA
2000-03-29 | E Americas | Denver - Gas (end of week) | 2 | Shona Wilson | Mechelle Atwood (EAS) | NA |  |  |  | 2001-04-10 | Beth Apollo
2nd Q 2001
2001-04-02 | E Americas | Calgary - Power, Gas (3/12 - no deals, no profits yet, only G&A, Mkt won't open till 3Q) | 3 | Shona Wilson | Frank Hayden | EAS - Clayton Stafford | y | EO |  | 2001-04-10 | Beth Apollo
2000-04-09 | EEL | London - Metals (Agency, Brokerage, Recycling, Softs) Scoping Only | 2 | Brenda Herod | NA | NA
2000-04-16 | EEL | Montreal - Agency Primary Aluminium | 2 | Laura Scott | NA | Christy Lobusch |  |  |  | 2001-04-06 | Beth Apollo
2001-04-23 | EGM, EEL | Sydney (Power, Jet Fuel, Weather, Japanese Operations) | 8 | Brent Price |  | EAS - Juan Camarillo |  |  |  | 2001-04-10 | Beth Apollo
2001-05-07 | Corporate, EEL | Seoul ( Ske JV & Metals) | 4 | Heidi Mason | Michael Pitt | AA Deal Tester |  |  |  | 2001-04-06 | Beth Apollo
2000-05-14 | EEL | Oslo - Nordic Power, Weather | 2 | Stacey White | Cindy Horn (Ops) | AA Deal Tester |  |  |  | 2001-04-10 | Beth Apollo
2000-05-14 | EEL, EGM | Helskinki - Power & Liquids | 1 | Stacey White | NA | NA
2000-05-14 | EEL | Stockholm - Metals, EBS Energydesk | 1 | Cindy Horn | NA | NA |  |  |  | 2001-04-10 | Beth Apollo
2000-06-11 | EGM | Singapore - EGM | 5 | Shona Wilson |  | AA Deal Tester |  |  | John confirmed 4/27 | 2001-04-10 | Beth Apollo
2001-06-11 | E Americas | Houston - Power East | 10 | James New, Rob Yeo |  | AA Deal Tester |  |  |  | 2001-04-10 | Beth Apollo
2001-06-11 | E Americas | Houston - Gas | 10 | James New, Michael Wellings |  | AA Deal Tester |  |  |  | 2001-04-10 | Beth Apollo
2000-07-16 | Corporate | Mariner - Wholly Owned Investement | 1 | Nancy Hernandez | Frank Hayden | AA Deal Tester*
2001-07-23 | EBS | EBS London | 2 | Scott Earnest | Lloyd Fleming | AA Deal Tester* |  |  | confirmed 6/19
2001-07-23 | EIM | London - EIM | 3 | Scott Earnest | Lloyd Fleming | AA Deal Tester* |  | EO |  | 2001-04-10 | Beth Apollo
2001-08-13 | EEL | Shanghai - Metals | 3 | Jan-Erland Bekeng | John Suttle | NA |  | EO
2001-08-13 | EEL | Beijing - Metals | 3 | Jan-Erland Bekeng | John Suttle | NA |  | EO
Aug. 13 | EBS | EBS Houston | 4 | Christy Lobusch/Nancy Hernandez | Nick Paraschos | EAS - Vicky Gregorcyk or Brenda Haase |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 | 2001-05-04 | Beth Apollo
2001-08-20 | E Americas | Portland - Power West | 3 | Michelle Bruce | Minal Dalia | None needed
2001-08-20 | EGM | Houston - Weather, Coal, Emmissions | 5 | Kevin Sweeney | Mary Nordstrom | EAS - Clayton Stafford/Sandra Wilson |  |  | Confirmed EAS with Mechelle/Shawn on 7/24
2001-09-10 | E Americas | Sao Paulo - Power, Gas | 3 | Keith Constadine | Frank Hayden | AA Deal Tester |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 | 2001-04-06 | Beth Apollo
2001-09-10 | E Americas | Buenos Aires - Power, Gas, TGS | 3 | Keith Constadine | Frank Hayden | AA Deal Tester |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 | 2001-04-10 | Beth Apollo
2001-11-05 | EEL | London Metals (Brokerage, Concentrates, Softs, Recycling) |  | Brenda Herod, Todd Busby |  | AA Deal Tester |  |  |  | 2001-04-10 | Beth Apollo | 14372 | Brenda Herod | Ted to provide | Andersen deal tester needed. Paul Bromley to coordinate with Paul Day.
2001-11-05 | EEL | Germany - Essen recycling, Warsaw, Frankfurt - Continental Power and Gas | 3 | Shona Wilson | Bjorn Hagelmann | None needed per Shona | [5 empty] | 1800 | Shona Wilson | Bjorn Hagelmann | Andersen needed at Essen
2001-11-05 | EGM | Houston - Interest Rate, FX, Equities, Softs | 5 | Mike Jordan, Michael Kass |  | EAS - Ken Lewchuk |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 | 2001-04-09 | Beth Apollo | 34069 | Al Miralles / Ken Lewchuk | Mary Nordstrom (consulting only) | Christy Lobusch will do deal test.
2001-11-19 | EEL | London - Credit, Debt, Structured Transactions | 5 | Al Miralles | Jitendra Patel | AA Deal Tester |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 | 2001-04-10 | Beth Apollo | 20799 | Al Miralles | Rudy Zipter (consulting only) | Using EAS deal testing
2001-11-12 | EGM | London - EGM | 5 | Mike Jordan, Lou Colarusso | [7 empty] | -18999 | Mike Jordan, Louis Colarusso | Bjorn Hagelmann (consulting only) | TBD depending on AA's work
2001-11-05 | EEL | London - Continental Power | 1 | Stacey White | [7 empty] | 242781 | Stacey White/Kristin Albrecht | Lloyd Fleming (consulting only) | Using EAS deal testing
2001-12-03 | EEL | European Natural Gas | 8 | Jeff Gossett |  | AA Deal Tester |  |  | discussed w/Jeff & Stacey on April 5 | 2001-04-27 | Beth Apollo | 62905 | Jeff Gossett | Lloyd Fleming (consulting only) | Using EAS deal testing
2001-12-03 | EGM | Houston - Global Liquids | 7 | Mike Jordan | Mary Nordstrom | AA Deal Tester |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 | 2001-04-10 | Beth Apollo | 93730 | Shona Wilson | Bjorn Hagelmann (consulting only) | Christy Lobusch will do deal test.
Late Nov or Dec. | EIM | Houston - EIM | 5 | TBD by James New |  | EAS - Ken Lewchuk |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 | 2001-05-04 | Beth Apollo | -6287 | Todd Hall | Bjorn Hagelmann (consulting only)
December | Corporate | EOTT* | 5 | Scott Earnest | Tom Moran | EAS - Terry Wheeler |  |  | Confirmed EAS with Mechelle/Shawn on 7/24 |  |  | 119703 | Scott Earnest | Bjorn Hagelmann | Christy Lobusch will do deal test.
Note on A23: Consider doing the remaining nordic offices (Stockholm, EES)
Note on A66: swilson5: 1st week in May is the golden week in Japan - no work
Note on V94: Consider doing the remaining nordic offices (Stockholm, EES)
Note on V135: swilson5: 1st week in May is the golden week in Japan - no work