## 6.5% - Swap (hidden)
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: February 23, 1999 | [17 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Draw_Sched___020800.xls'#$6.5% - Swap
Power Plants - 2000 | [19 empty] | 2025-09-26 22:53
| 1998 | 1999 | [11 empty] | 2000
| Total | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | Total | Person Responsible
Wilton Center IL
( Dev Owner: Scott Healy)
GE 7EA's (8ea) | 6800000 | 0 | 32884800 | 13650278 | 6825139 | 6825139 | 6825139 | 6825139 | 6825139 | 6825139 | 8531424 | 12790310 | 16869995 | 0 |  |  |  |  | 6825139 | 139302780 | Mike Miller
ABB | 0 |  |  |  | 670000 |  | 5360000 | 2680000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 |  |  |  |  | 13400000 | Mike Miller
EECC | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mike Miller
NEPCO | 0 | [7 empty] | 1642664 | 1558726 | 1558726 | 1558996 | 2620773 | 4676732 | 4676732 | 4676732 | 4676732 | 3176732 | 3176455 | 34000000 | Mike Miller
EI (Mobilization of O&M) | 0 | [12 empty] | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 750000 | Kevin Presto
PARTS | 0 | [15 empty] | 500000 | 500000 | 204000 | 1204000 | Mike Miller
LAND | 0 |  |  |  | 1668400 | 0 |  |  |  | 350000 | [9 empty] | 2018400 | Scott Healy
ENVIR PERMITTING | 0 |  |  | 100000 | 100000 | 100000 | 100000 | [12 empty] | 400000 | Scott Healy
GAS INTERCONNECT | 0 | [12 empty] | 1750000 | 500000 | 500000 | 500000 | 250000 |  | 3500000 | Chris Meyer
ELECT INTERCONNECT | 0 |  |  | 100000 | 100000 | [7 empty] | 1000000 | 850000 | 750000 | 600000 |  |  |  | 3400000 | Scott Healy
START UP FUEL | 0 | [15 empty] | 500000 | 500000 | 0 | 1000000 | Kevin Presto
SALES TAX | 0 | [12 empty] | 0 | 0 | 4500000 | 1500000 | 1500000 | 1500000 | 9000000 | Scott Healy
INSURANCE | 0 | [8 empty] | 150000 | [9 empty] | 150000 | Scott Healy
SALARIES | 0 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 200000 | Scott Healy
DEVELOPMENT | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 45000 | 300000 | Scott Healy
LEGAL | 0 | [5 empty] | 12500 | 5000 | 5000 | 5000 | 5000 | 5000 | 162500 | 5000 | 5000 | 5000 | 5000 | 5000 | 175000 | 400000 | Scott Healy
Total Plant | 6800000 | 26111.1111 | 32910911.1111 | 13876389.1111 | 9389650.1111 | 6951250.1111 | 12323750.1111 | 9536250.1111 | 9168914.1111 | 9584976.1111 | 10791261.1111 | 15050417.1111 | 21349379.1111 | 8102843.1111 | 6752843.1111 | 10432843.1111 | 7832843.1111 | 6082843.1111 | 12061705.1111 | 209025180
Cumulative Total Plant | 6800000 | 6826111.1111 | 39737022.2222 | 53613411.3333 | 63003061.4444 | 69954311.5556 | 82278061.6667 | 91814311.7778 | 100983225.8889 | 110568202 | 121359463.1111 | 136409880.2222 | 157759259.3333 | 165862102.4444 | 172614945.5556 | 183047788.6667 | 190880631.7778 | 196963474.8889 | 209025180
$$/Kw | [19 empty] | 348.3753
IDC | 187366 | 42500 | 38219.876 | 216694.3355 | 293031.8709 | 345479.7316 | 385003.6849 | 453842.768 | 507955.7711 | 560372.1496 | 623451.1193 | 685280.8106 | 770515.841 | 890331.9387 | 939044.9702 | 980709.364 | 1042532.7732 | 1090607.7259 | 1129463.9179 | 11182404.6484 | Rodney Malcolm
FINANCING FEE | 0 | [8 empty] | 1500000 | [9 empty] | 1500000 | Rodney Malcolm
CONTINGENCY (5%) | 0 | [17 empty] | 7970755.4 | 7970755.4 | Mike Miller
Subtotal | 187366 | 42500 | 38219.876 | 216694.3355 | 293031.8709 | 345479.7316 | 385003.6849 | 453842.768 | 507955.7711 | 2060372.1496 | 623451.1193 | 685280.8106 | 770515.841 | 890331.9387 | 939044.9702 | 980709.364 | 1042532.7732 | 1090607.7259 | 9100219.3179 | 20653160.0484
Cumulative subtotal | 187366 | 229866 | 268085.876 | 484780.2116 | 777812.0824 | 1123291.814 | 1508295.4989 | 1962138.2669 | 2470094.038 | 4530466.1876 | 5153917.307 | 5839198.1175 | 6609713.9586 | 7500045.8972 | 8439090.8674 | 9419800.2314 | 10462333.0046 | 11552940.7305 | 20653160.0484
Total Wilton Center | 6987366 | 68611.1111 | 32949130.9871 | 14093083.4466 | 9682681.982 | 7296729.8427 | 12708753.796 | 9990092.8791 | 9676869.8822 | 11645348.2607 | 11414712.2305 | 15735697.9217 | 22119894.9521 | 8993175.0498 | 7691888.0813 | 11413552.4751 | 8875375.8843 | 7173450.837 | 21161924.429 | 229678340.0484
Cumulative Total | 6987366 | 7055977.1111 | 40005108.0982 | 54098191.5449 | 63780873.5269 | 71077603.3696 | 83786357.1656 | 93776450.0447 | 103453319.9269 | 115098668.1876 | 126513380.4181 | 142249078.3398 | 164368973.2919 | 173362148.3417 | 181054036.423 | 192467588.898 | 201342964.7823 | 208516415.6194 | 229678340.0484
$$/Kw | [19 empty] | 382.7972
IDC 6.5% - Swap | 6.5%
| 600 | MW
DEBT RESERVE | 0 | [17 empty] | 7340000 | 7340000 | Rodney Malcolm
Total Current month less IDC | 6800000 | 26111.1111 | 32910911.1111 | 13876389.1111 | 9389650.1111 | 6951250.1111 | 12323750.1111 | 9536250.1111 | 9168914.1111 | 11084976.1111 | 10791261.1111 | 15050417.1111 | 21349379.1111 | 8102843.1111 | 6752843.1111 | 10432843.1111 | 7832843.1111 | 6082843.1111 | 20032460.5111 | 218495935.4
CALVERT CITY, KY
( Dev Owner: Ben Jacoby)
WH501FD (2 ea) | 11990800 | 29977000 | 2997700 | 2997700 | 2997700 | 2997700 | [8 empty] | 2997700 |  |  |  | 4531100 | 61487400 | Mike Miller
WH 501F (1 ea) | 17151750 | 0 | 12474000 | [15 empty] | 1559250 | 31185000 | Mike Miller
ABB | 0 |  |  |  | 440000 |  | 3520000 | 1760000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 |  |  |  |  | 8800000 | Mike Miller
NEPCO | 0 | [7 empty] | 600000 | 1000000 | 1000000 | 1000000 | 1500000 | 4206667 | 3866666.6667 | 3866666.6667 | 2986666.6667 | 2986666.6667 | 2986666.6667 | 26000000.3333 | Mike Miller
EI (Mobilization of O&M) | 0 | [12 empty] | 150000 | 150000 | 150000 | 150000 | 150000 |  | 750000 | Kevin Presto
PARTS | 0 | [15 empty] | 500000 | 500000 |  | 1000000 | Mike Miller
LAND | 0 | [7 empty] | 250000 | [10 empty] | 250000 | Ben Jacoby
ENVIR PERMITTING | 0 |  |  | 100000 | 100000 | 150000 | 150000 | [12 empty] | 500000 | Ben Jacoby
WATER LINE | 0 |  |  |  |  | 200000 | 200000 | [12 empty] | 400000 | Ben Jacoby
GAS INTERCONNECT | 0 | [11 empty] | 375000 | 125000 | 125000 | 125000 | 250000 |  |  | 1000000 | Chris Meyer
ELECT INTERCONNECT | 0 | [11 empty] | 200000 | 600000 | 600000 | 600000 |  |  |  | 2000000 | Ben Jacoby
START UP FUEL | [16 empty] | 500000 | 500000 |  | 1000000 | Kevin Presto
RESALE AND HANDLING FEE | [18 empty] | 256000 | 256000 | Patrick Maloy
SALES TAX | 0 | [11 empty] | 20000 |  |  | 30000 |  |  |  | 50000 | Ben Jacoby
INSURANCE | 0 | [8 empty] | 200000 | [9 empty] | 200000 | Ben Jacoby
SALARIES | 0 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 200000 | Ben Jacoby
DEVELOPMENT | 0 |  | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 |  |  |  | 400000 | Ben Jacoby
LEGAL | 0 | [5 empty] | 25000 | 10000 | 10000 | 10000 | 10000 | 10000 | 325000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 500000 | Ben Jacoby
Total Plant | 29142550 | 29988111.1111 | 15511382.5397 | 3137382.5397 | 3577382.5397 | 3387382.5397 | 3934682.5397 | 1809682.5397 | 1339682.5397 | 1689682.5397 | 1489682.5397 | 1489682.5397 | 2899682.5397 | 5571349.5397 | 8229049.2063 | 4821349.2063 | 4407777.7778 | 4157777.7778 | 9394127.7778 | 135978400.3333
Cumulative Total Plant | 29142550 | 59130661.1111 | 74642043.6508 | 77779426.1905 | 81356808.7302 | 84744191.2698 | 88678873.8095 | 90488556.3492 | 91828238.8889 | 93517921.4286 | 95007603.9683 | 96497286.5079 | 99396969.0476 | 104968318.5873 | 113197367.7937 | 118018717 | 122426494.7778 | 126584272.5556 | 135978400.3333
$$/Kw | [19 empty] | 283.2883
IDC | 184443 | 182141 | 322276.7444 | 408042.3988 | 427246.7839 | 448938.5261 | 469718.5985 | 493575.7713 | 506051.7538 | 516049.4813 | 536122.1964 | 547095.3054 | 558127.852 | 576857.6583 | 610160.4473 | 658039.4996 | 687719.5218 | 715320.1321 | 741716.0791 | 9589642.7501 | Rodney Malcolm
FINANCING FEE | 0 | [8 empty] | 1500000 | [9 empty] | 1500000 | Rodney Malcolm
CONTINGENCY (5%) | 0 | [17 empty] | 5379352.0267 | 5379352.0267 | Ben Jacoby
Subtotal | 184443 | 182141 | 322276.7444 | 408042.3988 | 427246.7839 | 448938.5261 | 469718.5985 | 493575.7713 | 506051.7538 | 2016049.4813 | 536122.1964 | 547095.3054 | 558127.852 | 576857.6583 | 610160.4473 | 658039.4996 | 687719.5218 | 715320.1321 | 6121068.1058 | 16468994.7768
Cumulative subtotal | 184443 | 366584 | 688860.7444 | 1096903.1432 | 1524149.927 | 1973088.4531 | 2442807.0516 | 2936382.8229 | 3442434.5768 | 5458484.0581 | 5994606.2544 | 6541701.5598 | 7099829.4119 | 7676687.0702 | 8286847.5175 | 8944887.0171 | 9632606.5388 | 10347926.671 | 16468994.7768
Total Calvert City | 29326993 | 30170252.1111 | 15833659.284 | 3545424.9385 | 4004629.3236 | 3836321.0657 | 4404401.1382 | 2303258.311 | 1845734.2935 | 3705732.021 | 2025804.7361 | 2036777.8451 | 3457810.3917 | 6148207.198 | 8839209.6537 | 5479388.706 | 5095497.2995 | 4873097.9099 | 15515195.8836 | 152447395.1101
Cumulative Total | 29326993 | 59497245.1111 | 75330904.3951 | 78876329.3336 | 82880958.6572 | 86717279.723 | 91121680.8611 | 93424939.1721 | 95270673.4657 | 98976405.4866 | 101002210.2227 | 103038988.0678 | 106496798.4595 | 112645005.6575 | 121484215.3111 | 126963604.0171 | 132059101.3166 | 136932199.2265 | 152447395.1101
317.5987
IDC 6.5% - Swap | 6.5%
$$/Kw | 480 | MW
DEBT RESERVE | 0 | [17 empty] | 6338000 | 6338000 | Rodney Malcolm
Total Current month less IDC | 29142550 | 29988111.1111 | 15511382.5397 | 3137382.5397 | 3577382.5397 | 3387382.5397 | 3934682.5397 | 1809682.5397 | 1339682.5397 | 3189682.5397 | 1489682.5397 | 1489682.5397 | 2899682.5397 | 5571349.5397 | 8229049.2063 | 4821349.2063 | 4407777.7778 | 4157777.7778 | 14773479.8044 | 142857752.36
WHEATLAND, INDIANA
( Dev Owner: Steve Dowd)
WH 501D5A (4) | 16673404 | 40778500 | 4077852 | 4077852 | 4077852 | 4077852 | 4077852 | [11 empty] | 4077852 | 81919016 | Mike Miller
ABB | 0 |  |  |  |  | 440000 | 3520000 | 1760000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 |  |  |  |  | 8800000 | Mike Miller
NEPCO | 0 | [7 empty] | 1600000 | 1440000 | 1440000 | 1440000 | 2400000 | 4426666.6667 | 4426666.6667 | 4426666.6667 | 4426666.6667 | 2986666.6667 | 2986666.6667 | 32000000 | Mike Miller
EI (Mobilization of O&M) | 0 | [12 empty] | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 750000 | Kevin Presto
PARTS | 0 | [15 empty] | 500000 | 500000 |  | 1000000 | Mike Miller
LAND | 0 | [7 empty] | 770000 | [10 empty] | 770000 | Steve Dowd
ENVIR PERMITTING | 0 |  |  | 112500 | 112500 | 112500 | 112500 | [12 empty] | 450000 | Steve Dowd
GAS INTERCONNECT | 0 | [13 empty] | 500000 | 166666.6667 | 166666.6667 | 166666.6667 |  | 1000000 | Chris Meyer
ELECT INTERCONNECT | 0 | [12 empty] | 1000000 | 500000 | 500000 |  |  |  | 2000000 | Steve Dowd
START UP FUEL | 0 | [15 empty] | 500000 | 500000 | 0 | 1000000 | Kevin Presto
RESALE HANDLING FEE | [18 empty] | 236000 | 236000 | Patrick Maloy
SALES TAX | 0 | [17 empty] | 50000 | 50000 | Steve Dowd
INSURANCE | 0 | [8 empty] | 200000 | [9 empty] | 200000 | Steve Dowd
SALARIES | 0 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 200000 | Steve Dowd
DEVELOPMENT | 0 |  | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 | 28571.4286 |  |  |  | 400000 | Steve Dowd
LEGAL | 0 | [10 empty] | 10000 | 290000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 400000 | Steve Dowd
Total Plant | 16673404 | 40789611.1111 | 4117534.5397 | 4230034.5397 | 4230034.5397 | 4670034.5397 | 7750034.5397 | 1799682.5397 | 2849682.5397 | 2119682.5397 | 1919682.5397 | 1929682.5397 | 3169682.5397 | 6041349.2063 | 6041349.2063 | 5268015.873 | 5739444.4444 | 4299444.4444 | 7536629.7778 | 131175016
Cumulative Total Plant | 16673404 | 57463015.1111 | 61580549.6508 | 65810584.1905 | 70040618.7302 | 74710653.2698 | 82460687.8095 | 84260370.3492 | 87110052.8889 | 89229735.4286 | 91149417.9683 | 93079100.5079 | 96248783.0476 | 102290132.254 | 108331481.4603 | 113599497.3333 | 119338941.7778 | 123638386.2222 | 131175016
$$/Kw | [19 empty] | 285.1631
IDC | 146354 | 104209 | 312615.2148 | 336611.8593 | 361347.8606 | 386217.8486 | 413605.8824 | 457825.6013 | 470053.7704 | 488035.6754 | 510285.8158 | 523448.1444 | 536735.9356 | 556812.369 | 592552.4108 | 628486.0446 | 660425.43 | 695091.3918 | 722145.1276 | 8902859.3823 | Rodney Malcolm
FINANCING FEE | 0 | [8 empty] | 1500000 | [9 empty] | 1500000 | Rodney Malcolm
CONTINGENCY (5%) | 0 | [17 empty] | 5535250.48 | 5535250.48 | Steve Dowd
Subtotal | 146354 | 104209 | 312615.2148 | 336611.8593 | 361347.8606 | 386217.8486 | 413605.8824 | 457825.6013 | 470053.7704 | 1988035.6754 | 510285.8158 | 523448.1444 | 536735.9356 | 556812.369 | 592552.4108 | 628486.0446 | 660425.43 | 695091.3918 | 6257395.6076 | 15938109.8623
Cumulative subtotal | 146354 | 250563 | 563178.2148 | 899790.074 | 1261137.9346 | 1647355.7832 | 2060961.6656 | 2518787.2669 | 2988841.0374 | 4976876.7128 | 5487162.5286 | 6010610.6729 | 6547346.6085 | 7104158.9774 | 7696711.3883 | 8325197.4329 | 8985622.8629 | 9680714.2547 | 15938109.8623
Total Calvert City | 16819758 | 40893820.1111 | 4430149.7545 | 4566646.399 | 4591382.4003 | 5056252.3883 | 8163640.4221 | 2257508.141 | 3319736.3101 | 4107718.2151 | 2429968.3554 | 2453130.684 | 3706418.4752 | 6598161.5753 | 6633901.6172 | 5896501.9176 | 6399869.8744 | 4994535.8362 | 13794025.3854 | 147113125.8623
Cumulative Total | 16819758 | 57713578.1111 | 62143727.8656 | 66710374.2645 | 71301756.6648 | 76358009.0531 | 84521649.4751 | 86779157.6161 | 90098893.9262 | 94206612.1414 | 96636580.4968 | 99089711.1808 | 102796129.6561 | 109394291.2314 | 116028192.8486 | 121924694.7662 | 128324564.6406 | 133319100.4769 | 147113125.8623
319.8111
IDC 6.5% - Swap | 6.5%
$$/Kw | 460 | MW
DEBT RESERVE | 0 | [17 empty] | 5842000 | 5842000 | Rodney Malcolm
Total Current month less IDC | 16673404 | 40789611.1111 | 4117534.5397 | 4230034.5397 | 4230034.5397 | 4670034.5397 | 7750034.5397 | 1799682.5397 | 2849682.5397 | 3619682.5397 | 1919682.5397 | 1929682.5397 | 3169682.5397 | 6041349.2063 | 6041349.2063 | 5268015.873 | 5739444.4444 | 4299444.4444 | 13071880.2578 | 138210266.48
Cumulative total w/o Debt reserve | 53134117 | 124266800.3333 | 177479740.3589 | 199684895.143 | 217963588.8489 | 234152892.1456 | 259429687.5019 | 273980546.833 | 288822887.3188 | 308281685.8156 | 324152171.1376 | 344377777.5884 | 373661901.4075 | 395401445.2306 | 418566444.5827 | 441355887.6813 | 461726630.7396 | 478767715.3228 | 529238861.0208
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19520000
Cumulative total with Debt reserve | 53134117 | 124266800.3333 | 177479740.3589 | 199684895.143 | 217963588.8489 | 234152892.1456 | 259429687.5019 | 273980546.833 | 288822887.3188 | 308281685.8156 | 324152171.1376 | 344377777.5884 | 373661901.4075 | 395401445.2306 | 418566444.5827 | 441355887.6813 | 461726630.7396 | 478767715.3228 | 548758861.0208

## Summary
Enron Capital & Trade Services
Business Analysis & Reporting
Capital Expenditures
Power Plants - 2000
| 1998 | 1999 | [11 empty] | 2000
| Total | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | Total
Capital
WILTON CENTER, IL | 7140000 | 1296410 | 33024184 | 225882.6 | 1752232.9 | 18800373.5 | 8037788.4025 | 8808343.9621 | 6987028.9287 | 7789242.489 | 11600775.8309 | 17679921.6272 | 39310183.4086 | 2943898.9492 | 28783032.3018 | 18405069.9602 | 16253451.8963 | 9190124.6903 | 16367253.464 | 254395198.9108
Gleason | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93174572.05 | 706459.93 | 2178270.256 | 7520808.7566 | 2620724.5786 | 8277786.4303 | 12213686.0401 | 10343236.5211 | 10448521.1716 | 8288235.3697 | 22652869.2065 | 175924879.3105
WHEATLAND, IN | 17087218 | 43641491 | 4681548 | 362603.6 | 4745094.59 | 9091692.23 | 497761.1286 | 1048367.4821 | 1496281.6764 | 1780115.93 | 1566383.4088 | 5481999.341 | 4425759.3 | 8750380.6584 | 12414298.4198 | 10676468.4579 | 8601675.1491 | 8114938.0638 | 16313264.2336 | 161954211.3969
TOTAL 2000 PLANTS | 24227218 | 44937901 | 37705732 | 588486.2 | 6497327.49 | 27892065.73 | 8535549.5311 | 9856711.4442 | 101657882.6551 | 10275818.349 | 15345429.4957 | 30682729.7247 | 46356667.2872 | 19972066.038 | 53411016.7617 | 39424774.9392 | 35303648.217 | 25593298.1238 | 55333386.9041 | 592274289.6182
Cumulative Total | 24227218 | 69165119 | 106870851 | 107459337.2 | 113956664.69 | 141848730.42 | 150384279.9511 | 160240991.3953 | 261898874.0505 | 272174692.3995 | 287520121.8952 | 318202851.62 | 364559518.9072 | 384531584.9452 | 437942601.7069 | 477367376.6461 | 512671024.8631 | 538264322.9869 | 593597709.891

## Calvert City (hidden)
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: Actuals through December 24, 1999 | [19 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Draw_Sched___020800.xls'#$Calvert City
Power Plants - 2000 | [21 empty] | 2025-09-26 22:53
| 1998 | 1999 | [8 empty] | Gleason | Expense |  |  |  | 2000
| Total | January | February | March | April | May | June | July | August | September | Transfer | Transfer | October | November | December | January | February | March | April | May | June | Total | Person Responsible
Capital
CALVERT CITY, KY
( Dev Owner: Ben Jacoby)
WH501FD (2 ea) | 12224800 | 31276400 | 3107550 |  | 3107250 | 6240218.71 |  | 107199 | 393211 |  | -56456629 | [10 empty] | -0.29 | Mike Miller
WH 501F (1 ea) | 17151750 | 12474000 | 0 | [5 empty] | 0 |  | -29625750 | [10 empty] | 0 | Mike Miller | -0.29
ABB | 0 | [6 empty] | 293461 | 883701.65 |  | -1177162 | [10 empty] | 0.65 | Mike Miller | 5885811
Overheads and Fees -EECC | [7 empty] | 77483.3333 | 77483.3333 | 77483.3333 | -232450 | [10 empty] | 0 | Mike Miller | 929800
Overheads and Fees -NEPCO | [7 empty] | 236725 | 236725 | 236725 | -710175 | [10 empty] | 0 | Mike Miller | 2840700
BASE FEE | [21 empty] | 0 | Mike Miller | 3066700
NEPCO-Reimbursables | 0 | [7 empty] | 0 | [12 empty] | 0 | Mike Miller | 41741400
SWITCHYARD | [21 empty] | 0 | Mike Miller | 9230000
Union Adders/Others | [21 empty] | 0 | Mike Miller | 2125800
EI (Mobilization of O&M) | 0 | [20 empty] | 0 | Kevin Presto | 908786
PARTS | 0 | [20 empty] | 0 | Mike Miller | 1247007
LAND | 0 | [5 empty] | 6000 | 0 | 0 | 369040.52 | -369041 | -6000 | [9 empty] | -0.48 | Ben Jacoby | 453841
ENVIR PERMITTING | 0 |  |  |  | 0 | 239729 | 46480 | 62682 | 7969 | 9500 | -69419 | -296941 | [9 empty] | 0 | Ben Jacoby
GAS INTERCONNECT | 0 | [20 empty] | 0 | Chris Meyer | 750000
WATER INTERCONNECT | [21 empty] | 0 |  | 700000
Power INTERCONNECT | [21 empty] | 0 |  | 2200000
START UP FUEL | [21 empty] | 0 | Kevin Presto | 1000000
RESALE AND HANDLING FEE | [21 empty] | 0 | Patrick Maloy | 256000
SALES TAX | 0 | [20 empty] | 0 | Patrick Maloy | 1750000
INSURANCE | 0 | [20 empty] | 0 | Patrick Maloy | 200000
SALARIES | 0 | 0 | 0 |  | 4235 | 20999 | 10759.47 | 6023 | 6146 | 0 | -33713 | -14448.6 | [9 empty] | 0.87 | Patrick Maloy
DEVELOPMENT | 0 |  |  |  | 1154 | 17366 | 11430 | 17413.59 | 43023 | 33474 | -129040 | 5179 | [9 empty] | -0.41 | Patrick Maloy
LEGAL | 0 |  |  |  |  | 55406.15 | 16078 | 32697.52 | 0 | 0 | -14302 | -89879.78 | [9 empty] | -0.11 | Patrick Maloy
Total Plant | 29376550 | 43750400 | 3107550 | 0 | 3112639 | 6573718.86 | 90747.47 | 833684.4433 | 1648258.9833 | 726222.8533 | -88817681 | -402090.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23
Cumulative Total Plant | 29376550 | 73126950 | 76234500 | 76234500 | 79347139 | 85920857.86 | 86011605.33 | 86845289.7733 | 88493548.7567 | 89219771.61 | -324132.2433 | -726222.6233 | 89219771.61 | 89219771.61 | 89219771.61 | 89219771.61 | 89219771.61 | 89219771.61 | 89219771.61 | 89219771.61 | 89219771.61
$$/Kw | [21 empty] | 4.5098e-07
Interest SWAP |  |  |  | -21556.4 | 66478.91 | -51000 | [15 empty] | -6077.49 | Rodney Malcolm
IDC | 704264 | 320324 | 477081 | 425796 | 378280 | 557261 | 481371.225 | 488494.4432 | 500068.5242 | 0 | -4326862.7024 | 0 | [9 empty] | 6077.49 | Rodney Malcolm
Commitment Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | Rodney Malcolm
FINANCING FEE | 0 | [20 empty] | 0 | Rodney Malcolm
CONTINGENCY (5% NEPCO; 3% Ttl Plant) | 0 | [19 empty] | 0 | 0 | Ben Jacoby
Subtotal | 704264 | 320324 | 477081 | 404239.6 | 444758.91 | 506261 | 481371.225 | 488494.4432 | 500068.5242 | 0 | -4326862.7024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative subtotal | 704264 | 1024588 | 1501669 | 1905908.6 | 2350667.51 | 2856928.51 | 3338299.735 | 3826794.1781 | 4326862.7024 | 4326862.7024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Calvert City | 30080814 | 44070724 | 3584631 | 404239.6 | 3557397.91 | 7079979.86 | 572118.695 | 1322178.8865 | 2148327.5076 | 726222.8533 | -93144543.7024 | -402090.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23
Cumulative Total | 30080814 | 74151538 | 77736169 | 78140408.6 | 81697806.51 | 88777786.37 | 89349905.065 | 90672083.9515 | 92820411.459 | 93546634.3124 | 402090.61 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23
4.5098e-07
IDC 6.5% | 6.5%
+ 35 Bps Com Fee | 0.35% | 174500000
$$/Kw | 510 | MW
DEBT RESERVE | 0 | [19 empty] | 0 | 0 | Rodney Malcolm
Total Current month less IDC | 29376550 | 43750400 | 3107550 | -21556.4 | 3179117.91 | 6522718.86 | 90747.47 | 833684.4433 | 1648258.9833 | 726222.8533 | -88817681 | -402090.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6077.26
Expense
CALVERT CITY, KY
ENVIR PERMITTING | 0 | 500 | 43071 | 32361 | 6649 | 0 | 0 | 0 | 0 | 0 |  | 296941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379522 | Patrick Maloy | 379522 | #REF!
DEVELOPMENT | 0 | 135 | 34605 | 7328 | 1627 | 0 | 83611.75 | 48014.21 | 0 | 0 |  | 11179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186499.96 | Patrick Maloy | 186499.55 | #REF!
SALARIES | 0 | 0 | 21984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14448.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36432.6 | Patrick Maloy | 36433.47 | #REF!
LEGAL | 0 |  | 0 | 9963 | 76235 | 5510.85 | 10271.2 | 16720.48 | 0 | 0 |  | 89879.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208580.31 | Patrick Maloy | 208580.2 | #REF!
Subtotal Calvert City Expense | 0 | 635 | 99660 | 49652 | 84511 | 5510.85 | 93882.95 | 64734.69 | 0 | 0 | 0 | 412448.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 811034.87
Current FIT |  |  |  |  | -82061 | -1928 | -32859 | -22657 | [13 empty] | -139505
Total Income Statement | 0 | 635 | 99660 | 49652 | 2450 | 3582.85 | 61023.95 | 42077.69 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671529.87
-241341.1933

## Wilton
Enron Capital & Trade Services | [24 empty] | 0
Business Analysis & Reporting |  |  | Last updated: Actuals through December 24, 1999 | [20 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Draw_Sched___020800.xls'#$Wilton
Power Plants - 2000 | [23 empty] | 2025-09-26 22:53
|  | 1998 | 1999 | [11 empty] | 2000
|  | Total | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | Total | Person Responsible
Capital
Wilton Center IL
( Dev Owner: Scott Healy) |  |  |  | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 76.25% | 85.62% | 95% | [5 empty] | 100%
GE 7EA's (8ea) | 140040940 | 6800000 | 0 | 32884800 | 0 | 0 | 18310527 | 6800000 | 5225143 | 6152847 | 6924847 | 6924847 | 6924847 | 24688143.75 |  | 13325691 | 0 |  |  | 7103247 |  |  |  | 142064939.75 | Mike Miller | 142064940 | -0.25
ABB |  | 0 | 1250000 | 60%: -74270.4; 65%: 7480; 76.25%: 1774814.4; 95%: 1774814 | 591604.8 | 591604.8 | [7 empty] | 5916047.6 | Mike Miller | 5916048 | -0.4
SOUND - Braden |  |  |  | 55%: 815280; 60%: 2025876; 65%: 0; 76.25%: 1894103.8 |  | 1183814.88 | 1775722.31 | 1302196.36 |  | 482525.95 |  |  |  | 9479519.3 | Mike Miller | 9479519 | 0.3
Overheads and Fees -EECC |  | 0 |  | 60%: 77933.3333; 65%: 77933.3333; 70%: 77933.3333; 76.25%: 77933.33; 85.62%: 82933.3333; 95%: 77933.3333 | 77933.3333 | 77933.3333 | 77933.3333 | 77933.3333 | 77933.3333 | 77933.3333 |  |  |  | 940199.9967 | Mike Miller | 940200 | -0.0033333
Overheads and Fees -NEPCO |  |  |  | 60%: 235400; 65%: 235400; 70%: 235400; 76.25%: 235399; 85.62%: 235400; 95%: 235398 | 235399 | 235400 | 235400 | 235400 | 235400 | 235403 |  |  |  | 2824799 | Mike Miller | 2824800 | -1
BASE FEE | [19 empty] | 3066700 |  |  |  | 3066700 | Mike Miller | 3066700 | 0
NEPCO- General Provisions |  | 0 |  | 65%: 0; 76.25%: 0; 85.62%: 862088; 95%: 636689 | 1727562 | 2134700 | 2351106 | 2233236 | 1746094 | 2655434 |  |  |  | 14346909 | Mike Miller | 14346909 | 0
NEPCO - BOP Procurement |  |  |  | 85.62%: 3301; 95%: 346618 | 1451621 | 1032590 | 1862702 | 1954057 | 231962 | 466327 |  |  |  | 7349178 | Mike Miller | 7349178 | 0
NEPCO - Construction |  |  |  | 85.62%: 0; 95%: 2569929 | 4657660 | 4537347 | 7381251 | 6849670 | 3000000 | 5327329 |  | 0 |  | 34323186 | Mike Miller | 34323186 | 0
NEPCO - Switchyard |  |  |  | 76.25%: 0; 85.62%: 0; 95%: 28388 | 763285 | 1827096 | 1327137 | 490869 | 136699 | 763285 |  |  |  | 5336759 | Mike Miller | 5336759 | 0
NEPCO - Reimburse Tax |  |  |  | 85.62%: 0 | [5 empty] | 500000 |  |  |  | 500000 | Mike Miller | 500000 | 0
NEPCO - MISC |  |  |  | 95%: 41531 |  |  |  | -785782 |  | 744251 |  | 0 |  | 0 |  | -744251 | 744251
NEPCO % Complete |  |  |  | 85.62%: 8573073; 95%: 7093919 | -7855877 |  |  |  |  | -7811115 |  |  |  | 0 | Mike Miller |  | 0
EI (Mobilization of O&M) |  | 0 | [12 empty] | 0 | 250000 | 125000 | 125000 | 125000 | 283786 |  |  |  | 908786 | Kevin Presto | 908786 | 0
PARTS |  | 0 | [15 empty] | 500000 | 500000 | 253881 |  |  |  | 1253881 | Mike Miller | 1253881 | 0
LAND |  | 0 |  |  | 20000 | 1446361 | 8500 |  | 821965 | 0 |  | 1000 | 7992 |  | 180000 | [8 empty] | 2485818 | Scott Healy | 2485818.14 | -0.14
ENVIR PERMITTING |  | 0 |  | 0 | 0 |  | 71081 | 13262 | 24704.06 | 9361.22 | 11746.18 | 19878 | 29832 | 39860 | 5434 | 51338 | 73458 |  |  | 0 |  |  |  | 349954.46 | Scott Healy
WATER INTERCONNECT |  |  |  | 95%: 216382 | 2174 | [8 empty] | 218556 |  | 218555.81 | 0.19
POWER INTERCONNECT |  | 0 |  | 76.25%: 50050; 85.62%: 160616; 95%: 8228 | 115500 | 665606 | 200000 | [6 empty] | 1200000 | Chris Meyer | 1200000 | 0
GAS INTERCONNECT |  | 0 |  | 95%: 0 | 0 | 1750000 | 1750000 | 1500000 | 1250000 | 250000 |  |  |  | 6500000 | Chris Meyer | 6500000 | 0
START UP FUEL |  | 0 | [15 empty] | 500000 | 500000 | 500000 |  |  |  | 1500000 | Kevin Presto | 1500000 | 0
INSURANCE |  | 0 |  | 76.25%: 0; 85.62%: 0; 95%: 266248.5 | [9 empty] | 266248.5 | Scott Healy | 266248.5 | 0
SALARIES |  | 0 | 0 | 0 | 0 | 7949 | 29402 | 13770.85 | 7746 | 6276 | 6591.41 | 0 | 0 | 0 | 0 | 13333.3333 | 13333.3333 | 19608 | 5588 | 53798 |  |  |  | 177395.9267 | Scott Healy
DEVELOPMENT |  | 0 | 0 | 0 | 0 | 0 | 11792 | 16860 | 16353.6 | 33741 | 26999.88 | 47825 | 131162 | 154225 | 51069 | 40869 | 31732 |  |  | 28374 |  |  |  | 591002.48 | Scott Healy
LEGAL |  | 0 | 0 | 0 | 0 | 0 | 604.5 | 0 | 21423 | 0 | 75 | 6749 | 4455 | 258057.5 | 49464 | 19571 | 55000 | 18404 | 99076.5 | 15544 |  |  |  | 548423.5 | Scott Healy | 0
Total Plant |  | 6800000 | 1250000 | 32884800 | 20000 | 1454310 | 18431906.5 | 7659172.85 | 8382273.5933 | 6523038.5533 | 7283592.8033 | 11032599.53 | 17015699.3333 | 38436364.0833 | 2052829.1333 | 27736894.3467 | 17259774.9767 | 15020591.6933 | 7907752.8333 | 14996703.2833 | 0 | 0 | 0 | 242148303.5133
Cumulative Total Plant |  | 6800000 | 8050000 | 40934800 | 40954800 | 42409110 | 60841016.5 | 68500189.35 | 76882462.9433 | 83405501.4967 | 90689094.3 | 101721693.83 | 118737393.1633 | 157173757.2467 | 159226586.38 | 186963480.7267 | 204223255.7033 | 219243847.3967 | 227151600.23 | 242148303.5133 | 242148303.5133 | 242148303.5133 | 242148303.5133
$$/Kw | [23 empty] | 398.2702
Interest SWAP |  |  |  | 40%: -21556.4; 45%: 66478.9; 50%: -51000 | [9 empty] | -6077.5 | Rodney Malcolm
IDC |  | 340000 | 46410 | 139384 | 227439 | 231444 | 419367 | 378615.5525 | 426070.3687 | 463711.3754 | 505639.6857 | 568176.3009 | 663422.2939 | 873819.3253 | 891069.8159 | 1046137.9551 | 1145294.9835 | 1232860.203 | 1282371.8569 | 1370550.1806 |  |  |  | 12251783.8975 | 0
Commitment Fee |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Franchise Tax |  | 0 |  | 50%: 100; 65%: 279; 70%: 10; 76.25%: 0; 85.62%: 800 | [9 empty] | 1189
CONTINGENCY (5% NEPCO; 3% Ttl Plant) |  | 0 | [17 empty] | 0 |  |  |  | 0 | Mike Miller
Subtotal |  | 340000 | 46410 | 139384 | 205882.6 | 297922.9 | 368467 | 378615.5525 | 426070.3687 | 463990.3754 | 505649.6857 | 568176.3009 | 664222.2939 | 873819.3253 | 891069.8159 | 1046137.9551 | 1145294.9835 | 1232860.203 | 1282371.8569 | 1370550.1806 | 0 | 0 | 0 | 12246895.3975
Cumulative subtotal |  | 340000 | 386410 | 525794 | 731676.6 | 1029599.5 | 1398066.5 | 1776682.0525 | 2202752.4212 | 2666742.7966 | 3172392.4823 | 3740568.7832 | 4404791.0771 | 5278610.4024 | 6169680.2183 | 7215818.1734 | 8361113.1569 | 9593973.3599 | 10876345.2168 | 12246895.3975 | 12246895.3975 | 12246895.3975 | 12246895.3975
Total Wilton Center Capital |  | 7140000 | 1296410 | 33024184 | 225882.6 | 1752232.9 | 18800373.5 | 8037788.4025 | 8808343.9621 | 6987028.9287 | 7789242.489 | 11600775.8309 | 17679921.6272 | 39310183.4086 | 2943898.9492 | 28783032.3018 | 18405069.9602 | 16253451.8963 | 9190124.6903 | 16367253.464 | 0 | 0 | 0 | 254395198.9108
Cumulative Total |  | 7140000 | 8436410 | 41460594 | 41686476.6 | 43438709.5 | 62239083 | 70276871.4025 | 79085215.3646 | 86072244.2933 | 93861486.7823 | 105462262.6132 | 123142184.2404 | 162452367.649 | 165396266.5983 | 194179298.9001 | 212584368.8602 | 228837820.7566 | 238027945.4468 | 254395198.9108 | 254395198.9108 | 254395198.9108 | 254395198.9108
$$/Kw | [23 empty] | 418.4132
IDC 6.5% |  | 6.5%
+ 35 Bps Com Fee |  | 0.35% | 245672000
|  | 608 | MW
DEBT RESERVE |  | 0 | [17 empty] | 0 |  |  |  | 0 | 0
Total Current month less IDC |  | 6800000 | 1250000 | 32884800 | -1556.4 | 1520788.9 | 18381006.5 | 7659172.85 | 8382273.5933 | 6523317.5533 | 7283602.8033 | 11032599.53 | 17016499.3333 | 38436364.0833 | 2052829.1333 | 27736894.3467 | 17259774.9767 | 15020591.6933 | 7907752.8333 | 14996703.2833 | 0 | 0 | 0 | 242143415.0133
Expense | [26 empty] | total project
Wilton Center IL | [26 empty] | weekly Report
ENVIR PERMITTING |  | 0 | 0 | 0 | 8000 | 24712 | 0 | 0 | 14873.37 | 2460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50045.37 | Scott Healy | 399999.83 | 400000 | 0.17
DEVELOPMENT |  | 0 | 1236 | 56504 | 26820 | 11551 | 0 | 199867.23 | 48014.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 343992.42 | Scott Healy | 934994.9 | 934994.48 | -0.42
SALARIES |  | 0 | 0 | 22604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 22604 | Scott Healy | 199999.9267 | 200000 | 0.073333
LEGAL |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10000 | Scott Healy | 558423.5 | 558423.13 | -0.37
Subtotal Wilton Center Expense |  | 0 | 1236 | 79108 | 44820 | 36263 | 0 | 199867.23 | 62887.56 | 2460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426641.79
Current FIT | [5 empty] | -56500 | -34 | -69954 | -22011 | -959 | -3 | 52217 | -52497 | [10 empty] | -149741
Total Income Statement |  | 0 | 1236 | 79108 | 44820 | -20237 | -34 | 129913.23 | 40876.56 | 1501 | -3 | 52217 | -52497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276900.79
Plano, IL
SALARIES |  |  |  | 35%: 19729; 40%: 0; 50%: 12698.23; 60%: 5725; 95%: 1242.3 | [9 empty] | 39394.53 | Scott Healy
DEVELOPMENT |  |  | 1343 | 35%: 28915.95; 40%: 19328.69; 45%: 568; 50%: 68419; 70%: 591.45 | [9 empty] | 119166.09 | Scott Healy
LEGAL |  | 52133 |  | 45%: 1331 | [9 empty] | 53464 | Scott Healy
LAND |  | 87500 | [21 empty] | 87500
Subtotal Plano Expense |  | 139633 | 1343 | 48644.95 | 19328.69 | 1899 | 81117.23 | 0 | 5725 | 0 | 591.45 | 0 | 0 | 1242.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299524.62
Total Project Cost (w/o Debt Reserve) |  | 7279633 | 1298989 | 33151936.95 | 290031.29 | 1733894.9 | 18881456.73 | 8167701.6325 | 8854945.5221 | 6988529.9287 | 7789830.939 | 11652992.8309 | 17627424.6272 | 39311425.7086 | 2943898.9492 | 28783032.3018 | 18405069.9602 | 16253451.8963 | 9190124.6903 | 16367253.464 | 0 | 0 | 0 | 254971624.3208
-0.41667
Note on Y10: Shelly May: Contract still not final; $136,000,000 is the contract price per draft on 3/16/99 Amy - 05/21 Contract executed, contract price has changed to $140,040,940

## Gleason
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: Actuals through December 24, 1999 | [21 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Draw_Sched___020800.xls'#$Gleason
Power Plants - 2000 | [23 empty] | 2025-09-26 22:53
| 1998 | 1999 | [12 empty] | 2000
| Total | January | February | March | April | May | June | July | August | Transfer | September | October | November | December | January | February | March | April | May | June | July | August | September | Total | Person Responsible
Capital
Gleason
( Dev Owner: Ben Jacoby)
WH501FD (2 ea) | [9 empty] | 56456629 |  | 1282310 | 144155 | 0 | 0 | 1160414 |  |  | 11 | 1799221 |  |  |  | 60842740 | Mike Miller
WH 501F (1 ea) | [9 empty] | 29625750 | [7 empty] | 142790 | 1645716 | 3304048 |  |  |  | 34718304 | Mike Miller | 95561044 | 0
ABB | [9 empty] | 1177162 |  | 0 | 58500 | 1773743.3 | 1896543.3 | 645575.4 | 473086.8 | 0 |  | 0 |  |  |  | 6024610.8 | Mike Miller | 6024611 | -0.2
Overheads and Fees -EECC | [9 empty] | 232450 | 0 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 |  |  |  | 929800 | Mike Miller | 929800 | 0
Overheads and Fees -NEPCO | [9 empty] | 710172 | 0 | 236722 | 236722 | 236725 | 236722 | 236725 | 236725 | 236725 | 236725 | 236737 |  |  |  | 2840700 | Mike Miller | 2840700 | 0
BASE FEE | [19 empty] | 3066700 |  |  |  | 3066700 | Mike Miller | 3066700 | 0
NEPCO- General Provisions | [12 empty] | 420818 |  | 1769159 | 3131172.0286 | 2901392.7012 | 2294363.7318 | 1409541.8442 | 3155663.2636 | 2065600 |  |  | 17147710.5694 |  | 17147711 | -0.4306
NEPCO - BOP Procurement | [12 empty] | 84021 |  | 225269 | 778046.0006 | 720949.5252 | 570112.5678 | 350248.5282 | 998469.9356 | 533814 |  |  | 4260930.5574 |  | 4260931 | -0.4426
NEPCO - Construction | [12 empty] | 204588 |  | 2792896 | 2820028.3848 | 2613082.1616 | 2066373.4824 | 1269476.0856 | 1642549.3648 | 2034755 |  |  | 15443748.4792 |  | 15443748 | 0.4792
NEPCO - Switchyard | [11 empty] | 0 | 0 |  | 848349 | 2216176.941 | 2053544.022 | 1623901.833 | 997643.727 | 2637335.666 | 1759834 |  |  | 12136785.189 | Mike Miller | 12136785 | 0.189
NEPCO - Reimburse Tax | [19 empty] | 675000 |  |  |  | 675000 | Mike Miller | 675000 | 0
NEPCO % Complete | [12 empty] | 5344605 |  | -340467 |  |  |  |  | 591222 | -8983121 |  |  | -3387761 | Mike Miller | 0 | -3387761
EI (Mobilization of O&M) | [15 empty] | 225000 | 225000 | 150000 | 150000 | 158786 |  |  |  | 908786 | Kevin Presto | 908786 | 0
PARTS | [17 empty] | 500000 | 500000 | 247007 |  |  |  | 1247007 | Mike Miller | 1247007 | 0
1/2 of Redesign costs to change projects | [13 empty] | -250000 | [9 empty] | -250000
LAND | [9 empty] | 369041 |  | 0 |  |  | 14500 | [8 empty] | 383541 | Ben Jacoby | 383541 | 0
ENVIR PERMITTING | [9 empty] | 69419 | 190571 | 0 | 264856 | 0 | 38192 | 0 | 0 | 0 | [5 empty] | 563038 | Ben Jacoby
GAS INTERCONNECT | [14 empty] | 20486 | 125000 | 125000 | 350000 | 375000 | 104514 |  |  |  | 1100000 | Chris Meyer | 1100000 | 0
Power INTERCONNECT | [11 empty] | 18018 |  | 7500 |  | 25518 |  | 1500000 |  | 2339081 |  |  |  | 3890117 |  | 3890117 | 0
START UP FUEL | [17 empty] | 0 | 250000 | 250000 |  |  |  | 500000 | Kevin Presto | 500000 | 0
RESALE AND HANDLING FEE | [19 empty] | 0 |  |  |  | 0 | Patrick Maloy | 0 | 0
INSURANCE | [11 empty] | 0 | 0 | 200935 | [9 empty] | 200935 |  | 200935.25 | -0.25
SALARIES | [9 empty] | 55021.05 | 0 | 0 | 0 | 0 | 1755 | 23870.1111 | 11111.1111 | 11111.1111 | 31111 | 32312 | 20529 |  |  | 186820.3833
DEVELOPMENT | [9 empty] | 137763 | 2411 | 18874 | 113219 | 0 | 80147 | 58997 | 35000 | 35000 | 35000 | 127171 |  |  |  | 643582
LEGAL | [9 empty] | 14302 | 13886 | 27415 | 13908 | 0 | 0 | 7127 | 132585 | 96092 | 121058 | 253994 | 68298 |  |  | 748665
Total Plant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88847709.05 | 206868 | 1660822.3333 | 6962875.3333 | 2046386.6333 | 7661034.6333 | 11531133.1994 | 9604959.6544 | 9653953.0594 | 7449014.5183 | 21697294.5633 | -2500291 | 0 | 0 | 164821759.9783
Cumulative Total Plant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88847709.05 | 89054577.05 | 90715399.3833 | 97678274.7167 | 99724661.35 | 107385695.9833 | 118916829.1828 | 128521788.8372 | 138175741.8967 | 145624756.415 | 167322050.9783 | 164821759.9783 | 164821759.9783 | 164821759.9783
$$/Kw | [23 empty] | 323.1799
Interest SWAP | [10 empty] | -6077 | [12 empty] | -6077 | Rodney Malcolm
IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326863 | 505668.93 | 517447.9227 | 557933.4232 | 574337.9453 | 616751.7969 | 682552.8407 | 738276.8667 | 794568.1121 | 839220.8514 | 955574.6432 |  |  |  | 11109196.3322 | Rodney Malcolm
Commitment Fee | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | Rodney Malcolm
FINANCING FEE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | Rodney Malcolm
CONTINGENCY (5% NEPCO; 3% Ttl Plant) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 |  |  |  | 0 | Ben Jacoby
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326863 | 499591.93 | 517447.9227 | 557933.4232 | 574337.9453 | 616751.7969 | 682552.8407 | 738276.8667 | 794568.1121 | 839220.8514 | 955574.6432 | 0 | 0 | 0 | 11103119.3322
Cumulative subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326863 | 4826454.93 | 5343902.8527 | 5901836.2759 | 6476174.2212 | 7092926.0181 | 7775478.8588 | 8513755.7255 | 9308323.8376 | 10147544.689 | 11103119.3322 | 11103119.3322 | 11103119.3322 | 11103119.3322
Total Calvert City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93174572.05 | 706459.93 | 2178270.256 | 7520808.7566 | 2620724.5786 | 8277786.4303 | 12213686.0401 | 10343236.5211 | 10448521.1716 | 8288235.3697 | 22652869.2065 | -2500291 | 0 | 0 | 175924879.3105
Cumulative Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93174572.05 | 93881031.98 | 96059302.236 | 103580110.9926 | 106200835.5712 | 114478622.0015 | 126692308.0416 | 137035544.5627 | 147484065.7343 | 155772301.104 | 178425170.3105 | 175924879.3105 | 175924879.3105 | 175924879.3105
344.9507
IDC 6.5% | 6.5%
+ 35 Bps Com Fee | 0.35% | 174500000
$$/Kw | 510 | MW
DEBT RESERVE | 0 | [18 empty] | 0 | 0 |  |  | 0 | Rodney Malcolm
Total Current month less IDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200791 | 1660822.3333 | 6962875.3333 | 2046386.6333 | 7661034.6333 | 11531133.1994 | 9604959.6544 | 9653953.0594 | 7449014.5183 | 21697294.5633 | -2500291 | 0 | 0 | 75967973.9283
Expense
Gleason/Weakly County, TN
ENVIRONMENTAL PERMITTING | [5 empty] | 183926.18 | 0 | 2645 | 0 | -194774.18 | 8203 |  |  |  | 0 | [8 empty] | 0 | ENVIRONMENTAL PERMITTING |  | 563038 | 563038.4 | -0.4
LEGAL EXPENSES |  |  | 0 | 3543 |  | 2193 | 0 |  | 0 | -2193 | [13 empty] | 3543 | LEGAL EXPENSES |  | 752208 | 752208.46 | -0.46
SYSTEM IMPACT STUDY |  | 0 |  |  |  |  | 0 |  | 0 | 0 | [13 empty] | 0 | SYSTEM IMPACT STUDY |  | 0 | 0 | 0
DEVELOPMENT EXPENSES | 0 | 0 | 5000 | 904 | 7490.5 | 2410.51 | 0 |  |  | -9901.01 | [13 empty] | 5904 | DEVELOPMENT EXPENSES |  | 649486 | 649485.77 | 0.23
SALARIES |  |  |  | 11817 | 1079 | 1772.57 | 0 |  | 0 | -1488.76 | [13 empty] | 13179.81 | SALARIES |  | 200000.1933 | 200000 | 0.19333
Subtotal Gleason Expense | 0 | 0 | 5000 | 16264 | 8569.5 | 190302.26 | 0 | 2645 | 0 | -208356.95 | 8203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22626.81
Current FIT |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -2135 | [9 empty] | -2135
Total Income Statement | 0 | 0 | 5000 | 16264 | 8569.5 | 190302.26 | 0 | 2645 | 0 | -208356.95 | 8203 | 0 | 0 | -2135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20491.81
Total Project Cost | 0 | 0 | 5000 | 16264 | 8569.5 | 190302.26 | 0 | 2645 | 0 | 92966215.1 | 714662.93 | 2178270.256 | 7520808.7566 | 2618589.5786 | 8277786.4303 | 12213686.0401 | 10343236.5211 | 10448521.1716 | 8288235.3697 | 22652869.2065 | -2500291 | 0 | 0 | 175945371.1205
-0.65167

## Wheatland
Enron Capital & Trade Services
Business Analysis & Reporting |  | Last updated: Actuals through December 24, 1999 | [20 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/Draw_Sched___020800.xls'#$Wheatland
Power Plants - 2000 | [22 empty] | 2025-09-26 22:53
| 1998 | 1999 | [11 empty] | 2000
| Total | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | Total | Person Responsible
Capital
WHEATLAND, INDIANA
( Dev Owner: Steve Dowd)
WH 501D5A (4) | 16673400 | 43401650 | 4291075 |  | 4291075 | 8617667.23 | 0 |  | 318421 |  | 0 | 39600 | 1077741.26 | 1077741 | 1172769 |  |  | 231601 | 5026561 |  |  |  | 86219301.49 | Mike Miller | 86219301 | 0.49
ABB | 0 | [6 empty] | 259883 | 350000 | 935 | 655033.1 |  | 1190506.2 | 1190506 |  | 793670.8 | 0 | [5 empty] | 4440534.1 | Mike Miller | 4440534 | 0.1
NEPCO- General Provisions | 0 | [7 empty] | 0 |  | 0 | 626946 |  | 2169322 | 2727672.8384 | 2515948.233 | 1828530.683 | 1196106.537 | 1062747.5323 | 720413.5924 | 900664 |  | 13748351.4161 | Mike Miller | 13748351 | 0.4161
NEPCO - BOP Procurement | 0 | [10 empty] | 115533 |  | 359796 | 942335.3216 | 869190.342 | 631706.642 | 413221.638 | 367149.8002 | 248882.9176 | 801858 |  | 4749673.6614 |  | 4749674 | -0.3386
NEPCO - Construction | [10 empty] | 0 | 61343 |  | 2112822 | 3165417.2416 | 2919714.492 | 2121978.292 | 1388060.988 | 1233300.1652 | 836027.5376 | 2116060 |  | 15954723.7164 |  | 15954724 | -0.2836
NEPCO - Switchyard | [11 empty] | 0 |  | 355795 | 2012952.3136 | 1856705.007 | 1349408.557 | 882695.823 | 784280.3117 | 531646.6796 | 2372445 |  | 10145928.6919 |  | 10145929 | -0.3081
NEPCO - Reimburse Tax | [19 empty] | 50000 |  |  | 50000 |  | 50000 | 0
NEPCO % Complete | [11 empty] | 3651557 |  | 239706 | 217412 | [5 empty] | -4108675 | -3953393 | -3953393 |  |  | -3953393
Overheads and Fees -EECC | [7 empty] | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.33 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 | 77483.3333 |  |  |  | 929799.9967 |  | 929800 | -0.0033333
Overheads and Fees -NEPCO | [7 empty] | 198891.6667 | 198891.6667 | 198888.6667 | 198888.67 | 198888.6667 | 198899 | 198889 | 198891.6667 | 198891.6667 | 198891.6667 | 198891.6667 | 198895.6667 |  |  |  | 2386699.67 |  | 2386700 | -0.33
BASE FEE | [18 empty] | 3066700 |  |  |  | 3066700 |  | 3066700 | 0
EI (Mobilization of O&M) | 0 | [13 empty] | 125000 | 125000 | 125000 | 125000 | 283786 | 125000 |  |  | 908786 | Kevin Presto | 908786 | 0
WATER INTERCONNECT | [11 empty] | 38084 |  | 16048 |  |  |  |  | 1445868 |  |  |  | 1500000 |  | 1500000 | 0
PARTS | 0 | [15 empty] | 500000 | 500000 | 172731 |  |  |  | 1172731 | Mike Miller | 1172731 | 0
LAND | 0 |  | 15000 | 10000 | 10000 | 7500 | 0 |  | 0 | 932284.26 | 128660 | 8500 | 5000 | 259325 | [8 empty] | 1376269.26 | Steve Dowd | 1376268.86 | 0.4
ENVIR PERMITTING | 0 |  |  | 0 | 0 | 9930 | 32111 | 22234 | 64176 | 27327.91 | 8595.51 | 47810 | 11305 | 28716 | 41756 |  |  | 19859 |  |  |  |  | 313820.42 | Steve Dowd
POWER INTERCONNECT | 0 | [8 empty] | 10000 |  |  | 15000 | 9120 | 500000 | 500000 | 490000 | 1500000 | 1485000 | 450000 | 40880 |  | 5000000 | Chris Meyer | 5000000 | 0
GAS INTERCONNECT | 0 | [11 empty] | 946000 |  | 500000 | 54000 | [6 empty] | 1500000 | Chris Meyer | 1500000 | 0
START UP FUEL | 0 | [15 empty] | 500000 | 500000 | 0 |  |  |  | 1000000 | Kevin Presto | 1000000 | 0
RESALE HANDLING FEE | [18 empty] | 0 |  |  |  | 0 | Patrick Maloy | 0 | 0
INSURANCE | 0 | [11 empty] | 175875 | [8 empty] | 24125 | 200000 |  | 200000 | 0
SALARIES | 0 |  |  |  | 3365.69 | 22738 | 14946.71 | 7607 | 10912 | 18233.16 | 0 | 0 | 0 | 1469 | 11111.1111 | 11111.1111 | 11111.1111 | 22223.1111 | 40729 | 9462 | 180 |  | 185199.0044
DEVELOPMENT | 0 |  |  |  | 0 | 5040 | 19126 | 29873 | 31111 | 30781.11 | 14653.58 | 113717 | 143263 | 34982 | 28571.4286 | 56516 | 22986 | 73939 |  |  |  |  | 604559.1186 | 0
LEGAL | 0 | [6 empty] | 15170 |  | 29399.49 | 20442.9 | 10582 | 68346.51 | 54824 | 62208 | 10000 | 10000 | 207558 | 201847 | 6653 | 4641 |  | 701671.9 | 0
Total Plant | 16673400 | 43401650 | 4306075 | 10000 | 4304440.69 | 8662875.23 | 66183.71 | 611142 | 1050995 | 1325332.93 | 1103757.0933 | 4990044 | 3909419.3 | 8186544.3333 | 11783580.2549 | 9988230.9851 | 7867096.2851 | 7336640.0971 | 15447078.8094 | 2978085.7272 | 2128053 | -3929268 | 151024485.7183
Cumulative Total Plant | 16673400 | 60075050 | 64381125 | 64391125 | 68695565.69 | 77358440.92 | 77424624.63 | 78035766.63 | 79086761.63 | 80412094.56 | 81515851.6533 | 86505895.6533 | 90415314.9533 | 98601859.2867 | 110385439.5415 | 120373670.5267 | 128240766.8118 | 135577406.9089 | 151024485.7183 | 154002571.4455 | 156130624.4455 | 152201356.4455
$$/Kw | [22 empty] | 321.3287
Interest SWAP |  |  |  | -21556.4 | 66478.9 | -51000 | [16 empty] | -6077.5 | Rodney Malcolm
IDC | 413818 | 239841 | 375473 | 374160 | 374175 | 479817 | 431577.4186 | 437225.4821 | 445286.6764 | 454783 | 462626.3155 | 491955.341 | 516340 | 563836.3251 | 630718.1649 | 688237.4728 | 734578.864 | 778297.9667 | 866185.4242 | 0 | 0 | 0 | 9758932.4514 | Rodney Malcolm | 9758932.4514
Commitment Fee |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | Rodney Malcolm
FINANCING FEE | 0 | [21 empty] | 0 | Rodney Malcolm
CONTINGENCY (5% NEPCO; 3% Ttl Plant) | 0 | [17 empty] | 0 |  |  |  | 0 | Steve Dowd | 0
Subtotal | 413818 | 239841 | 375473 | 352603.6 | 440653.9 | 428817 | 431577.4186 | 437225.4821 | 445286.6764 | 454783 | 462626.3155 | 491955.341 | 516340 | 563836.3251 | 630718.1649 | 688237.4728 | 734578.864 | 778297.9667 | 866185.4242 | 0 | 0 | 0 | 9752854.9514
Cumulative subtotal | 413818 | 653659 | 1029132 | 1381735.6 | 1822389.5 | 2251206.5 | 2682783.9186 | 3120009.4008 | 3565296.0772 | 4020079.0772 | 4482705.3927 | 4974660.7336 | 5491000.7336 | 6054837.0588 | 6685555.2237 | 7373792.6965 | 8108371.5605 | 8886669.5272 | 9752854.9514 | 9752854.9514 | 9752854.9514 | 9752854.9514
Total Wheatland | 17087218 | 43641491 | 4681548 | 362603.6 | 4745094.59 | 9091692.23 | 497761.1286 | 1048367.4821 | 1496281.6764 | 1780115.93 | 1566383.4088 | 5481999.341 | 4425759.3 | 8750380.6584 | 12414298.4198 | 10676468.4579 | 8601675.1491 | 8114938.0638 | 16313264.2336 | 2978085.7272 | 2128053 | -3929268 | 161954211.3969
Cumulative Total | 17087218 | 60728709 | 65410257 | 65772860.6 | 70517955.19 | 79609647.42 | 80107408.5486 | 81155776.0308 | 82652057.7072 | 84432173.6372 | 85998557.046 | 91480556.387 | 95906315.687 | 104656696.3454 | 117070994.7652 | 127747463.2232 | 136349138.3723 | 144464076.4361 | 160777340.6697 | 163755426.3969 | 165883479.3969 | 161954211.3969
344.5834
IDC 6.5% | 6.5%
+ 35 Bps Com Fee | 0.35% | 163000000
$$/Kw | 470 | MW
DEBT RESERVE | 0 | [21 empty] | 0 | Rodney Malcolm
Total Current month less IDC | 16673400 | 43401650 | 4306075 | -11556.4 | 4370919.59 | 8611875.23 | 66183.71 | 611142 | 1050995 | 1325332.93 | 1103757.0933 | 4990044 | 3909419.3 | 8186544.3333 | 11783580.2549 | 9988230.9851 | 7867096.2851 | 7336640.0971 | 15447078.8094 | 2978085.7272 | 2128053 | -3929268 | 152195278.9455
Expense
WHEATLAND, INDIANA
ENVIR PERMITTING | 0 | 0 | 0 | 53841 | 82339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 136180 | Steve Dowd | 450000.42 | 450000 | -0.42
DEVELOPMENT | 0 | 1178 | 427 | 2729 | 1480 | 0 | 75487.01 | 68414.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 149715.2 | Steve Dowd | 754274.3186 | 754273.98 | -0.33857
LAND |  |  | 0 | 0 | 0 | [17 empty] | 0 |  | 1376269.26 | 1376268.86 | -0.4
SALARIES | 0 | 0 | 14497 | 0 | 304.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14801.38 | Steve Dowd | 200000.3844 | 200000 | -0.38444
LEGAL | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | Steve Dowd | 701671.9 | 701672.13 | 0.23
Subtotal Wheatland Expense | 0 | 1178 | 14924 | 56570 | 84123.38 | 0 | 75487.01 | 68414.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300696.58
Current FIT |  |  |  |  | -67129 | 12250 | -26420 | -23945 |  |  | 0 | 0 | [10 empty] | -105244
Total Income Statement | 0 | 1178 | 14924 | 56570 | 16994.38 | 12250 | 49067.01 | 44469.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195452.58
Petersburg, IN
LAND |  |  | 15000 | [19 empty] | 15000 | Steve Dowd
SALARIES |  |  | 0 | [19 empty] | 0 | Steve Dowd
DEVELOPMENT |  | 0 | 0 | 100 | [18 empty] | 100 | Steve Dowd
LEGAL |  | 0 | [20 empty] | 0 | Steve Dowd
Subtotal Petersburg Expense | 0 | 0 | 15000 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15100
Total Project Cost (w/o Debt Reserve) | 17087218 | 43642669 | 4711472 | 419273.6 | 4762088.97 | 9103942.23 | 546828.1386 | 1092836.6721 | 1496281.6764 | 1780115.93 | 1566383.4088 | 5481999.341 | 4425759.3 | 8750380.6584 | 12414298.4198 | 10676468.4579 | 8601675.1491 | 8114938.0638 | 16313264.2336 | 2978085.7272 | 2128053 | -3929268 | 162164763.9769
1.4555
Note on D50: acopela: Rounded the Cumulative total down to the nearest thousands
Note on K11: Shelly May: agreement with ABB today (3/19/99) is to hold payments until Aug, Sep, Oct