## Top Priorities
EES New Market State Status
2001-10-23
STATE | STATE LICENSE | EES PRIORITY | UTILITY | CHANGE REQUEST PREPARED | CSC STATUS (IMPACT STATEMENT) | Billing Model | EDI SET-UP COMPLETED BY | EDI TESTING STATUS | ENROLLMENT CAPABILITY BY | RATE APPROVAL | MAX. # OF EES RATES | EES SCHEDULING CAPABILITY | PHYSICAL DELIVERY COMPLETED BY | SUPPLIER TARIFF/SERVICE AGREEMENT | TRANSMISSION AGREEMENTS, ETC. | EDI TRADING PARTNER AGREEMENT | COMMENTS DELIVERABLES
Illinois | Yes | 1 | Illinois Power | 1622 | Completed | Supplier Consolidated | 2001-01-30 | Not Started | 2002-02-01 | Not Applicable | Not Applicapble | EWS | 2002-03-01 | Per Gloria - waiting on signed agreements from IP. - No issues. | 2001-12-01 | 2001-09-15 | Design Phase. - Rec'd pricing for Products. Sent to Bob G. for review and final solution approval.
Illinois | Yes | 1 | Commonwealth Edison | 1623 | Completed | Supplier Consolidated | 2001-01-30 | Not Started | 2002-02-01 | Not Applicable | Not Applicapble | EWS | 2002-03-01 |  | 2001-12-01 | 9/15/2001. Revised Per Gloria 9/29. | Design Phase. - SBO being registered with PUC.
Illinois | Yes | 3 | Ameren | N/A | N/A | TBD | N/A | N/A | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Analysis Provided
Maryland | Yes | 2 | BGE |  | Pending | Pending | 2002-06-01 | Not Started | 2002-06-01 | N/A | N/A | Jeff Merola EWS Contact | 2002-07-01 | Regulatory Reviewing | EWS | Requlatory Reviewing | Gloria needs Bus. Sponsor approval to move forward with agreements. Floris/Fite to review Supplier Process and advise to UDC changes that may benefit each party. Johnson working new product approvals - index product.
Massachusetts | Yes | 2 | Cambridge Electric | CR_961 | Completed | UDC Consolidated - Rate Ready | 2001-06-01 | Complete | 2001-06-20 | 5 days prior to meter read | Unlimited | EWS | 2001-07-01 | Completed | EWS | Completed | Pending enrollments
New Jersey | Yes | 1 | Connectiv (AEP) | CR_967 | Due 10/29 | UDC Consolidated - Bill Ready | 2002-01-01 | Not started | 2002-02-01 | Not Applicable | Not Applicable | EWS | 2002-03-01 | Completed | Pending | Pending | NME checklist submitted to CSC -
New Jersey | Yes | 1 | PSEG |  | Due 10/26 | UDC Consolidated - Bill Ready | 2002-12-01 | Not started | 2002-01-01 | Not Applicable | Not Applicable | EWS | 2002-02-01 | Pending | Pending | Pending | NME checklist submitted to CSC -
New Jersey | Yes | 1 | JCP&L (GPU) |  | Due 10/26 | UDC Consolidated - Bill Ready | 2002-12-01 | Not started | 2002-01-01 | Not Applicable | Not Applicable | EWS | 2002-02-01 | Pending | Pending | Pending | NME checklist submitted to CSC -
New York | Yes | 2 | Central Hudson Gas Electric |  | Pending NME checklist. | TBD | N/A | N/A | N/A | N/A | N/A | EWS | TBD | TBD | TBD | TBD | Fite/Merola met with Government Affairs to discuss billing issues & UDC Dereg status. Pending decsision at PUC level prior to submitting New Market Checklist to CSC
New York | Yes | 3 | NIMO | CR_1171 | Completed | Dual W/ Supplier Consolidated | N/A | N/A | TBD | N/A | Unlimited | EWS | TBD | Completed | Completed | N/A | PENDING DECISION FROM EES.
New York | Yes | 3 | NYSEG | ROM_1170 | Completed | Dual w/ Supplier Consolidated | N/A | N/A | TBD | N/A | Unlimited | EWS | TBD | Legal Review Pending | Legal Review Pending | N/A | PENDING DECISION FROM EES.
Ohio | Yes | 1 | CG&E | ECR_735 | Completed | Dual - Followed by UDC Consolidated Bill Ready. (Currently set up for Rate Ready | Completed | Completed | Completed | 7 days prior to enrollment. | Unlimited | EWS | 2001-12-01 | Completed | 2001-11-01 | Completed | Need confirmation of physical serve date. Need final on billing solution. Product Approval's Pending. Ability to calcualte transmission charges pending resolution.
Ohio | Yes | 1 | AEP - Columbus Southern | ROM_976 | Due 10/19. | UDC Consolidated Bill Ready | 2002-02-01 | Level 1 complete. | 2002-03-01 | N/A | N/A | EWS | 2002-04-01 | Legal Review Pending | Need Documentation | Legal Review Pending | NME checklist submitted to CSC -
Texas | Yes | 1 | Texas Utilities | ECR_992 | Completed | Supplier Consolidated | 9/1/2001(Pilot) 12/01/01 Open Market | Completed for Pilot. In Progress for Open Market | 2001-08-15 | N/A | N/A | EPMI - Preston Ochsner EWS Contact | 2001-09-01 | 2001-08-20 | 2001-08-20 | 2001-08-20 | Mass Market ROM Rec'd. Stipulated Volume/Heat rate pricing received. Demand/Energy pricing received. Distributed to EES/EWS for approval
Texas | Yes | 1 | CP&L |  | Completed | Supplier Consolidated | 2001-12-01 | In Progress | 2001-12-17 | N/A | N/A | EPMI - Preston Ochsner EWS Contact | 2002-01-01 | 2001-12-01 | 2001-12-01 | 2001-12-01 | Mass Market ROM Rec'd. Stipulated Volume/Heat rate pricing received. Demand/Energy pricing received. Distributed to EES/EWS for approval
Texas | Yes | 1 | WTU |  | Completed | Supplier Consolidated | 2001-12-01 | In Progress | 2001-12-17 | N/A | N/A | EPMI - Preston Ochsner EWS Contact | 2002-01-01 | 2001-12-01 | 2001-12-01 | 2001-12-01 | Mass Market ROM Rec'd. Stipulated Volume/Heat rate pricing received. Demand/Energy pricing received. Distributed to EES/EWS for approval
Texas | Yes | 1 | TNMP |  | Completed | Supplier Consolidated | 2001-12-01 | In Progress | 2001-12-17 | N/A | N/A | EPMI - Preston Ochsner EWS Contact | 2002-01-01 | 2001-12-01 | 2001-12-01 | 2001-12-01 | Mass Market ROM Rec'd. Stipulated Volume/Heat rate pricing received. Demand/Energy pricing received. Distributed to EES/EWS for approval
Texas | Yes | 1 | Reliant Energy | ECR_991 | Completed | Supplier Consolidated | 12/01/01 Open Market | In Progress | 2001-12-17 | N/A | N/A | EPMI - Preston Ochsner EWS Contact | 2001-01-01 | 2001-12-01 | 2001-12-01 | 2001-12-01 | Mass Market ROM Rec'd. Stipulated Volume/Heat rate pricing received. Demand/Energy pricing received. Distributed to EES/EWS for approval
NOTES:
NJ Market Analysis for JCP&L, 09/27

## Existing Markets
EES Existing Markets
STATE | EES PRIORITY | UTILITY | Cost to Implement | Billing Model | PHYSICAL DELIVERY COMPLETED BY
California | Done | Southern California Edison | Not Available | Bill Agent | 1998-04-01 | New enrollments are being accepted. As of today. Check Daily w/ Service Desk.
| Done | Pacific Gas & Electric | Not Available | Bill Agent | 1998-04-01 | New enrollments are being accepted. As of today. Check Daily w/ Service Desk.
| Done | San Diego Gas & Electric | Not Available | Bill Agent | 1998-04-01 | New enrollments are being accepted. As of today. Check Daily w/ Service Desk.
Ohio | Done | First Energy Corp (MSG), Toledo Edison, Cleveland Illuminating, Ohio Edison | 561740 | UDC Consolidated Rate Ready |  | NS needs metering contact for installations - referred to Bob Hurt.
Pennsylvania | Done | PECO Energy | Not Available | UDC Consolidated Rate Ready | 1999-01-01 | Customers w/ expired contracts being dropped. No new enrollments at this time.
New Hampshire | Done | New Hampshire Electric Coop | 50495 | UDC Consolidated Rate Ready |  | Ready to Enroll - No Customers from EES
Maine | Done | Central Maine Power Co | 288570 | UDC Consolidated Rate Ready | 2000-03-01 | New enrollments are being accepted.
| Done | Bangor Hydro Electric Power |  | UDC Consolidated Rate Ready | 2000-03-01 | Market Manager inquiry - how do we obtain pre-enrollment HU?
Rhode Island | Done | Naragansett | 58040 | UDC Consolidated Rate Ready | 2001-05-01 | 810 Issues - mapping to billing system
New York | Done | Consolidated Edison | 314471 | Dual with Supplier Consolidated | 2001-04-01 | 170 Tricon Invoices submitted to customer. RF researching missing cycles. Enron formed working group to push EDI implementation. Fite/Government Affairs working directly with utility to execute agency agreement. 1300 mass market customers submitted for October enrollment.
Massachusetts | Done | Western Massachusetts Elec |  | UDC Consolidated Rate Ready | 2001-06-01 | New enrollments are being accepted.
Massachusetts | Done | Massachusetts Electric Co |  | UDC Consolidated Rate Ready | 2001-06-01 | New enrollments are being accepted.
Massachusetts | Done | Cambridge Electric | 2001-06-01 | UDC Consolidated - Rate Ready | 2001-07-01 | New enrollments are being accepted.
Massachusetts | Done | BECO | 2001-06-01 | UDC Consolidated - Rate Ready | 2001-07-01 | New enrollments are being accepted.

## Revised_Group_Priorities
37187
STATE | STATE LICENSE | EES PRIORITY | UTILITY | CHANGE REQUEST PREPARED | CSC Change Request Status | EDI COMPLETED BY | DASR CAPABILTY BY | PHYSICAL DELIVERY COMPLETED BY | SUPPLIER TARIFF/SERVICE AGREEMENT | TRANSMISSION AGREEMENTS, ETC. | EDI TRADING PARTNER AGREEMENT | EDI TESTING STATUS | DRIVERS PHYSICAL/ FINANCIAL/ BOTH | NEW/EXISTING BUSINESS | MONTHLY MWh | ONE MONTH DELAY DOLLARS
|  |  | Ameren / CIPS | [11 empty] | 4796 | 14388
|  |  | Ameren / UE | [11 empty] | 120 | 360
|  |  | Cilco | [11 empty] | 355 | 1065
|  |  | GPU-Met Ed/Penelec | [5 empty] | Legal Review Pending | N/A | N/A |  | Physical | Existing | 649 | 1947
|  |  | PP&L | [9 empty] | Physical | Existing | 7624 | 22872
|  |  | Duquesne Light & Power | [9 empty] | Physical | Existing | 1243 | 3729
|  |  | Allegheny Power / West Penn | [11 empty] | 1200 | 3600
|  |  | Pennsylvania Electric | [11 empty] | 4566 | 13698
|  |  | Potomac Electric Company |  |  |  |  | 2005-01-01 |  |  |  |  | Physical | Existing | 85 | 255
|  |  | Public Service New Hampshire |  |  |  |  | 2002-01-01 | [5 empty] | New |  | 0
|  |  | Granite State Electric Co. | [12 empty] | 0
|  |  | Rochester Gas & Electric | [5 empty] | Need Documentation | [5 empty] | 312 | 936
|  |  | Orange & Rockland | [11 empty] | 887 | 2661
|  |  | Newport Electric Company | [9 empty] | Physical | New |  | 0
|  |  | EPEC | [11 empty] | 2565 | 7695
|  |  | GSU | [11 empty] | 298 | 894
|  |  | SPS | [11 empty] | 15105 | 45315
|  |  | SWEPCO | [11 empty] | 136 | 408
|  |  | Delmarva | [11 empty] | 4987 | 14961
First Energy Corp (Other)
|  |  | Dayton Power & Light Co. |  |  | 2001-05-01 |  |  | Need Documentation | Need Documentation
0
[15 empty] | 44928 | 134784
[15 empty] | Monthly Volume | Monthly Value