## Sheet1
EDI Production Set-up Steps:
1. Call pipe, forward amendment, get estimate on document turn around
2. Ask pipe what if anything needs to be established on their backend system
3. Get user ids and passwords established on each pipe
4. Get security access in Unify Gas Parrallel environment to ENA upstream
5. Setup transportation contracts in Sitara and Global | [5 empty] | Need scheduling team's / Kathy Kelly's help
6. Setup pipelines internal/external pools in production environment | [5 empty] | Need scheduling team's / Kathy Kelly's help
7. Send simple EDI test transaction to pipelines test environment
8. If successful, send simple EDI test to pipelines production envirnoment
9. If successful, notify scheduling desk ENA Upstream is ready and available for production
10. TPA NOT signed - testing w/ pipeline
10. TPA signed; testing w/ pipeline
10. RED indicates successful implementation & desk rollout
HIGH PRIORITY PIPES
Pipe | Amend Sent | TPA Contact | Phone # | User ID | Password | Contracts | Sitara # | K# in Unify | Inv Accts Setup | EDI Setup Complete | Comments
ANR | 2001-04-19 | Charlie Bass | (832)-676-3801 | s030900; 901; 902; 903 | april24 | IT: 106038; PTS-1: 106039; PTS-3: 106040 | 703533, 703523, 703537 | Y | Y | N | 5/14. TPA signed and sent to ANR for signatures. Due to special coding required and code freeze, we will be able to EDI noms July 1.
CGLF | 2001-04-19 | Randy | 3043572180 | nav1498 | aggie1kk | ITS1:70480; ITS2: 70481; IPP: 70482 |  | N | Y |  | Amendment was signed. Testing in progress
HIOS | 2001-04-19 | Robert Young | 8326765723 | gro | happy (domain - epfs) | IT: 5080 |  | Y | Y |  | TPA NOT signed - testing w/ pipeline. Left several messages. No response. .
TENN | 2001-04-19 | Leah Hall | 8326762637 | 001076A; 001076B | energy; plant (domain - tgpl) | sa pool: 80357; it: 36568 | 703532, 705740 | 36568 ONLY | Y |  | Tennessee has an issue with a section 7 language Legal has it. -Sandi needs to follow through..
UTOS | 2001-04-19 | Robert Young | 8326765723 | gro | happy | IT: 5081 |  | Y | Y |  | TPA NOT signed - testing w/ pipeline. - Left several messages.
STRY | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  | N | N |  | TPA NOT signed - testing w/ pipeline. Left several messages.
SECONDARY PRIORITY
Pipe | Amend Sent | TPA Contact | Phone # | User ID | Password | Contracts |  | K# in Unify | Inv Accts Setup | EDI Setup Complete | Comments
GLF STH | N | Randy Young | 7135444715 | @12402A | k3mirage | 28877, 28878, 28879 |  | 77 & 78 ONLY | N |  | Currently , we do not edi with them. Company was sold. New service provider, nothing is coded. TPA needs to be sent
CGAS | 2001-04-19 | John Young | 3043572887 | nav1498 | aggie1kk | IT: 67582; IT: 70473, |  | Y | N |  | Amendment was signed. Testing in progress their system, our contract not activated.
ALGN | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 |  |  | N | N |  | TPA signed. Testing in progress.
ETENN | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 |  |  | N | N |  | TPA signed. Testing in progress.
SEAR | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal |  |  | N | N |  | Amendment signed 5/16/01
PEPL | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal |  |  | N | N |  | Amendment signed 5/16/01
TRKL | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal | IT: 016791, TABS1: 016792; CAPACITY REL (FT): 016794 | 703481, 703475 | 91 & 92 ONLY | N |  | Amendment signed 5/16/01
TGT | 2001-05-03 | William Huels | 27--688-6748 | $KELLY_K | VOGESOB | PSNG15555; PSNG2556 |  | Y | N |  | Sent an amendment 5/03. They want a TPA - working with Nancy Cook.
THIRD PRIORITY LIST -5/10
Pipe | Amend Sent | TPA Contact | Phone # | User ID | Password | Contracts |  | K# in Unify | Inv Accts Setup | EDI Setup Complete | Comments
| N |  | 304-623-8549 | [5 empty] | N |  | Legal has to initiate an amendment.
| N |  | 713-853-9421 | [5 empty] | N |  | Legal has to initiate an amendment.
| N |  | 713-853-9421 | [5 empty] | N |  | Legal has to initiate an amendment.
| N |  | 713-853-9421 | [7 empty] | Legal has to initiate an amendment.
| N |  | 719-520-4599 | [7 empty] | Legal has to initiate an amendment.
In Production
Pipe | Amend Sent | TPA Contact | Phone # | User ID | Password | Contracts |  | K# in Unify | Inv Accts Setup | EDI Setup Complete | Comments
TETCO | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 | IT: 910109; TABS: 910110; BACKHAUL: B910109 | 707322, 910110, 707515 | Y | N |  | Amendment was signed. 5/17 -Testing in progress. Ready for production.
TRCO | N | Kathy Burkhe | 7132154659 | upnr160; upnr290 | kathy; shane | IT: 3.8539 |  | Y | N | Y | Working. Currently use flat file upload; TPA is not required; will need TPA upon OneLine rollout; file file counterparty requirements are established and schedulers CAN send electronic nomination as of 4/1/01; ; completed successful test in production. NOTE: users had ENA Upstream added to Enron North Americas.
SONAT | N |  |  | snt2q09 | cn9762 | PSNG15555; PSNG2556 |  | Y | N |  | We currently do not do edi with them. They have not been responsive . Noms will be manual
NGPL | N | Michael Schisler | 7133699337 | cenag10 | cenag10 or ENAUP01 | IT: 118900 |  | N | N | N | Currently use gas*flow method of file upload; TPA not required; grid codes must be hardcoded in program. Due to code freeze, code changes can not take place until after MSSQL migration

## Sheet2
ELECTRONIC DELIVERY MECHANISM IN PRODUCTION | [17 empty] | Current Production |  |  | August 27,01
Priority | Pipe | Amend Sent | TPA Contact | Phone # | User ID | Password |  | Contracts | Sitara # | K# in Unify | Inv Accts Setup | EDI Setup Complete | EES,Inc. | EEM Corp. | Comments | Electronic Capability | EDI Testing | EDI / Flat File | Manual Noms
1 | CGAS | [13 empty] | 9-4 sent to legal. | y |  |  | X
1 | CGLF | [13 empty] | 9-4 sent to legal. | Y |  |  | X
1 | ALGO | [5 empty] | Duke | [7 empty] | 9-4 sent to legal. | y |  |  | X
1 | ETEN | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 | Duke |  |  | N | N |  |  |  | 9-4 sent to legal. | Y |  |  | X
1 | TETCO | [5 empty] | Duke | [7 empty] | 9-4 sent to legal. | y |  |  | x
1 | TRNK | N | Kathy Burkhe | 7132154659 | upnr160; upnr290 | kathy; shane | CMS |  |  | Y | N | Y |  |  | 9-5 sent to legal | Y |  |  | X
1 | PEPL | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal | CMS |  |  | N | N |  |  |  | 9-5 sent to legal | Y |  |  | X
1 | SEAR | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal | CMS |  |  | N | N |  |  |  | 9-5 sent to legal | Y |  |  | X
1 | TGT | 2001-05-03 | William Huels | 27--688-6748 | $KELLY_K | VOGESOB |  |  |  | Y | N |  |  |  | 9-6 sent to legal | Y |  |  | x
1 | FGT | N | Michael Schisler | 7133699337 | cenag10 | cenag10 or ENAUP01 | ETS |  |  | N | N | N |  |  | 9-6 sent to legal | Y |  |  | X
1 | NNG | [5 empty] | ETS | [7 empty] | 9-6 sent to legal | Y |  |  | x
1 | TW | 2001-04-19 | Robert Young | 8326765723 | gro | happy | ETS |  |  | Y | Y |  |  |  | 9-6 sent to legal | Y |  |  | X
1 | TENN | [5 empty] | El Paso | [8 empty] | Y |  |  | x
1 | EPNG | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 | El Paso |  | 707322, 910110, 707515 | Y | N |  |  |  | In progress | Y |  |  | X
1 | ANR | 2001-04-19 | Charlie Bass | (832)-676-3801 | s030900; 901; 902; 903 | april24 | El Paso |  | 703533, 703523, 703537 | Y | Y | N |  |  | 9-10-01 sent to legal | Y |  |  | x | x
1 | Crod | 2001-04-19 | Charlie Bass | (832)-676-3801 | s030900; 901; 902; 903 | april24 |  |  | 703533, 703523, 703537 | Y | Y | N |  |  |  | Y |  |  | x
Have EDI Capabilities - Not Available at this Time
2 | PGEN | N | Randy Young | 7135444715 | @12402A | k3mirage |  |  |  | 77 & 78 ONLY | N |  |  |  |  | y | N |  | x
2 | Gulf South | N |  | 713-853-9421 | [6 empty] | N |  |  |  |  | Y | N |  | X
2 | IROQ | N |  | 713-853-9421 | [6 empty] | N |  |  |  |  | Y | N |  | X
2 | NFUL | N |  | 713-853-9421 | [11 empty] | Y | N |  | X
PROPRIETARY FILES
1 | NGPL | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  |  | N | N |  |  |  | Currently we use flat file upload; TPA not required at this time. However, GID codes must be hard coded in program. | Y | N |  | X
1 | NIGAS | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  |  | N | N |  |  |  | Need company code; requires IT to update the GID table | Y | N |  | X
1 | MICHCON | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  |  | N | N |  |  |  | Need company code; requires IT to update the GID table | Y | N |  | X
1 | PEOPLES | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  |  | N | N |  |  |  | Not available at this time. Need to develop. | Y | N |  | X
1 | TRCO | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  |  | N | N |  |  |  | Currently uses flat file upload: tpa not required. Will need tpa upon Oneline Rollout. | Y | N |  | X
PIPE DOES NOT OFFER EDM AT THIS TIME - MANUAL ONLY
3 | NRAM/Reliant | N |  |  | snt2q09 | cn9762 |  |  |  | Y | N |  |  |  |  | N | N |  | EBB
3 | WLPC | N |  | 713-853-9421 | [11 empty] | Y | N |  | EBB

## Sheet3
[7 empty] | Enron Energy |  |  |  |  | Services Inc
ELECTRONIC DELIVERY MECHANISM IN PRODUCTION | [14 empty] | Current Production |  | August 27,01
Priority | Pipe | Amend Sent | TPA Contact | Phone # | User ID | Password | Contracts | Sitara # | K# in Unify | Inv Accts Setup | EDI Setup Complete | Comments | Electronic Capability | EDI Testing | EDI / Flat File | Manual Noms
1 | ALGO | [11 empty] | y |  |  | X
1 | ANR | 2001-04-19 | Charlie Bass | (832)-676-3801 | s030900; 901; 902; 903 | april24 |  | 703533, 703523, 703537 | Y | Y | N |  | Y |  |  | x
1 | CGAS | [11 empty] | y |  |  | X
1 | CGLF | [11 empty] | Y |  |  | X
1 | EPNG | 2001-04-19 | Robert Young | 8326765723 | gro | happy (domain - epfs) |  |  | Y | Y |  |  | Y |  |  | X
1 | FGT | N | Michael Schisler | 7133699337 | cenag10 | cenag10 or ENAUP01 |  |  | N | N | N |  | Y |  |  | X
1 | NNG | [11 empty] | Y |  |  | x
| TENN | [11 empty] | Y |  |  | x
1 | TETCO | 2001-04-19 | Leah Hall | 8326762637 | 001076A; 001076B | energy; plant (domain - tgpl) |  | 703532, 705740 | 36568 ONLY | Y |  |  | Y |  |  | X
1 | TGT | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 |  | 707322, 910110, 707515 | Y | N |  |  | Y |  |  | X
1 | TRNK | N | Kathy Burkhe | 7132154659 | upnr160; upnr290 | kathy; shane |  |  | Y | N | Y |  | Y |  |  | X
1 | TW | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  | Y | Y |  |  | Y |  |  | X
1 | ALGN | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 |  |  | N | N |  |  | Y |  |  | X
1 | ETENN | 2001-04-19 | Trish Meigs | 7136276160 | lnk7218 | kathy1 |  |  | N | N |  |  | Y |  |  | X
1 | PEPL | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal |  |  | N | N |  |  | Y |  |  | X
1 | SEAR | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal |  |  | N | N |  |  | Y |  |  | X
1 | TGT | 2001-05-03 | William Huels | 27--688-6748 | $KELLY_K | VOGESOB |  |  | Y | N |  |  | Y |  |  | x
1 | TRKL | 2001-05-01 | Janet Langford | 7139897655 | msr2231 | fi26nal |  | 703481, 703475 | 91 & 92 ONLY | N |  |  | Y |  |  | X
Have EDI Capabilities - Not Available at this Time
2 | CROD | 2001-04-19 | Robert Young | 8326765723 | gro | happy (domain - epfs) |  |  | Y | Y |  |  | Y |  |  | x
2 | Gulf South | N |  | 713-853-9421 | [5 empty] | N |  |  | Y | N |  | X
2 | IROQ | N |  | 713-853-9421 | [5 empty] | N |  |  | Y | N |  | X
3 | NFUL | N |  | 713-853-9421 | [8 empty] | Y | N |  | X
PROPRIETARY FILES
3 | NGPL | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  | N | N |  |  | Y | N |  | X
3 | NIGAS | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  | N | N |  |  | Y | N |  | X
3 | MICHCON | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  | N | N |  |  | Y | N |  | X
3 | PEOPLES | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  | N | N |  |  | Y | N |  | X
3 | TRCO | 2001-04-19 | Robert Young | 8326765723 | gro | happy |  |  | N | N |  |  | Y | N |  | X
PIPE DOES NOT OFFER EDM AT THIS TIME - MANUAL ONLY
2 | PGEN | N | Randy Young | 7135444715 | @12402A | k3mirage | 28877, 28878, 28879 |  | 77 & 78 ONLY | N |  | EDI capability NOT available; working on new implementation; TPA is progress. | N | N |  | EBB
2 | NRAM | N |  |  | snt2q09 | cn9762 | PSNG15555; PSNG2556 |  | Y | N |  | NO EDI capability at this time. TPA in progress. | N | N |  | EBB
3 | WLPC | N |  | 713-853-9421 | [7 empty] | EDI capability but not GISB compliant. | Y | N |  | EBB