## Regulatory
ENRON NORTH AMERICA
GOVERNMENT AFFAIRS REPORT
Support Type | Deal Name | Responsible Person | $ Impact (MM) | Key Issues | Updated | Strategies/Comments/Next Actions
Regulatory Risk | Alberta PPA | Rob Hemstock |  | Modify Balancing Pool begins to dispatch Clover Bar PPA to more closely align Variable Cost with "no harm" commitment rather than try and minimize overall cost. | 2001-03-06 | 1. Long-term plan for sale of unsold PPAs (2300 MW of capacity) by Balancing Pool to a competitive market participant. 2. Short-term resolution of current offer strategy of unsold PPAs by Balancing Pool not a true variable cost. 3. ESBI Alberta (Transmission Administrator) Tariff Application seeks to incorrectly charged to PPA Buyer instead of PPA Owner. 4. Power Pool Rule Changes to enhance supplier ability to engage in physical bilateral contracts (direct sales). 5. Co-ordination of outage planning between TA and IPPs, PPA Buyers and PPA Owners. 6. Power Pool Rule Change that prohibits importers from setting pool price and distorts Alberta Power Pool Price downward.
| Cal PX Dissolution - Chargeback Process | Mary Hain Alan Comnes |  | Cal PX is utilizing its tariff in a manner that will have severe financial costs for EPMI. | 2001-03-06 | 1. ENA Legal has secured Injunction. 2. Govt Affairs is seeking FERC actions to support overall position that Chargeback is inappropriate action of Cal PX. 3. Contact with CDWR (M. Peevey) to complete the confiquration to include LCs. 4. Governor Davis "expropriation" of SCE / PG&E Block Forward positions still unclear in terms of economic implications.
| CPUC Subpoena / Lawsuits | Jim Steffes |  | Legal risk associated with class action lawsuits. Legal obligations of EPMI / EES / PGE to provide information. Public perception. | 2001-03-06 | Continue to support ENA Legal in defending Enron's interests. CPUC focus has fallen off from last summer given other issues (rate decisions).
| SDG&E Complaint Seeking Cost-Based Rates for All Sellers into Cal ISO and Cal PX (etal) | Mary Hain |  | SDG&E sought relief at FERC that would have removed Market-Based rate authority for all parties selling into the Cal ISO and Cal PX. | 2000-12-15 | FERC issued report in mid December. Key outcomes - 1. Non-stakeholder board for ISO. 2. $150/Mwh soft cap. 3. Defederalize CA UDC assets. 4. ALJ lead process to determine long-term contracts.
| Ontario Market Opening | Aleck Dadson |  | Seek Government commitment to "date certain" for market opening. | 2001-03-06 | Lobbying Ontario government to confirm market opening date.
| Peaker Sales | Mary Schoen Susan Landweher Barbara Hueter |  | IN - legislation may require sale to be approved by PUC. TN - legislation may modify GRT exemption. | 2001-03-06 | IN - Working on legislation re commission approval requirements. Legislation introduced would possibly require Enron to obtain prior commission approval to transfer ownership of plant. TN - Continue to monitor State budget deficit and implications for GRT taxes and PILOT arrangement.
Advocacy | Federal Wholesale Restructuring Legislation | Tom Briggs |  | Congressional mandate authorizing FERC to regulate bundled retail transmission service. | 2001-03-06 | Murkowski bill introduced 2/26/01 - insufficient electric transmission authority discussed for Open Access.
| EPMI v. FERC | Joe Hartsoe |  | FERC authority to regulate "all" transmission, including transmission used in bundled retail sales. | 2001-03-06 | US Supreme Court has accepted EPMI's legal challenge to FERC decision to not actively regulated transmission component of bundled retail sales. Expect legal case late Fall.
| RTO West | Steve Walton |  | Transmission access & market design. | 2001-03-06 | Current objective is to clarify design of transmission rights to (1) reduce the number of hubs/zones and tradable elements between hubs/zones, (2) fully define nature of transmission right to make trading simpler, (3) move debate toward accepting uncovered schedules (a modification of the current non-firm approach). Regular meetings held between Congestion and Planning, Ancillary Services, Scheduling and Pricing and Tariff groups are being used to coordinate efforts and to factor in Desk's view of what is needed
| SPP RTO | Ron McNamara |  | Transmission access & market design. | 2001-03-06 | SPP is working at detailed Market Structure issues. Govt Affairs leading the drafting efforts. SPP Board vote delayed from February on key market rules - pursuing votes.
| GridSouth Transco | Joe Connor Tom Chapman |  | Transmission access & market design. | 2001-03-06 | The second meeting of parties interested in collaborative process for both the GridSouth and SeTrans RTOs is being planned for late March. Also considering actions to ensure that neither RTO makes expenditures on market designs that have not been approved by FERC
| Southern Gridco | Joe Connor |  | Transmission access & market design. | 2001-03-06 | The second meeting of parties interested in collaborative process for both the GridSouth and SeTrans RTOs is being planned for late March. Also considering actions to ensure that neither RTO makes expenditures on market designs that have not been approved by FERC
| Florida RTO | Dan Staines |  | Transmission access, market design, 2020 Commission | 2001-03-06 | The major focus at the present time is on the real time energy market design. Joint Participants filing with FERC calls for a balanced schedule approach to the real time energy market. Presently working on a Real Time Energy Market "White Paper" that will clearly state our position and will be used to shift a balanced schedule approach to an unbalanced/uncovered approach. Have been having informational discussions with participants and stakeholders re benefits of a liquid real time energy market. Meetings scheduled with FL&P and TECO over the next two weeks. Governor's 2020 Study Commission issued its wholesale market recommendations to the Legislature on 1/31/2001. Senate Regulated Industries and House Telecommunication and Utilities Committees held public hearing on the recommendations the first two weeks of February. Enron is preparing comments on Draft Legislation dealing with Utility status.
| MISO / Alliance RTO | Jeff Brown |  | Transmission access & market design. | 2001-03-06 | FERC Settlement Conference held re MISO/Alliance merger. Outcome - RTOs will be separate but will work together to form a seamless market place. Enforcement of Ohio Settlements calling for nondiscriminatory access under the same tariffs, terms and conditions. Meetings with PUC chairman and legislators held. Complaint submitted to enforce OH settlements. Working on proposed tariff revisions.
| NYISO RTO | Howard Fromer |  | Key issues - 1. Circuit breaker for prices. 2. Interfaces with PJM and NE-ISO. 3. RTO filing. | 2001-03-06 | Comments filed 2/22/2001. Two pleadings filed. One dealing with the flaws in the NY proposal. The other pleading regarding size and scope to form one NE regional RTO. Intend to file protests to package of measures imposed- 18 month extensions of 1,000 bid cap, temporaneous extraordinary measures authority extended to 10/2002. Meeting held 3/1/2001 with suppliers to create coalition to educate policy makers and public on benefits of competition. Key next step - Coalition meetings with policy makers to ensure reasonable actions if power prices spike.
| California Matters - ABX1 | Sandi McCubbin |  | CDWR authorization to purchase electricity for "net short" of PG&E, SCE, and SDG&E. On and after January 1, 2003, the CDWR shall not contract under this division for the purchase of electrical power. Legislation also ends Direct Access going forward. | 2001-02-05 | Passed and signed by Governor Davis on 2/4/01. CDWR is implementing necessary contracts under "supervision" of Mike Peevey (SCE / New Power) & David Freeman (LADWP).
| California Matters - ABX18 | Sandi McCubbin |  | Utility authority to recovery past undercollection. | 2001-03-06 | Enron has offered legislative language to be included that would establish the end of the AB1890 rate freeze as the earlier of enactment or date that rates are established - seeking to legally protect past PX Credit underpayment. Urgency of bankruptcy is top agenda. In committee. Existing law authorizes authorizes the Director of Finance to accept on behalf of the state any gift of real or personal property whenever the director deems the gift and the terms and conditions thereof are in the best interest of the state. Bill would specifically authorize the director to accept on behalf of the state any tangible or intangible asset of an electrical corporation, as defined, including any parent or subsidiary corporation of that electrical corporation.
| California Matters - ABX31 | Sandi McCubbin |  | Air pollution, public utilities, electricity, curtailment programs | 2001-03-06 | Existing law authorizes any person to petition the hearing board of an air pollution control district or air quality management district for a variance from the rule, regulations, or orders of the district. Hearing date set for 3/7/2001. Re-referred to Comm. on APPR.
| California Matters - ABX60 | Sandi McCubbin |  | Electrical generating facilities certification | 2001-03-06 | Existing law requires State Energy Resources Conservation and Development Commission to approve the siting of electrical generating facilities, as specified. This bill would require, as a condition of certification by the commission, that an applicant offer to sell to an electrical corporation, a municipal corporation, or the Department of Water Resources, at a just and reasonable cost base price electrical power generated by the facility. In committee. First hearing set. Hearing cancelled at request of author.
| California Matters - SBX16 | Sandi McCubbin |  | California Consumer Power and Conservation Financing Authority. | 2001-03-06 | Under existing law, PUC has regulatory authority over public utilities, including electrical corporations and other specified entities. This bill would create the CA Consumer Power and Conservation Financing Authority, with powers and responsibilities as prescribed, including the issuance of revenue bonds, for the purposes of augmenting electric generating facilities and to ensure a sufficient and reliable supply of electricity. From committee with author's amendments. Read second time. Amended. Rereferred to committee.
| California Matters - SBX27 | Sandi McCubbin |  | Legislative "fix" to allow continued Direct Access. | 2001-03-06 | Sen. Bowen has indicated that the legislation will be drafted and passed. Enron (with customers and other marketers) has submitted language. Existing law imposes various duties and responsibilities on the Department of Water Resources with respect to the sale of water and power. This bill, would after a period of time that the bill would require the PUC to determine, suspend the right of a retain end use customer to acquire service from other providers until the department no longer supplied power, as specified.
| InPower Filings | Christi Nicolay |  | EPMI will have authority to support Industrial generation participation in Wholesale markets. | 2001-03-06 | FERC action is expected within 60 days granting EPMI authority to act under InPower.
| FP&L / Entergy Merger Complaint | Christi Nicolay |  | RTO formation, transmission access, market power. | 2001-03-06 | Filed comments with FERC seeking RTO formation as key condition precedent. Waiting for FERC to act.
Regulatory Ventures | Project E-Trans | Jim Steffes |  | ISO operator. | 2001-03-06 | Held meeting with PJM management. PJM proposes to "sell" their Market Operating System to other RTOs in Eastern Interconnect (and throughout world) as backbone for future market structure. PJM wants our support for their efforts - including policy agreement on market structure.
Deal Support | PSE&G | Steve Montovano |  | Regulatory approval. | 2001-03-06 | PSE&G Capacity Mgt: Working on MOU language and finalizing operational matters with respect to managing 20% of PSE&G's capacity assets. MOU is agreed in principal, signature is imminent. Once a settlement is filed in conjunction with PSE&G's transfer docket, definitive agreements will be finalized within 30 days.
| Las Vegas Cogen 1 and 2 | Paul Kaufman |  | Reformation of contract to allow operation of LVC 1 as EWG rather than QF | 2001-03-06 | Work legislature and PUCN to secure early approval for ENA response to Nevada Power RFP
| Las Vegas Cogen 2 | Paul Kaufman |  | Wastewater disposal; transmission and interconnection | 2001-03-06 | Get Governor's office to intervene with City of North Las Vegas and Sierra.
| Antelope Valley | Mary Hain |  | Interconnection Agreement | 2001-03-06 | Reviewing agreement for consistency with business objectives and FERC requirements.
| Longview Power Plant | Paul Kaufman |  | Current 250 MW threshold for EFSC sitting. | 2001-03-06 | Meeting held 2/27/2001 with Washington Governor Locke. Succeeded in getting support for increase to 350 MW. Bill has passed out of both Senate and House Committees. Work floor of both houses to ensure enactment.
| Alamac | Christi Nicolay |  | Interconnection Agreement | 2001-03-06 | Alamac deal has closed. Assisting on regulatory/legal issues on draft interconnection agreement and issues with charges that CP&L is trying to assess Enron for interconnection costs (on facilities already built).
| CA QF Restructuring | Alan Comnes |  | Monitor development and passage of decisions/bills that affect QF pricing, including ABX 47. In particular, assist origination team on regulatory feasibility of selling gas swaps as a solution to current high energy prices. | 2001-03-06 | Need to consider pushing increased visibility with utilities, CPUC and legislature. Legislation does not have sufficient support to pass currently.
| MS Georgia Control Area | Christi Nicolay |  | NERC rules. | 2001-03-06 | Support development of MS / EPMI control area using Olgethorpe outsourcing at both SERC and FERC. Waiting to hear from MS.
| People "Future of the Disco" | Roy Boston |  | Appropriate restructuring strategies to support PEC. | 2001-03-06 | Supporting Central Gas Origination in discussions with PEC. A gas incentive and unbundling mechanism report/document forwarded to ENA who is under discussions with PEC advising PEC of ENA's recommendations. Anticipated that PEC will make filing or seek legislative changes in the near future to bring certainty to its gas cost recover mechanisms.
| Silver Oak | Dan Allegretti |  | CT funding for green energy. | 2001-03-06 | Expect to make a key filing with CT regulators in the next several days. Hearings will begin 3/19/2001. Enron is expected to testify. Political support for the project remains high.
| Clarksdale | Christi Nicolay |  | Enron has been shortlisted (1st in line) to provide control area services to Clarksdale | 2001-03-06 | Working on comments to Entergy's draft interconnection agreement with Clarksdale and are submitting a request to SPP to create a control area.