## List (hidden)
ENERGY OPS - SETTLEMENTS/VM REVISED FINAL REPORT LIST
2000-06-16
| C# | PRIORITY | REVISED | NAME OF REPORT
1 | 1 & 2 | SS | SS | The Matrix - Transaction Detail
2 | 7 | SS | SS | G/L Line Item Report - Current Month (GL 110)
3 | 90 | SS | SS | Unify vs. SAP I/C Compare Report (Unify Report)
4 | 50 | SS | SS | Unify A/R Cash Flow Report (Apache Report)
5 | 15 | SS | SS | A/R and A/P Aging
7 | 46 | VH | SS | Past Due A/R Invoice > 60 Days Excluding Invoices Prior to 1/31/99 (for insurance policy)
16 | 48 | H | SS | Cash Forecast Report (Detail)
17 | 49 | H | SS | Forecasted Invoice by Expected Date
6 | 45 | VH | VH | Interface Detail Backup A/P Reports
8 | 8 | H | H | Intercompany A/R & A/P (GL 150)
9 | 9 | H | H | MSA Consolidated I/S Trial Balance (GL 210)
10 | 7 | H | H | Various Ad Hoc Queries (DSS)
11 | 16 | H | H | MSA Consolidated Balance Sheet Trial Balance (GL 211)
12 | 47 | H | H | Unapplied Cash Report
13 | 10 | H | H | Account Inquiry - A/P
14 | 10 | H | H | Account Inquiry - A/R
15 | 47 | H | H | Cash Deposit Listing by Deposit Date & Counterparty
18 | 48 | H | H | Forecast vs. Received by Counterparty
19 | 48 | M | M | Cash Forecast Report (Summary)
20 | 57 | M | M | Cash Collections by Accounting Month
21 | 58 | M | M | Late Payment by Coordinator & Invoice Due Date
22 | 59 | M | M | Late Payment by Counterparty
23 | 60 | M | M | Cash on Account
24 | 48 | M | M | A/P Load Outflow Forecast
25 | 56 | M | M | A/R Conversion Balance Analysis (BG54P660)
26 | 90 | L | L | Cash Forecast by Due Dates Graph
2025-09-26 22:45
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/ENERGY_OPS_000630.xls'#$List

## Showstoppers (hidden)
ENERGY OPS - SETTLEMENTS/VM REPORT LIST
REVISED SHOWSTOPPERS
2000-06-23
REPORT NAME | REPORT TYPE | MENU PATH | SAP DELIVERABLES | ENA ISSUES | COMMENTS/UPDATE | ACTION ITEMS (AI) & RESULTS (R)
#1-The Matrix-Transaction Detail Needed 8/1 (pending Troy K's agreement) | Custom | Accounting\Enterprise Controlling\Profit Center Accounting\Information System\Report Selection\ENA Matrix Report\ENA Matrix Report Your selection paramaters should be Period 8, Company 0364. You can leave profit center blank. | Matrix Report. Matrix Detail Report. | Users to first become comfortable with the summary report and then will pursue a detailed report. | Report is currently in development. The current plan is to bring in the PCA line item, special ledger information (settlement period) and Vendor/Customer Master Data into Excel and run VLOOKUP functions to create a report that includes all fields required by user by 6/29. | R: Settlements and OA group users viewed the summary matrix report in SAP. AI: Rhonda, Gary, and John V to work with the report and to review the accuracy of profit center mapping.
#2-G/L Line Item Report (GL 110) Complete | Standard | Accounting\Financial Accounting\General Ledger\Periodic Processing\Information System\Report Selection\ Information System\Account Information\Line Items | None - Accepted by Business Unit 6/23 | Manual work needed to present data to management. Report wraps one line item to the following line. | Can't change standard report format (wrapping) - use the GL extract report. | None
|  | Accounting\Financial Accounting\General Ledger\Account\ Display Line Items (use variant) | None - Accepted by Business Unit 6/23 | none | Per 6/14 phone conversation with Gary/Rhonda/Juan, instructed user to click on additional field icon and choose quantity field and included that column in the report. Report does not wrap. Custom layout was created that is suitable for users. | None
#3-Unify A/R Cash Flow Report (Apache Report) (Needed 8/1) | File Upload to Excel, Run Report In Access | Accounting\Financial Accounting\Accounts Receivable\ Periodic Processing\Information System\Report Selection\ Other Analyses\Account\Line Items. | A/R Line Item Flex File Upload - Done | E-Credit rating not available in SAP. | Send A/R line item report from SAP to Access and add in the E-Credit information. Sent test A/R file extract to S. Cook on 6/15. Also categorized document types by Invoice, Netting and Cash Application to be used for the report columns. | R: Sam is working on the access report using the flat file format from SAP. Excel cannot accommodate the spreadsheet format when the number of line items in the SAP report exceed 65,000. Sam said he is making steady progress. AI: Sam, Ranier, and Kris to communicate and resolve outstanding items as they are identified.
#4-Unify vs SAP I/C Compare Report (Needed 7/5) | Unify Report | N/A | None | Need various subtotals added to report, need variances supressed on mcf volumes, and need draft items added to the unify side of the report. Various formatting and header changes requested also. | N/A | R: Melissa White has communicated the ENA issues to the unify programmers. Revised reports with user requested features are available for review 6/23. AI: Users to review the report format and data and provide feedback to Melissa White.
#5-A/R and A/P Aging (Needed 7/5) | Standard | Accounting\Financial Accounting\Accounts Receivable\ Periodic Processing\Info System\Select Report\Information System\Account Information\AR/AP Aging Report |  | (1) xef2 field will be populated for data converting from MSA (2) A/P A/R Aging sorts by profit center and is awkward to use. (3) The multiple search options that exist with dynamic selections and variants are a workable option for 7/1 but do not provide the flexibility requested for long-term use (such as viewing data by profit center/region). Bryce suggested utilizing an external table that SAP can reference for running reports by coordinator or regional responsibilities. In addition, settlement period is not displayed on any custom A/R report. (4) Need to design processes for the xref2 field to be populated for netting and cash application functions where sap generates the document. This is necessary to display all open items for a subledger account when using report variants that pull data based on the xref2 field contents. (5) Need a report to identify sap generated transactions without data in the xref2 field (6) Residual (netting) transactions have been identified as not having the ability to store xref2 information. A programming change is needed. | (1) see results section (2) no way to prevent report from sorting by profit center per Ranier (3) Multiple search options will work temporarily. It is not acceptable for long term use of the report because information needs to be presented in more ways than can be achieved through SAP functionality. (example: viewing ENA deals for Texas business only). Kris and Melissa White discussed the possibility of having unify populate the text field in the A/P and A/R records with the settlement period. Many changes would have to be made for this to work. (5) A report has been identified that will display only the documents missing data in xref2 field. | R: Tech spec with settlement's requirements was approved by Bryce and forwarded to Rainier 6/19. Emitra's response to the spec was ,"At this time we are not doing an additional custom report, because the AP/AR aging report currently being tested has the information requested that can be retrieved from AP/AR." Emitra asked Rainier to review the current report options with Energy Ops and to determine what needs to be done from there. Rainier, Emitra. Lisa, Bryce, Pam and Kris met 6/23 and discussed reporting needs and feasability of the tech spec. (6) Rena initiated the programming spec change to have xref2 present in residual transactions. The spec was approved. and the change made. AI: (1) Kris to test data in the xref 2 field after the interface occurs. Kris left message with Diana to arrange a time to view interface results. (3)Rainier, Emitra, and Rena are looking into how to provide settlement period (production month) information on the report. (4) Kris to research the process necessary to populate xref2 field for SAP generated documents. Pam and Kris to implement processes to populate xref 2 in netting and cash application procedures.(6) Rena to test the results of the spec change that will allow residual transactions to store xref2 data.
|  | Accounting\Financial Accounting\Accounts Receivable\ Periodic Processing\Info System\Select Report\Information System\Account Information\Days Overdue Analysis (same report/path available in Accounts Payable section). | Breakdown of AB document type by commodity type. Settlement Period - per Business Unit Spec dated 6/21. Profit Center (new business unit requirement-new report). |  | Use summarization level #6 for best format. User can define overdue dates. Use search term criteria to pull customer/vendors by name (A to AZZZZZ for A vendors). Save variant specific to responsibilities. | and cash application procedures.(6) Rena to test the results of the spec change that will allow residual transactions to store xref2 data and let Kris know the results on 6/26.
#7-Past Due A/R Invoices > 60 Days Exluding Invoices Prior to 1/30/99 (for insurance policy) (Needed 8/1) | ZCASH | Accounting\Enron Enhancements\Accounts Receivable\ Cash Management\Accounts Receivable\Customer Invoices\Invoice - Flex Sort | Invoice Flex File from ZCASH - done. | (1) xref2 field needs to be populated for data converted from MSA (2) research needed to determine how best to populate xref2 in sap generated documents |  | R: (1) xref2 to be populated in MSA data conversion. AI: (1) Kris to observe MSA interface results 6/23. (2) Processes and procedures are being developed to populate xref2 for SAP generated transactions. The information will be shared with Bob Klein.
#16-Cash Forecash Report (Detail) (Needed 7/5) | ZCASH | Accounting\Enron Enhancements\Accounts Payable\Cash Management\Cash Flow\Accounts Payable\By Expected Date | Report breakdown by commodity type | (1) Report needs to be sorted by xref2 below the company code level sort. (2) Xref2 field needs to be populated for data converted from MSA | Shawn Franks, zcash programmer, said the changes requested in the spec are simple changes that don't require a great deal of time. No changes can occur in zcash before 7/1, but changes can be made after 7/1 to be available on 7/7. This change has been requested by financial and treasury also. | R: Maura and Kris met to review the new, detailed tech spec that requests forecasting information to be sorted by xref2. (2) xref2 field will be populated for MSA data and SAP generated documents (see aging report for more details) AI: (1) Maura to make small modifications in the spec and send to Kris for review, who will forward to Lisa and Bryce for approval. (2) Kris to observe MSA data interface results (3) Rainier to find out how soon the changes can be implemented after 7/1
#17-Forecasted Invoices by Expected Date (Needed 7/5) | ZCASH | Accounting\Enron Enhancements\Accounts Payable\Cash Management\Accounts Payable\Cash Flow\Accounts Payable\By Expected Date | Report breakdown by commodity type | (1) Report needs to be sorted by xref2 below the company code level sort. (2) Xref2 field needs to be populated for data converted from MSA | Shawn Franks, zcash programmer, said the changes requested in the spec are simple changes that don't require a great deal of time. No changes can occur in zcash before 7/1, but changes can be made after 7/1 to be available on 7/7. This change has been requested by financial and treasury also. | R: Maura and Kris met to review the new, detailed tech spec that requests forecasting information to be sorted by xref2. (2) xref2 field will be populated for MSA data and SAP generated documents (see aging report for more details) AI: (1) Maura to make small modifications in the spec and send to Kris for review, who will forward to Lisa and Bryce for approval. (2) Kris to observe MSA data interface results (3) Rainier to find out how soon the changes can be implemented after 7/1
2025-09-26 22:45
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/ENERGY_OPS_000630.xls'#$Showstoppers

## Sheet1
ENERGY OPS - SETTLEMENTS/VM
REVISED SHOWSTOPPERS STATUS REPORT
2000-06-30
REPORT NAME | ACTION REQUIRED | RESPONSIBLE | DUE DATE
#1-The Matrix-Transaction Detail | 1. Review and sign off on Matrix summary report. | J. Pond, J. Valdes, R. Robinson | COMPLETE
| 2. Show BU users Matrix detail line item solution with VLOOKUPS. | T. Le, R. Cockrell | COMPLETE
| 3. Review and sign off on Matrix detail report | J. Pond, J. Valdes, R. Robinson | 2000-07-07
| 4. If necessary, develop action plan for long term solution for Matrix detail report | S. Chulki, R. Cockrell, T. Le | TBD based on BU comments
#2-G/L Line Item Report (GL 110) | 1. User Acceptance Received |  | COMPLETE
#3-Unify A/R Cash Flow Report- | 1. R. Cockrell sent S. Cook A/R Line Item Upload file. | R. Cockrell | COMPLETE
(Apache Report) | 2. Use upload and create report in Access for BU. | S. Cook | 2000-07-14
#5-A/R and A/P Aging | 1. Develop solution to include xref field in AP/AR aging report
| 1a. Configure posting keys to open fields for xref field for manual population | R. D'Souza, K. Hanson | COMPLETE
| 1b. Explore method for automated population of xref fields and make a recommendation based on findings. | R. D'Souza, K. Hanson | 2000-08-01
2. Develop solution for capturing settlement period and application info on AP/AR aging report
| 2a. Complete design spec for report, determining logic for obtaining and reporting on "Delivery Period" and "Applications (Cash/Net)" | K. Hanson, R. Cockrell, R. D'Souza, S. Chulki | COMPLETE
| 2b. Review netting document types (AB and ZO) and determine if consistent document type is required across business units. Develop action plan as necessary. | K. Cantu | COMPLETE
| 2c. Review and approve A/R Aging spec. | B. Baxter, K. Hanson | COMPLETE
| 2d. Create new document type for account clear. Include XREF fields in document type configuration. | G. Whiting, K. Cantu | 2000-07-05
| 2e. Review and approve A/R Aging spec. | B. Baxter, K. Hanson | COMPLETE
| 2f. Complete A/R report development, testing of report and user sign-off | S. Chulki, K. Hanson, R. Cockrell | 2000-07-21
| 2g. Review and approve A/P Aging spec. | B. Baxter, K. Hanson | 2000-07-05
| 2e. Complete A/P report development, testing of report and user sign-off | S. Chulki, K. Hanson, R. Cockrell | TBD based on receipt of approved report spec
3. Determine tool to manipulate AR/AP data for ad hoc queries.
| 3a. Custom reports will download to Excel in a flat format. Based on 6/30 e-mail from K. Hanson, this request has been dropped from the action items list. | N/A | COMPLETE
#7-Past Due A/R Invoices > 60 Days Excluding Invoices Prior to 1/30/99 (for insurance policy) | 1. Review Invoice Flex Sort file as a tool/report to meet reporting requirements and sign off if acceptable, or develop plan if not acceptable. User acceptance received. | B. Baxter, L. Csikos, K. Hanson | COMPLETE
#16-Cash Forecast Report (Detail) & #17-Forecasted Invoices by Expected Date | 1a. Send completed/revised spec to BU for final approval | M. O'Neil | COMPLETE
| 1b. Review and approve spec | B. Baxter, L. Csikos | COMPLETE
| 1c. SAP to review and approve spec. Provide comments on what can be changed vs. what can't be changed. | P. Lebrane | COMPLETE
| 1d. Determine whether expected date and expected amount data can be added to FLEXSORT report to meet additional sorting requirements | P. Lebrane, M. Leskowitz | 2000-07-05
| 2. Development and unit testing based on on approved BU spec. | S. Franks | 2000-07-06
| 3. Test report and sign off | K. Hanson, J. Smith, M. Leskowitz | 2000-07-12
2025-09-26 22:45
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/ENERGY_OPS_000630.xls'#$Sheet1

## High (hidden)
ENERGY OPS - SETTLEMENTS/VM REPORT LIST
VERY HIGH/HIGH
REPORT NAME | MENU PATH | ENA ISSUES | COMMENTS
Interface Detail Backup A/P Reports (VH) | Accounting\Financial Accounting\Accounts Payable\ Periodic Processing\Info System\Select Report\Information System\Other Analyses\Account\Line Items
Intercompany A/R & A/P (GL 150) | Accounting\Financial Accounting\General Ledger\Periodic Processing\Information System\Report Selection\ Reporting\Enron Custom Reports\General Ledger Reporting\G/L Intercompany Reporting\Intercompany Elimination Report
MSA Consolidated I/S Trial Balance (GL 210) | Accounting\Financial Accounting\General Ledger\Periodic Processing\Information System\Report Selection\ Information System\Balance Sheet/P&L for FI Companies or Accounting\Enterprise Controlling\Consolidation\ Information System\Report Selection\Consolidate Income Statement Drill Down FSI w/Comparison Periods-IS for FI or CS Companies
Various Ad Hoc Queries (DSS)
MSA consolidated Balance Sheet Trial Balance (GL 211)
Unapplied Cash Report | Accounting\Financial Accounting\General Ledger\Account\ Display Line Items
Account Inquiry - AP | Accounting\Financial Accounting\Accounts Payable\ Periodic Processing\Info System\Select Report\Enron Specific Reports\Pay Entity Report (ability to subtotal by vendor and payment method)
Account Inquiry - AR | Accounting\Financial Accounting\Accounts Receivable\ Periodic Processing\Info System\Select Report\Enron Specific Reports\Pay Entity Report (ability to subtotal by customer and payment method)
Cash Deposit Listing by Deposit Date & Counterparty
Forecasted Invoice by Expected Date
Forecast vs Received by Counterparty