## Sheet1
Project No. | Task Order No. | Description | Facility/Location | Approved Budget | Costs to date | Status
166503 | Task Order 005 | Transition Consulting | All | 127000 | 90394.75 | Closed. This was a lump sum project that ENTRIX completed early and under budget. $36,605.25 was returned to EOTT for use on other tasks.
466502 | Task Order 007 | EHS Partnering | All | 442500 | 135000 | Contract is for $45,000 per month through 12/21/2001.
466503 | Task Order 006 | Spill Remediation Planning | All | 210800 | 152019.02
466504 | Task Order 007 | Remediation Planning & Mgmt | Kennan Property/Lea County, NM | 15000 | 9808.12 | Known sites (74 in total)
466505 | Task Order 008 | Remediation Planning & Mgmt | Chickasha, OK | 14072 | 14000 | Risk assessment verbally approved by state,
466505 | Task Order 037 | Remediation Planning & Mgmt | Chickasha, OK | 20000 | 12663.73 | See above
466506 | Task Order 006 | Remediation Planning & Mgmt | Sonora Station, NM | 10000 | 6945.03 | Project waiting EOTT approval
466507 | Task Order 007 | Remediation Planning & Mgmt | McCasland 90-23, NM | 10000 | 754 | Litigation pending, known site
466508 | Task Order 008 | Remediation Planning & Mgmt | Jay Anthony, NM | 10000 | 7895.75 | Project waiting AIG approval
466509 | Task Order 009 | Remediation Planning & Mgmt | Red Byrd Ranch, NM | 10000 | 7185.25 | Multiple sites, project waiting AIG approval
466510 | Task Order 010 | Remediation Planning & Mgmt | D. K. Boyd, NM | 10000 | 3167.5 | More than 100 sites, project pending review of Landowner assessment
466511 | Task Order 011 | Remediation Planning & Mgmt | Kennan 97-23, NM | 10000 | 3072.5 | Litigation pending, known site
466512 | Task Order 012 | Remediation Planning & Mgmt | LF-37 | 10000 | 869 | Waiting on workplan for additional investigation
466513 | Task Order 013 | Remediation Planning & Mgmt | LF-59 (Monument 10") | 10000 | 391 | Waiting on workplan for additional investigation
466514 | Task Order 014 | Remediation Planning & Mgmt | Durham, NM | 10000 | 4760 | Litigation pending, possible source for Cooper contamination
466515 | Task Order 015 | Remediation Planning & Mgmt | Gillette, WY | 10000 | 460 | Investigation complete, work plan approval pending
466516 | Task Order 016 | Remediation Planning & Mgmt | Lea Station, NM | 10000 | 1555.55 | Remediation project underway, landfarm candidate
466517 | Task Order 017 | Remediation Planning & Mgmt | Eunice Booster, NM | 10000 | 203 | Investigation complete, work plan approval pending
466518 | Task Order 018 | Remediation Planning & Mgmt | Eunice Gathering, NM | 10000 | 25 | Remediation project underway
466519 | Task Order 019 | Remediation Planning & Mgmt | Clay Osborne, NM | 10000 | 559 | Multiple historic sites, visual inspection completed May 2000
466520 | Task Order 020 | Remediation Planning & Mgmt | Wright, WY | 10000 | 247.5 | Truck rollover, investigation complete, waiting on state for ok
466521 | Task Order 021 | Remediation Planning & Mgmt | R. L. Rogers, NM | 10000 | 2405 | Additional investigation underway, sidewall contamination
466522 | Task Order 022 | Remediation Planning & Mgmt | Saunders 95-10, NM | 10000 | 1441 | Work plan approved, project in progress
466523 | Task Order 023 | On-site EES Assistance | EOTT, Midland, TX | 10764 | 18278.01 | Rob Card administrative support on site
466524 | Task Order 024 | Remediation Planning & Mgmt | Darr Angel, New Mexico | 10000 | 725 | Three sites, groundwater impacts, more investigation needed
466525 | Task Order 025 | Remediation Planning & Mgmt | Lemunyon Sump, New Mexico | 10000 | 25 | New site, investigation continues
466526 | Task Order 026 | Remediation Planning & Mgmt | S. Mattix, New Mexico | 10000 | 25 | New site, investigation continues
466527 | Task Order 027 | Remediation Planning & Mgmt | Gary Blocker, New Mexico | 10000 | 25 | New site, investigation continues
466528 | Task Order 028 | Remediation Planning & Mgmt | Dickie Wheeler, New Mexico | 10000 | 25 | New site, investigation continues
466529 | Task Order 029 | Remediation Planning & Mgmt | Texaco-Buckeye, New Mexico | 10000 | 25 | New site, investigation continues
466530 | Task Order 030 | Remediation Planning & Mgmt | Lynch, New Mexico | 10000 | 25 | New site, investigation continues
466531 | Task Order 031 | Remediation Planning & Mgmt | Loco Hills, New Mexico | 10000 | 25 | New site, investigation continues
466532 | Task Order 032 | Remediation Planning & Mgmt | Beeson Station, New Mexico | 10000 | 25 | New site, investigation continues
466533 | Task Order 033 | Remediation Planning & Mgmt | Elliott Tank Battery, New Mex | 10000 | 247.5 | Waiting on workplan for additional investigation
466534 | Task Order 034 | Project Mgmt, Tank Database | EOTT, Houston, TX | 4000 | 25 | New site, investigation continues
466535 | Task Order 035 | Planning and Support Services | Cooper v. EOTT, Lea Cty NM | 50000 | 1269 | Litigation pending, new site
466536 | Task Order 036 | Spill Delineation Management | Nechanitz Trkg. Giddings Area 3, La Grange, TX | 15000 | 1280.5 | Truck station overfill, offsite contamination
466537 | Task Order 038 | Remediation Planning & Mgmt | Delrose Scott 98-05 | 10000
466538 | Task Order 039 | Remediation Planning & Mgmt | Delrose Scott 98-05A | 10000
466539 | Task Order 040 | Remediation Planning & Mgmt | June Tippett | 10000
466540 | Task Order 041 | Spill Delineation Management | Midland Tank Farm | 10000
466541 | Task Order 042 | Spill Delineation Management | Sonora Truck Spill | 10000
466542 | Task Order 043 | Spill Delineation Management | Taft Pontap Station Leak, Taft, TX | 10000
466543 | Task Order 044 | Spill Delineation Management | Buster Goff, New Mexico | 10000