## L, T & R
LEGAL, TAX & REGULATORY TEAM
Team Members: Carlos, Andrea, Brent, Lynn, Guillermo, Cristian, Jeff, Michael, Roberto, Bernardo, Patrick
Area | Resolution | Requirements | Accountability | Due Date | Status
LEGAL
| Solve the CNV issue | Decide strategy | Team | 2000-07-18
| Draft Password Agreement |  | Andrea | 2000-08-10
| Draft Electronic Trading Agreement |  | Andrea | 2000-08-10
| Draft GTC for Gas contracts |  | Andrea | 2000-08-15
| Draft GTC for Physical Power contract |  | Andrea | 2000-08-15
| Revise existing ISDA / Master Agreement |  | Andrea | 2000-08-01
| Draft contracts between EOL an each Enron entity |  | Andrea | 2000-08-17
| Draft a sample of a Confirmation Document |  | Andrea | 2000-08-17
| Register all names and intellectual property |  | Counsel, Andrea | 2000-08-17
| Register and set up enrononline.com.ar |  | Counsel, Andrea | 2000-08-17
| Register and set up enron.com.ar |  | Counsel, Andrea | 2000-08-17
| Look into other North American product contracts |  | Andrea | 2000-07-20
| Set up Enron paper company on shore |  | Counsel, Andrea | 2000-08-17
| Establish necessary procedures and rules, in the transaction process for each product (what can we do and what not do, in order to keep in safe legal terms) |  | Andrea, M Taylor, D Forster | 2000-08-17
| Include electronic billing and payment language |  | Andrea | 2000-08-17
Other things to do
| Define the Enron entity for each product |  | Michael, Carlos, Jeff, Houston
| Look at GIRE's services and contract (Passwords) |  | Patrick, Andrea
| Check the exact mechanism of password granting |  | Patrick, Andrea
TAX
| Finish the "White Paper" |  | Team | 2000-07-20
| Pitch Provinces with our tax "White Paper" |  | Team | 2000-07-23
| Secure favorable interpretation of Gross Receipts Tax |  | Team | 2000-09-01
| Secure exemption from Gross Receipts Tax |  | Team | 2000-09-01
REGULATORY
| Solve the CNV issue | Decide strategy | Team | 2000-07-18
| Propose a change in "Lauras" Law project |  | Team | 2000-08-06
| Solve the volume issue for purchasing power |  | Team | 2000-09-01
| Reduce the Term for Power Contracts to 1 month |  | Team | 2000-09-01
| Flexibility to sell Power with different Load Curve |  | Team | 2000-09-01
| Propose and Promote a Natural Gas Index |  | Santiago, Team | 2000-09-01
| Push for Release Capacity and Open Access |  | Team | 2000-09-01
| Test filing procedures with CAMMESA |  | Team | 2000-08-25
| Establish necessary procedures and rules, in the transaction process for each product (what can we do and what not do) |  | Carlos, Team | 2000-09-01
| Define needed power reg changes decreased declaration period |  | Team | 2000-07-20
| Define needed power reg changes Increased flexibility |  | Team | 2000-07-20
| Establish a spot index via Publication or Govt. body |  | Team | 2000-07-20
| Interconnect with Cammesa filling procedure |  | Team | 2000-09-01
Other things to do
| IAPG presentation of Derivatives |  |  | 2000-07-27
IIR conference on Energy Markets
Other lobbying activity
PUBLIC RELATIONS
| Roll Out |  |  | 2000-09-01
| Promotion, advertisement |  |  | 2000-09-01
| Argentina Web Page |  |  | 2000-08-20

## Commercial
COMMERCIAL TEAM
Team Members: Michael, Carlos, Jeff, Rolo, Julian, John, Mario, Santiago, Bernardo, Patrick, Paul Radous
Area | Resolution | Requirements | Accountability | Due Date | Status
TRADING
| Learn about EOL applications | work with Houston | Patrick, Traders | 2000-07-21
| Passwords for test enviroment |  | Houston | 2000-07-21 | Done
| Training on Stack Manager |  | Traders | 2000-08-11
| Test the Power and Gas curves (Power Model) |  | Traders | 2000-08-25
| Simulation of EOL |  | All | 2000-08-25
| Determine Trading limits (monthly, intra-date, other) |  | Michael, Jeff | 2000-08-11
| Determine the Product Control Group |  | Michael, Jeff | 2000-08-11
| Determine other operating procedures, limits and responsibilities |  | Michael, Jeff | 2000-08-11
| Determine who are going to be the backup persons for each trader. |  | Michael, Jeff | 2000-08-11
| Trader in Houston if Financial Products are off-shore |  | Michael, Jeff | 2000-08-11
| Gather financials and other information from potential customers |  | Traders | 2000-09-01
| Start marketing to our clients the products we want to quote in EOL. We need to get them familiar with trading standardized products |  | Traders | Today
| Impliment new gas model |  | Traders | 2000-08-25
| Impliment new power model |  | Traders | 2000-08-25
| Establish client training program EOL workshops |  | Traders | 2000-08-25
SIMULATION
| Full Simulation Objectives to be developed |  | All | 2000-08-25
| Full Web Latency testing |  | All | 2000-08-25
| Full Stack Management |  | All | 2000-08-25
| Full bridging test - all products / traders / controls |  | All | 2000-08-25
| Trader Position Keeping - Inter and Intra Day |  | All | 2000-08-25
| Dynamic Trading - multiple hits / rapid hits |  | All | 2000-08-25
| Managing counter offers for partial volume |  | All | 2000-08-25
| Trade capture |  | All | 2000-08-25
| Setting up new Products |  | All | 2000-08-25
| Multiple traders on same logon |  | All | 2000-08-25
| Credit Management |  | All | 2000-08-25
| Trade Tenure Management |  | All | 2000-08-25
| Trader Limit Management |  | All | 2000-08-25
| Crisis Management |  | All | 2000-08-25
CREDIT
| Gather financials from customer and other data |  | Traders, Mariana
| Houston determine credit limit or collateral request |  | Paul Radous
| Fluid contact Trader-Client and Trader-Houston |  | Traders, Mariana
| Determine procedure and controls for new clients |  | Houston
| Establish interactive Credit Report |  | All
MARKETING
| Brochures from Houston |  | Monica Talan | 2000-07-28
| Local Web Page |  | Houston | 2000-09-01
| Determine a Plan to approach customers |  | Team | 2000-08-04
| Prepare customized presentations |  | Team | 2000-08-11
| Set up simulation and training desk in-house |  | Team | 2000-08-25
| Invite customers to see EOL working |  | Traders | 2000-08-25
| Get clients to sign ISDA's or Master Agreements |  | Traders | 2000-09-01
| Survey of market needs for products (which commodity, what volumes, delivery points, other) |  | Team
Other suggested activities
| System in spanish |  | Houston
North American Products
| Set up North American Products |  | Houston, BA | 2000-08-04
| Agree on cost coverage with North America |  | Houston, BA | 2000-08-04
| Set up North American Product monitoring |  | Houston, BA | 2000-08-04

## Back-Office
BACK-OFFICE TEAM
Team Members: Scott, Julie, Ariel, Rolo, Julian, Michael, Patrick
Area | Resolution | Requirements | Accountability | Due Date | Status
IT
| Increase Bandwidth | Sao Paulo | Julie, Steve | 2000-07-28
| Install Citrix in traders hardware |  | Ariel | Today
| New hardware (Monitors, other stations) |  | Ariel, Julie | 2000-08-25
| Record of Transactions |  | Houston | 2000-08-25
| Test connection efficiency during Simulation period |  | Julie, Ariel | 2000-08-25
PASSWORD CONTROL
| Which is the process and procedures |  | Houston | 2000-08-25
| Control group |  | Houston | 2000-08-25
| Legal signoff |  | Houston | 2000-08-25
TRADING ACCOUNTING
| Sitara installed and population |  | Scott, Team
| EnPower installed and population |  | Scott, Team
| Bridging complete |  | Scott, Team
| Test bridging during Simulation period |  | Scott, Team
| Trade capture |  | Scott, Team
| Trade allocation between traders |  | Scott, Team
| Credit Monitoring |  | Paul, Team
| Position keeping |  | Scott, Team
FINANCIAL ACCOUNTING
Billing
Mark to Market
Electronic billing

## Prod. Alt.
EOL - PLATFORM IMPLEMENTATION
| IT | Trader | Legal | Regulatory | Tax | Back Office
| Increase Bandwidth | Product Manager Population | Solve the CNV issue | Solve the CNV issue | White Paper for Tax exemption | Financial Accounting
| Install Traders Applications | Stack Manager Population | Password Agreement | Filing Automization |  | Trading Accounting
| Install Back Office Applications | Simulation | Electronic Trading Agreement | Push for an Open Market |  | Password Granting
| Help Desk | Product Control Group | Service Agreements Ilustrate separation
EOL - PRODUCT ALTERNATIVES
| EOL | Trader | Legal | Regulatory | Tax | Commercial
| Platform |  |  |  |  | Size | Interest
Natural Gas City Gate (forward & spot) | OK | Rodolfo Freyre | YES | OK | Gross Receipt | Big | Big
| September 1 | TBA |  | Required changes: | Stamp Tax
|  |  | GTC - Master Agreement | For volume purposes we need to get: Release Capacity and Open Access | VAT | Generators, Industrials, Commercial, Other
Natural Gas Well Head (forward & spot) | OK | Rodolfo Freyre | YES | OK | Gross Receipt | Small | Small
| September 1 | TBA |  | Required changes: | Stamp Tax | YPF monopoly
|  |  | GTC - Master Agreement |  | VAT
Power Physical Ezeiza (forward) | OK | Julian Poole | YES | NO | Gross Receipt | Big | Big
| September 1 | TBA |  | Required changes: | Stamp Tax
|  |  | GTC - Master Agreement | We need changes in volume, term and curve of each contract. | VAT | Generators, Industrials, Commercial, Other
Power Financial BA (swap) | OK | Julian Poole | NO | OK | Gross Receipt | Big | Big
| September 1 | TBA | Required changes: | Required changes: | Stamp Tax
|  |  | The Argentine Bankruptcy law should change |  | VAT
Power Financial Houston | OK | TBA Houston | Yes | No Argentine Regulation | No - Gross Receipt | Limited | Limited
| September 1 |  | All counterparties Off-Shore | ISDA | No - Stamp Tax
|  |  | ISDA signed |  | No - VAT
LPG Index Houston | OK | TBA Houston | Yes | No Argentine Regulation | No - Gross Receipt | Limited | Limited
| September 1 |  | All counterparties Off-Shore | ISDA | No - Stamp Tax
|  |  | ISDA signed |  | No - VAT
Fuel Index Houston | OK | TBA Houston | Yes | No Argentine Regulation | No - Gross Receipt | Limited | Limited
| September 1 |  | All counterparties Off-Shore | ISDA | No - Stamp Tax
|  |  | ISDA signed |  | No - VAT
Other Internationaly traded Commodities | OK | TBA Houston | Yes | No Argentine Regulation | No - Gross Receipt | Limited | Limited
| September 1 |  | All counterparties Off-Shore | ISDA | No - Stamp Tax
|  |  | ISDA signed |  | No - VAT