## calendar
| MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER
| 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
Communications Plan
Select ESES spokesperson
Draft press/information kit
Issue press release to announce ESES
Target launch website
Ongoing press briefings
Third party presentation for client approval
Ongoing third party outreach
Compile list of analysts/institutional investors
Analyst cover letter to client for approval
Analyst mailing
Introductions of IPPNY and SS+K
Ongoing coordination with IPPNY
Survey in field
Release survey findings (June 21)
Begin planning panel discussion event
Panel discussion
ESES to provide schedule of speaking engagements
SS+K to begin identifying and booking other speaking opp's
Stump speeches for client approval
Crisis statements for client approval
| MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER
| 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
Advertising Plan
Brief creative team
Write radio spot
Develop creative for print ad
Review radio spot and creative for print internally
Submit radio and print to client
Client comments on radio and print
Submit revised radio spot and print ad
Client approval for radio spot and layout/copy for print ad
Client comments on proof for print ad
Purchase space for radio spot and print ad to run in Week 6
Find talent and book studio for radio spot
Record radio spot, edit and secure client approvals
Run radio and print