## Expands
ENRON NORTH AMERICA |  |  |  | 2025-09-26 23:09 |  | expands2
PIPELINE EXPANSION UPDATE
Project
[5 empty] | Daily | Start |  | ECT |  |  | Term | Cost of
| Pipeline |  | Project | Path | Quantity | Date | Probability | Position | Docket | Pricing | Years | Project | Miles | HP
Northeast:
| Iroquois |  |  | Waddington to S. Comack | 35000 | 1996-11-01 | Done | 15000 | NA |  | 10
| National Fuel |  |  | Niagara to Leidy | 25000 | 1997-11-01 | Done | 25000 | CP96-671 |  | 10 | 10600000 |  | 1300
| Tennessee |  | Niagara Expansion | National Fuel Compressor Expansion | 21344 | 1997-11-01 | Done |  | CP96-721 |  |  | 51620
| Transco |  | Pocono Expansion Project | Leidy to Northhampton County, PA | 35000 | 1997-11-01 | Done |  | CP97-328 |  | 15 | 9800000
| Vermont Gas Systems |  |  | Import at Highgate Springs, Vermont | 52000 | 1997-11-01 | Done |  | CP97-324
| CNG Transmission |  | Market Value Project | Lebanon to Leidy and CNG Citygates | 400000 | 1998-11-01 | Dead
| Iroquois |  | Athens | Waddington to Brookfield | 30160 | 1998-11-01 | Done |  | CP96-687 |  | 10 | 22000000 |  | 9500
| National Fuel |  | Son of Seaboard | Niagara to Leidy | 100000 | 1998-11-01 | Dead
| Tennessee |  | DOMAC Expansion | DOMAC Everett Plant to Saugus, Mass | 90000 | 1998-11-01 | Done |  | CP96-194 |  |  | 25900000 | 8
| Texas Eastern |  | Spectrum Related | Lebanon Lateral Expansion | 302290 | 1998-11-01 | Done |  | CP98-336 |  |  | 31000000 |  | 17070 | (Gas City and Glen Karn)
| Portland/Maritimes |  | Joint Line Application |  |  | 1999-02-01 | Done |  | CP97-238 |  |  | CP96-178 ???
| Algonquin |  | EMI Dighton, MA Plant | Delivery off mainline to Dighton Plant | 33000 | 1999-03-01 | Done |  | CP98-99 |  |  | 5000000 | 2 | 850
| Portland Natural Gas Transmission |  | Granite State PL replacement | TCPL to Tennessee at Haverhill, Mass. | 178000 | 1999-03-01 | Done | 30000 | CP96-248 |  | 15-20 | 270000000 | 243
| Algonquin LNG |  | Providence, RI tie to Algonquin | Northeast City Gates (currently 100,000) | 150000 | 1999-11-01 | Done |  | CP96-517 |  | 30 | 75700000
| Duke Energy |  | Spectrum | Chicago to New Jersey | 500000 | 1999-11-01 | Dead |  | CP97-626
| National Fuel |  | Grandson of Seaboard | Niagara to Leidy | 400000 | 1999-11-01 | Dead
| National Fuel |  | Ellisburg compression | Ellisburg to Leidy, PA | 60919 | 1999-11-01 | Done |  | CP99-160 |  |  | 223600
| Portland Natural Gas Transmission |  | TQM Link | TQM from Sable Island to Dracut, Mass | 350000 | 1999-11-01 | Dead |  | CP96-249
| Tatham Offshore (Leviathon) |  | North Atlantic Pipeline Project | Hibernia/Sable Island to New England | 250000 | 1999-11-01 | Dead |  | CP98-29/30/31/32
| Tennessee |  | Ellisburg Extension (me too) | Niagara to Leidy | 250000 | 1999-11-01 | Dead
| Tennessee |  | Eastern Express | Chicago to Leidy | 500000 | 1999-11-01 | Dead
| Maritimes & Northeast |  | Sable Island Phase I | Wells, Maine to Dracut, MA (flows backwards) | 60000 | 1999-12-01 | Done |  | CP96-178 |  |  | 103726000
| Maritimes & Northeast |  | Sable Island Phase II | Sable Offshore Energy Int. to Dracut, Mass. | 360000 | 1999-12-01 | Done |  | CP96-809 |  |  | 79217000 | 454 | 31160
| Algonquin |  | EMI Tiverton Plant | Compressor Upgrades & mainline work | 46000 | 2000-04-01 | Done |  | CP99-46 |  |  | 13900000 | 17
| Texas Eastern |  | Duke Vermillion Lateral | Midwestern PL to the plant (Cayuga) | 200000 | 2000-06-01 | High |  | CP 00-67 |  |  | 13000000 | 14
| Maine Natural Gas |  | Westbrook Lateral | MN&E to the Calpine Westbrook Plant | 100000 | 2000-07-01 | High
| Algonquin |  | Lake Road Plant | Compressor Upgrades & mainline work | 146000 | 2000-08-01 | Done
| Tennessee |  | Honeoye Storage Expansion | 1.8 Bcf increase in working gas | 15000 | 2000-08-01 | Low |  | CP00-93 |  |  | 3000000
| Maritimes & Northeast |  | Gorham Lateral |  | 160000 | 2000-09-01 | Done |  | CP98-724 |  |  | 2000000 | 1
| TETCO |  | AES Ironwood Plant Lateral | Lateral in TETCO M3 (PA) | 120000 | 2000-09-01 | Done | 20 yr | CP99-621 |  |  | 5700000
| Algonquin |  | ANP Bellingham Lateral |  | 110000 | 2000-10-01 | Done |  | CP98-100 |  |  | 4600000 | 1
| Continental States Peaking Svs |  | El Paso/Tennessee/MCN | Maryland/Delaware LNG 2.0 Bcf MSQ | 200000 | 2000-11-01 | Dead |  |  |  |  | 45000000
| Granite State |  | Wells LNG | Portland/Northern Utilities 2.0 Bcf MSQ |  | 2000-11-01 | Dead |  | CP96-610 |  | 20 | 44221000
| Iroquois/Tennessee |  | EPEM/PDC Milford Plant | Waddington to Milford/Tenn Zone 6 Delivery | 35000 | 2000-11-01 | High
| Maritimes & Northeast |  | Veazie Lateral |  | 124000 | 2000-11-01 | Done | [5 empty] | 77
| Maritimes & Northeast |  | Halifax Lateral | NS Power Tufts Cove Plant | 166000 | 2000-12-01 | Done | [5 empty] | 63
| Maritimes & Northeast |  | St John Lateral | JDI & NB Power Bayside Power Station | 105002 | 2001-01-01 | Med |  | CP98-799 |  |  | 6000002 | 3
| Maritimes & Northeast |  | Phase III | adds Beverly MA as another Delivery Point | 360000 | 2002-11-01 | Med |  | CP01-4 |  |  | 134000000 | 24
| TCPL/St. Clair Pipeline |  | Lake Erie Crossing Pipeline | 7 shippers | 650000 | 2000-11-01 | Med |  |  |  |  | 106000000 | 60
| Tennessee |  | Eastern Express 2000 | Dracut to New England | 288000 | 2000-11-01 | Done |  | CP99-262 | rolled in |  | 28000000 |  | 13320
| TETCO |  | Independence/ML Substitute | ANR/Muncie to Linden, NJ | 663000 | 2000-11-01 | Low
| TETCO |  | Excelsior | New Jersey to New York | 500000 | 2000-11-01 | Dead
| Texas Eastern |  | Enhanced Spectrum | Chicago Alliance to M3 | 55000 | 2000-11-01 | High |  |  | 0.46
| NGPL |  | New York | Chicago to New York |  | 2000-12-01 | Dead
| Maine Natural Gas |  | Brunswick Lateral | MN&E to Brunswick and Topsham | 50000 | 2001-08-01 | High |  |  |  |  | 10000000 | 18
| Tennessee |  | Stagecoach Lateral | Central New York - Tennessee Line 300 | 500000 | 2001-08-01 | High | FEIS rcvd | CP 00-65 |  | 10 |  | 23.7
| Algonquin/MNE |  | Sithe Energy Lateral | Lateral from Canton, MA to Plant (Fore River) | 140000 | 2001-09-01 | Done |  | CP 00-34 | AFT-CL | 20 | 32020000 | 7.4
| Maritimes & Northeast |  | Four Rivers Plant |  |  | 2001-09-01 | Med
| Tennessee |  | Concord Lateral/AES Loundonderry | Dracut to Loundonderry, NH 20" replacement | 130000 | 2001-10-01 | Done |  | CP 00-48 |  | 20 | 32400000 | 19
| CNG/Tennessee |  | Atlantic Advantage Project | Chicago/Niagara to the Northeast | 750000 | 2001-11-01 | Med
| Duke Energy/Williams/Iroquois |  | Lighthouse Pipeline | Long Island to Milford, CT | 350000 | 2001-11-01 | Dead |  |  |  |  | 240000000
| Iroquois |  | Vermont Extension | EDC Bennington & Rutland Plants | 250000 | 2001-11-01 | Dead |  |  |  |  | 105000000 | 70
| Transco |  | MarketLink Phase I | Leidy to New York City | 166000 | 2001-11-01 | Done |  | CP98-540 |  |  | 123300000 | 60.6 | 30000
| TETCO |  | Phildelphia Lateral Expansion | Liberty Plants (Columbia and PG&E) | 84000 | 2002-01-01 | High |  | CP00-404 |  | 14.5 |  | 1 | 4000
| DOMAC |  | Sithe Mystic Plant Expansion | 4 submerged combustion vaporization units | 280000 | 2002-05-01 | High |  | CP00-447
| Algonquin |  | HubLine | Plaistow, NH (M&NE) to Algonquin | 300500 | 2002-11-01 | Med |  | CP01-5 |  |  |  | 70
| Columbia Gas/CMS/MCN/Westcoast |  | Millennium | Chicago to New York City | 650000 | 2002-11-01 | Low |  | CP98-150 |  |  | 678000000 | 443
| Iroquois |  | Eastchester Bay Marine Ext Proj | Waddington to Eastchester (ConEd) | 220000 | 2002-11-01 | Med | None | CP00-232 | rolled in | 10-30 | 170808000 | 30.3 | 58300
| Transco |  | MarketLink Phase II | Leidy to New York City | 130000 | 2002-11-01 | Done |  | CP98-540 |  |  | 119600000
| Transco/ANR/National Fuel |  | Independence Pipeline | Chicago to Leidy | 946500 | 2002-11-01 | High | 30000 | CP97-315/320/321 |  |  | 677900000 | 400 | 60000
| Duke Energy/Williams/Keyspan |  | Cross Bay Pipeline | Transco/TETCO in NJ to JFK Airport | 125000 | 2002-12-01 | Low |  | CP00-412-414 |  |  | 59500000 | 44 | 16000
| Transco |  | MarketLink Phase III | Leidy to New York City | 432000 | 2004-11-01 | Med |  | CP98-540
| MHP |  | Tioga Storage Facility (PA) | 5.0 Bcf working gas capacity | 1500000 | 2004 | High
| National Fuel |  | Distribution Company |  | 30000
| Tennessee |  | CanEast | Niagara to Leidy via CNG lease | 250000
| Transco |  | Seaboard 97 (or so) | Leidy to New York City | 115000 |  | Dead | 30000 | CP96-545 |  | 15-21 | 117700000
Southeast:
| Transco |  | Southeast Mainline Exp I | Stn 85 to Stn 150 NC | 35000 | 1994-11-01 | Done |  | CP94-68
| Transco |  | Southeast Mainline Exp II | Stn 85 to Stn 150 NC | 115000 | 1995-11-01 | Done |  | CP94-109
| Southern |  | North System | North System to Chattanooga | 25000 | 1996-11-01 | Done |  | CP94-682
| Transco |  | Southeast Mainline Exp III | Stn 85 to Stn 150 NC | 50000 | 1996-11-01 | Done |  | CP94-109
| East Tennessee |  | System Wide | Knoxville Area | 31902 | 1997-11-01 | Done |  | CP96-696 |  | 3-10 | 12915473
| South Carolina Pipeline |  | New compressor - Blacksburg | Increase Transco takeaway | 75000 | 1997-11-01 | Done |  | Non-Jurisdictional |  |  | 10000000
| Southern |  | Zone 3 Markets | MS/AL Loops - Wren/Savannah Line | 45880 | 1997-11-01 | Done |  | CP96-541 |  | 10 | 36043000 | 28 | 10640
| Transco |  | SunBelt | 100 Stn 65 to Stn 85, 146 Stn 85 to Stn 145 NC | 145666 | 1997-11-01 | Done |  | CP96-16 |  | 20 | 85000000 | 15 | 30000
| Transco |  | Maiden Lateral | Expansion to Piedmont | 69000 | 1997-12-01 | Done |  | CP97-193 |  |  | 13200000 | 18
| East Tennessee |  | Virginia Expansion Project | Greenbriar, TN to Chilhowie & Roanoke, VA | 10300 | 1998-11-01 | Done | Roanoke Gas | CP98-40 |  | 20 | 8600000 | 10
| Southern |  | Zone 2 and 3 Markets | MS/AL Loops | 64911 | 1998-11-01 | Done |  | CP97-526 |  | 12 | 52179005
| Transco |  | Cherokee Expansion | Stn 85 to Stn 130 Madison Co., GA | 87070 | 1998-11-01 | Done |  | CP97-331 |  | 15 | 68000000 | 15 | 23000
| Southern |  | Zone 2 Markets | Alabama Power | 34925 | 1998-12-01 | Done |  | CP97-526 | Increm | 12 | 52179005
| Pine Needle LNG |  | Transco/Piedmont | North Carolina Peaking 4 Bcf MSQ | 400000 | 1999-11-01 | Done |  | CP96-52 |  | 20 | 107000000
| Transco/PSNC/Piedmont/NCNG |  | Cardinal Extension Co. | Stn 160 Rockingham, NC to Burlington, NC | 140000 | 1999-11-01 | Done |  | Non-Jurisdictional |  |  | 98300000 | 67
| Southern |  | North Alabama PL Exp | N. Alabama to Huntsville (Alatenn Bypass) | 76350 | 2000-01-01 | Done |  | CP96-153 |  |  | 66800000 | 118 | 6300
| ANR |  | LS Power Batesville lateral | Panola, MS to Tennessee 20" | 235000 | 2000-06-01 | Done |  | CP98-801 |  |  |  | 15
| Tennessee |  | LS Power Batesville lateral | Panola, MS to Tennessee | 216000 | 2000-06-01 | Done |  | CP98-770 |  |  |  | 3
| Transco |  | Cumberland Pipeline | Walton Co., GA to Chattanooga, TN | 450000 | 2000-11-01 | Dead |  |  |  |  | 115000000 | 141
| Transco |  | Cumberland Pipeline II | Walton Co., GA to Chattanooga, TN | 220000 | 2000-11-01 | Dead
| Transco |  | SouthCoast | Stn 85 to Zone 4 points north of Atlanta, GA | 204999 | 2000-11-01 | Done | PD recvd | CP99-392 | Southern Co 40,000/d | 15 | 108000000 | 44 | 31500
| Columbia Gulf |  | Baxter Wilson & Warren Power | Warren Co., MS | 285000 | 2001-05-01 | High
| Florida Gas Transmission |  | Phase IV | Central and South Central Florida | 272000 | 2001-05-01 | High | PD recvd | CP99-94 |  | DEIS | 351000000 | 205 | 48570
| CP&L |  | Iredell-Richmond Pipeline | Transco Stn 150 (Sundance) to CP&L Richmond Co | 200000 | 2001-06-01 | Med |  |  |  |  | 100000000 | 82
| Petal Gas Storage |  | Hattiesburg Storage Lateral | Hattiesburg,MS to Destin, Koch, Sonat & Transco | 700000 | 2001-06-01 | Done |  | CP00-59 |  |  |  | 5.5 | 35000
| Reliant Energy Gas Transmission |  | Pine Bluff Plant Lateral (Skygen) | Jefferson Co, AR (Line AC) | 40000 | 2001-06-01 | High | Skygen | CP00-137 |  | 10 | 1500000 | 2
| Southern Natural Gas |  | Wrens Compression Upgrade | Improve flow on Wrens/Savannah Line |  | 2001-10-01 | Med |  | CP00-231 |  |  |  |  | 3500
| ANR |  | Mountaintop | Brownsville Compressor to Altanta, GA | 500000 | 2001-11-01 | Low
| East Tennessee |  | Rocky Top Expansion | Greenbriar, TN to Chilhowie & Roanoke, VA | 27500 | 2001-11-01 | Done |  | CP00-51 |  | 10 | 21000000 | 15
| MCN/Col Gulf |  | Volunteer Pipeline | Chicago (via Midw) to Atlanta | 250000 | 2001-11-01 | Low |  |  |  |  | 160000000
| Southern/AGL |  | Etowah LNG | Polk County, Georgia 3 Bcf | 450000 | 2001-11-01 | Med |  | CP98-363 |  | 20
| Florida Gas Transmission |  | Phase V | Plant Smith and Sanford Plant | 428000 | 2002-04-01 | High |  | CP00-40 |  |  | 466000000 | 191 | 125215
| Panda |  | Trans-Union Interstate Pipeline | Claibourne Parish, LA to Arkansas Plant | 400000 | 2002-04-01 | Done |  | CP00-47 |  |  | 41000000 | 41.7
| Southern LNG |  | Elba Island LNG Terminal | 4 Bcf Capacity | 330000 | 2002-04-01 | High | PD recvd | CP99-579 |  |  | 26200000
| Southern/CP&L |  | Palmetto Interstate Pipeline | SoNat system expansion and extension from Aiken, SC to Robeson CO, NC (NCNG) | 250000 | 2002-04-01 | Dead |  |  |  |  | 450000000 | 175
| Transco |  | Sundance Pipeline | Station 65 to North Carolina (CP&L) | 236383 | 2002-04-01 | Med | PD recvd | CP00-165 | Incremental | 15 | 134674037 | 421 | 41225
| Transco/Duke (Formerly Coastal) |  | Gulfstream | Mobile, AL to West Palm Beach, FL | 1100000 | 2002-06-01 | Med |  | CP00-6 |  |  | 1600000000 | 744
| East Tennessee |  | Patriot Extension | Virginia to North Carolina (Transco) | 200000 | 2002-11-01 | Med |  |  |  |  | 215000000 | 95
| FGT/El Paso |  | Cypress | Elba Island LNG to FGT Jacksonville | 300000 | 2003-04-01 | Med
| Transco/Duke |  | Buccaneer Pipeline | Station 82 to north of Tampa Bay | 900000 | 2003-04-01 | Dead |  | CP00-14 |  |  | 1423879951 | 674 | 75000
| Transco |  | Momentum Expansion Project | Station 65 to Station 165 Virginia | 250000 | 2003-05-01 | Med
| Southern Natural Gas |  | South System Expansion | Phase I Loop from MS to GA/Phase II Loop from MS toAL | 335800 | 2003-06-01 | Med |  | CP00-233 |  |  | 147000000 | 73 | 34000
| Scana |  | Carolinas Pipeline | South Carolina (Elba) to North Carolina (Pembroke) | 250000 | 2003-11-01 | Low |  |  |  |  | 1780000000
| Dominion |  | Greenbriar Pipeline | Charleston WV to Transco Rockingham, NC | 250000 | 2005-06-01 | Low |  |  |  |  | 400000000 | 200
| Florida Gas Transmission |  | Phase VI | Bayside Plant
| Scana |  |  | Rockingham, NC
| Southern Natural Gas |  | AL/GA Expansion |  | 17000 | 2001-11-01 | Med |  | CP01-35 |  |  | 6000000 | 7
| Bay Gas |  | Mobile County Expansion |  |  | 2001-06-01 | Med | [5 empty] | 18
Texas/OK to Louisiana:
| Sabine |  |  | HPL to Henry | 30000 | 1996-12-01 | Done
| Delhi |  | East Texas Cotton Valley | Pinnacle Reef Gathering Capacity | 275000 | 1997-04-01 | Done |  | Non-Jurisdictional
| Valero |  | Texas Expansion I | Bethel - Pinnacle Reef to Carthage Hub | 250000 | 1997-07-01 | Done |  | Non-Jurisdictional |  |  | 11700000
| Southern |  | N. Louisiana | Texas to Louisiana |  | 1997-11-01 | Dead
| Ozark |  |  | Oklahoma to Louisiana | 185000 | 1997-11-01 | Dead
| Trunkline |  |  | Katy to Henry | 250000 | 1997-11-01 | Dead
| Florida Gas Transmission |  |  | Texas to Louisiana |  | 1997-11-01 | Dead
| NGPL |  | Louisiana Line Expansion | Compression | 63000 | 1997-11-01 | Dead |  | CP96-720 |  | 7 | 4300000
| NGPL |  |  | Arkoma to Henry | 125000 | 1997-12-01 | Dead
| Valero |  | Texas Expansion II | Bethel - Pinnacle Reef to Carthage Hub | 200000 | 1998-06-01 | Dead |  | Non-Jurisdictional
| Noram |  | North Louisiana Expansion | Carthage to Perryville Hub | 170000 | 1998-11-01 | Done | UPRC 50/Amoco 15 | CP97-724 |  | 10/5 | 32200000
| Koch Gateway |  | East Texas | Carthage to Perryville | 250000 | 1998-11-01 | Dead |  |  |  |  | 31000000
| ANR |  | Katy Project | Katy to Eunice | 200000 | 1999-11-01 | Dead
Onshore Louisiana/Texas:
| Southern Natural Gas |  | TOCA Expansion |  |  |  | Done |  | CP95-500
| Southern Natural Gas | 1 | Lease of Capacity by Destin | Destin delivery into SoNat to TETCO Cranfield | 200000 | 1998-09-01 | Order disallowed roll-in |  | CP96-655 |  | 20
| Koch Gateway Pipeline |  | Venice Expansion | Venice to Koch Mainline | 615000 | 1997-11-01 | Done |  | CP96-572 |  |  | 20500000
| Venice Gathering System LLC |  | Venice Expansion |  | 328000 | 1998-11-01 | Done |  | CP97-533/534 |  |  | 40000000 | 52
| Texas Gas Transmission |  | Carthage Expansion | Haughton Comp Stn to Bossier Parish, LA | 105000 | 1998-11-01 | Done | UPRC | CP97-656 |  | 10 | 5980000 |  | 4600
| Mid Louisiana |  | Baton Rouge Expansion | Transco Station 61 to Baton Rouge | 60000 | 1998-10-01 | Low
| Columbia Gulf |  | Mainline 99 | Rayne to Leach (3 compression upgrades) | 315000 | 1999-12-01 | Done | 27%LDC/63%Mktg/10%Indust |  |  |  | 38000000
|  |  |  | (270,000 11/99 & 45,000 11/2000) |  |  |  |  | CP98-596 | rolled in
| Columbia Gulf |  | Onshore Louisiana | Eastern Legs to Rayne (3 phases) | 400000 | 1998-11-01 | Dead
| Reliant |  | SWEPCO Wilkes Plt Extension |  | 100000 | 2000-06-01 | Done | [5 empty] | 18
| Trunkline |  | Centennial Project | 720 miles of 26" line (chicago to gulf) | -255000 | 2001-12-01 | Low |  | CP00-114 |  |  | -10200000
|  |  | Liquids line conversion | Longville, LA to Bourbon, IL
| Gulf States Pipeline |  | Panda El Dorado Plant | Expansion from the Sharon La tie-in to TGP |  | 2002-06-01 | Med
| Tennessee |  | Panda El Dorado Plant | Interconnect |  | 2002-06-01 | Med
| Trans-Union Interstate Pipeline |  | Panda El Dorado Plant | Gulf States Pipeline to the El Dorado Plant | 430000 | 2002-06-01 | Med | [5 empty] | 42
Deep Water Louisiana:
| Stingray Pipeline Company |  | Garden Banks 72/VER Blocks | GB 72 to Stingray at VER 362 lateral | 100000 | 1995-11-01 | Done |  | CP96-91 |  |  | 9000000 | 15
| Mississippi Canyon Gath System |  | Shell (Mars, Ursa, Mensa) | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 600000 | 1996-09-01 | Done |  | CP96-159 |  |  | 75000000 | 45
| Garden Banks Pipeline |  | Shell/Hess (Ench/Auger/Bladpate) | GB 128A (Enchilada) to SMI 76 (BlueW/TRCO) | 600000 | 1997-04-01 | Done |  | CP96-679 |  |  | 108000000 | 50
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | GC 65 (Bullwinkle) to Ship Shoal 207 (Nautilus) | 300000 | 1997-12-15 | Done |  | CP96-796
| Nautilus Pipeline |  | Shell | SS 207 to South Bend, LA (Troika) to ANR | 600000 | 1997-12-15 | Done |  | CP96-790/791/792 |  |  | 121000000 | 101
| Discovery Gas Transmission |  | Texaco/MAPCO/British Borneo (Hardy/Allegheny/Morpeth) | ST 200, GI 115 & EB 873 to Larose, LA | 600000 | 1998-01-01 | Done |  | CP96-712 |  |  | 300000000 | 147
| Dauphin Island Gath System |  | Phase I | Main Pass 225 to AST 73 | 200000 | 1998-04-01 | Done |  | CP97-301 |  |  | 54000000 | 63
| Trunkline |  | SS Block 139 Compression | SS 139 to Patterson (upstream of constraints) | 500000 | 1998-05-01 | Done |  | CP97-105 |  |  | 52217940 |  | 28950
| Transco |  | Mobile Bay Extension | Main Pass 261 to Mobile Bay 822 to Stn 82 | 350000 | 1998-08-01 | Done | WESCO | CP97-92 |  | 15 | 120200000 | 77 | 30000 | Totally in-service on Nov. 9
| Transco |  | Mobile Bay Expansion | Station 85 | 128137 | 1998-08-01 | Done |  | CP97-93
| Destin Pipeline Svs Company |  | Shell/Amoco | MP/VK to Pascagoula Area (VK 915 Marlin) | 1000000 | 1998-09-01 | Done |  | CP96-655 |  |  | 308000000 | 210 | 26400
| Dauphin Island Gath System |  | Phase II | Alabama State Tract 73 to Transco/Colden, AL | 300000 | 1998-10-01 | Done |  | CP98-6 |  |  | 19000000 | 13
| Tennessee/Leviathon |  | Viosca Knoll Expansion | Looping of existing VK Line (Bi-flow) | 250000 | 1998-11-01 | Done
| Transco |  | Mobile Bay Expansion II | Station 85 | 135711 | 1998-11-01 | Done |  | CP97-94
| Transco |  | Genesis Field | Green Canyon 205 to Transco Ship Shoal | 72000 | 1999-02-01 | Done |  | Non-Jurisdictional
| Mississippi Canyon Gath System II |  | Compression upgrades | WD 143 to Venice (TETCO/Koch/SNG/CGLF) | 200000 | 1999-07-01 | Done |  |  |  |  | 216000
| Transco |  | SE Louisiana Crossover | Garden Banks PL @ SMI 76 to Station 50 | 264020 | 1999-09-01 | Done | at risk | CP99-76 |  | Hess | 80000000 | 53
| Transco |  | SE Louisiana Crossover | SMI 76 to VER 67 offshore | 141970 | 1999-09-01 | Done | at risk | CP99-76
| Destin Pipeline Svs Company |  | Shell/Amoco | New Lateral MP 283 to MP 279 (Gemini) | 111675 | 1999-11-01 | Done | Mobil & Phillips | CP98-512 |  |  | 7200000 | 31
| El Paso Field Services |  | Diana Line | East Breaks 945/6 to HIOS @ EB 165 | 500000 | 1999-11-01 | Med
| Green Canyon Gathering System |  | Tennessee/National Fuel | EB, GC & MC to Lafourche Parish, LA | 515000 | 1999-11-01 | Low |  | CP96-557 |  |  | 200000000 | 133
| Koch |  | Grand Isles Extension |  | 300000 | 1999-11-01 | Dead | [5 empty] | 5
| Tennessee |  | Express 500 | 500 Line Expansion from offshore LA |  | 1999-11-01 | Low
| Columbia Gulf |  | Sun Star (SP & WD to GI) | 2 new 24" laterals and one 30" mainline | 660000 | 1999-12-01 | Low | [5 empty] | 56
| Texas Eastern Transmission |  | Lease of Capacity by DIGP | Main Pass 164 to Venice Plant | 100000 | 2000-01-01 | Done | 15 | CP99-18 |  |  |  | 10
| ANR/Leviathan/NGPL |  | East Breaks Gathering | Alaminos Canyon 25 to HIOS HI A-573 (Diana/Hoover) | 400000 | 2000-07-01 | Done |  |  |  |  | 90000000 | 85
| Tennessee |  | Texas Deepwater link Project | HIOS WC 167 to WC 180 (Tennessee) | 400000 | 2000-11-01 | Med | Vastar | CP00-441 |  |  | 14500000 | 17.5
| Manta Ray Offshore Gathering |  | Marathon/Shell/El Paso | ST 292 to GI 116 (Anadarko/Hickory) | 300000 | 2001-03-01 | High | [5 empty] | 22
| Canyon Express |  | Total/Fina/Elf | Aconcaqua/KingsPeak/CandemHills to EMP 261 | 500000 | 2001-05-01 | Med
| Leviathan/Tejas |  | Nemo Gathering | Brutus (GC 158) to Manta Ray | 150000 | 2001-12-01 | Med | [5 empty] | 24
| ANR |  | Conch Project | EI 63 to Patterson | 461000 | on hold | FERC ordered at risk |  | CP97-71 |  |  | 51200000 | 37 | 461
| Chandeleur Pipe Line |  | Chevron | Venice Plant to Destin @ Pascagoula | 50000 |  | Low
| Williams |  | Kerr McGee Boomvang/Nansen | connects to CTGS | 300000 | 2001-11-01 | Med |  |  |  |  | 200000000 | 55
Mexico:
| Valero |  | Reynosa | McAllen, TX to Reynosa, Mexico | 400000 |  | Done |  | Non-Jurisdictional
| El Paso |  | Douglas Extension | Extension from Douglas to Mexico Border | 78000 |  | Done | Grupo Mex | CP98-359 |  |  | 600000 | 1
| El Paso |  | Samalayucca II (Phase I) | Waco Station to PEMEX Juarez (Guars) | 72000 | 1998-06-01 | Done | PEMEX | CP93-252 |  |  | 18200000 | 20
| El Paso |  | Samalayucca II (Phase II) | Waco Station to PEMEX Juarez (Guars) | 100000 | 1998-10-01 | Done | Samal..
| Tenneco |  | Donna Lateral | Extension to Reynosa | 220000 | 1999-10-01 | Done |  | CP98-28 |  |  | 15000000 | 10
| Tenneco |  | Mexicali | California to Baja California |  |  | Dead | replaced by Sempra
| Sempra Energy International |  | Rosarito Power Plt/Vecinos | Riverside Co., CA to Tijuana | 500000 | 1999-12-01 | Done | Sempra | CP94-207 |  |  | 35000000 | 23
| El Paso |  | PEMEX | Waco Station to PEMEX Juarez (Guars) | 40000 | 2000-01-01 | Done
| TCPL |  | Merida III Power Plant | Ciudad Pemex, Tabasco to Campeche/Merida | 370000 | 2000-06-01 | Done
| Coral Mexico |  | New PEMEX Line/Border Crossing | Kleburg County to Hildago Co., TX | 300000 | 2000-11-01 | Done |  | CP99-564 |  |  | 30000000 | 104
| Midcon Texas |  | Roma Crossing | Bob West Field to Mexican Border | 275000 | 2000-12-01 | Med |  | CP96-770
| Midcon Texas |  | Monterey Pipeline Project | Cuidad Mier to Monterey | 275000 | 2000-12-01 | Med |  | CP96-583 |  |  | 520000 | 92
| El Paso |  | Willcox Lateral | Extension from Willcox to Douglas (Border) | 130000 | 2001-06-01 | High |  | CP99-322 |  |  | 30000000 | 56
| El Paso |  | Yuma Extension | Yuma to Baja California (Mexicali) | 300000 | 2002-01-01 | Med |  |  |  |  | 143000000 | 94
| Sempra/PG&E/Proxima Gas SA |  | North Baja Pipeline/Ehrenberg Exp | El Paso Ehrenberg to Baja California | 400000 | 2003-01-01 | Med |  |  |  |  | 230000000 | 212
West:
| Transwestern |  |  | San Juan Lateral | 255000 | 1996-12-01 | Done | 8000 | CP96-10 |  |  | 14600000
| Transwestern |  |  | Thoreau to East | 107000 | 1996-12-01 | Done | 8000
| El Paso |  | Havasu | San Juan to East | 184140 | 1997-05-01 | Done | 16495 | CP96-321 |  |  | 19564419
| El Paso |  | Bondad Compressor Expansion | Ignacio to Blanco Station | 116500 | 1999-01-01 | Dead | 100000 | CP98-149 |  |  | 3600000 |  | 5160
| AEC |  | Wild Goose Storage | PG&E/Scramento Area | 14.0 Bcf | 1999-04-01 | Done |  | Non-Jurisdictional
| Transwestern |  | San Juan Junior | Ignacio to Blanco | 200000 | 1998-04-01 | Dead | 45000 | CP97-516 |  |  | 21000000 |  | 22000
| Transwestern |  | San Juan Junior | Blanco to Thoreau | 130000 | 1998-04-01 | Dead | 45000 | CP97-517
| Pacific Gas Transmission |  | Kingsgate to Malin | Duke, Montana Power, El Paso, POCO, Avista | 57000 | 1998-11-01 | Done |  | CP98-167 |  | 3-15 | 6000000
| Northwest Pipeline |  | Columbia River Gorge Expansion | Stanfield to Sumas | 50000 | 1999-11-01 | Done | DETM | CP98-554 |  |  | 18570000 |  | 10870
| Questar |  | Southern Trails | San Juan to Long Beach | 120000 | 2001-10-01 | Med |  | CP99-163 |  |  | 155000000 | 705
| Kern River |  | Long Beach Extension | Bakersfield to Long Beach | 300000 | 2001-11-01 | Low
| Kern River |  | Kern River Expansion | Opal to Bakersfield | 300000 | 2001-11-01 | on hold
| Transwestern |  | Gallup Expansion | Thoreau to California Border | 140000 | 2000-05-01 | Done |  | CP99-552 |  |  | 11600000 |  | 10000
| Northwest Pipeline |  | Jackson Prairie Expansion | Storage Field Expansion of 3.2 Bcf | 300000 | 1999-11-01 | Done |  | CP98-250 |  |  | 30192000 |  | 6960
| Northwest Pipeline |  | Jackson Prairie Expansion II | Displacement expansion for system operations | 175000 | 2003 | Med |  | CP98-251 |  |  | 100000000 |  | 6961
| Northwest Natural Gas |  | Mist Expansion Phase III | Storage Field Expansion of 2 Bcf | 45000 | [6 empty] | 122000000 | eight year plan
| Northwest Natural Gas |  | Mist Expansion Phases IV | Storage Field Expansion of 14 Bcf |  | 2002-11-01 | Low |  |  |  |  | 58000000 | 32
| Northwest Natural Gas |  | Mist Expansion Phases V | Storage Field Expansion of 14 Bcf |  | 2004-11-01 | Low | [5 empty] | 20
| Sumas Energy 2 |  | NWPL bypass | Westcoast Energy to 720 MW CC Plant | 140000 | 2003-11-01 | Med |  | CP99-320 |  |  |  | 4.5
| Williams/BC Hydro |  | Gerogia Straight Crossing | Sumas to Vancouver Island | 100000 | 2002-11-01 | Med | NEB Filed |  |  |  | 120000000 | 85
| El Paso |  | Line 200 - oil line conversion | Midland to Bakersfield (mostly replacement) | 300000 | 2001-10-01 | High
| El Paso |  | All American Pipeline Conversion | McCarney, TX to Emidio, CA | 0 | 2001-04-01 | High |  |  |  |  | 75000000 | 1058
| Northwest Pipeline |  | Displacement Expansion | Ignacio to Stanfield Corridor | 175000 | 2003-10-01 | High |  |  |  |  | 81000000
| Westcoast/Cascade/Puget Sound |  | Orca Gas Pipeline | Sumas to Puget Sound |  | 2004 | [6 empty] | 140
| Western Hub Partners |  | LODI Storage | Connects to PG&E | 12.0 Bcf | 2001 | [5 empty] | 80000000 | 35
| Western Hub Partners |  | Wheeler Ridege Storage |  | 12.0 Bcf | 2004
| WestCoast |  | Orca Natural Gas Pipeline | Sumas to Washington areas | 430000 | 2004-11-01 | On Hold |  |  |  |  | 195000000 | 140 | 22000
| PG&E/Avista |  | Jackson Prairie Expansion | Storage Field Expansion of 5.0 Bcf |  | 2003-10-01 | Med
| PG&E/Avista |  | Stanfield Storage | Stanfield, OR 15.0 Bcf working gas |  | 2003-11-01 | Med
| Kern River |  | Kern River Expansion | Opal to Bakersfield | 124500 | 2002-05-01 | Med |  |  |  |  | 80000000 |  | 3 comps
| Northwest Pipeline |  | Puget Sound Plant Lateral | Snohonmish County, WA | 133000 | 2002-08-01 | High |  |  |  |  | 17200000
| Northwest Pipeline |  | Grants Pass Lateral Expansion |  | 50000 | 2002-11-01 | Med
| PGT |  | Kingsgate to Malin | Kingsgate to Malin | 200000 | 2002-11-01 | Med
| Tuscarora |  | Sierra Pacific Power | Lemmon Valley, NV Plant | 75000 | 2002-12-01 | Med |  |  |  |  | 10200000 | 16.4
| Transwestern |  | San Juan to California | could be 100/d or 300/d | 610000 | 2002-11-01 | Low
Rockies:
| CIG |  | Parachute Creek lateral | Uinta Lateral to Parachute | 37000 | 1996-09-27 | Done
| TransColorado |  | Phase I | Rio Blanco, CO to EP Blanco | 75000 | 1996-12-01 | Done |  | CP90-1777 |  |  | 14100000
| CIG |  | Piceance & Uinta Basins | Parachute Creek & Uinta laterals | 100000 | 1997-06-01 | Done
| CIG |  | Wind River | Lateral Expansion | 68000 | 1997-08-01 | Done |  | CP96-289 |  |  | 10844200 |  | 10566
| KNE |  | Pony Express | Wind River Basin to Kansas City | 135000 | 1997-08-01 | Done |  | CP96-477
| Questar |  | Phase I | Clay Basin Storage to Kanda | 59000 | 1997-08-01 | Done - at risk |  | CP96-820
| Trailblazer |  |  | Tomahawk to NGPL | 104500 | 1997-08-01 | Done |  | CP96-506 |  | 10 | 11663000 |  | 5200
| WIC |  |  | Kanda to Tomohawk | 192000 | 1997-08-01 | Done |  | CP96-288 |  |  | 39933100 |  | 28612
| Williams |  | Rawlins-Hesston | Wyoming (Wamsutter) to Kansas | 30000 | 1997-11-01 | Done |  | CP97-7 |  |  | 9300000
| KNE |  | Pony Express | Dull Knife to Kansas City | 120000 | 1997-12-01 | Done |  | CP96-477 |  |  | 154000000 | 804
| Questar |  | Clay Basin Expansion | Increase by 4.0 Bcf (by adding cushion gas) | 88000 | 1998-05-01 | Done |  | CP96-820 |  |  | 18000000 | 41 | 110
| Questar |  | Phase II | Clay Basin Storage to Kanda | 25000 | 1998-08-01 | Done - at risk |  | CP96-820 |  |  | 18000000 | 41 | 110
| CIG |  | Campo Lateral | Pickwick Lateral to Campo Station | 107000 | 1998-09-01 | Done |  | CP97-769
| CIG/PSCO |  | Front Range Pipeline | Cheyenne Compressor to Ft. St. Vrain | 269000 | 1998-11-01 | Done |  | CP98- |  |  | 25000000 | 53
| CIG/WIC |  | Powder River Lateral | Compression at Laramie & Cheyenne | 49000 | 1998-11-01 | Done |  | CP98-128 |  | 10 | 15000000 |  | 7380
| TransColorado |  | Phase II | Rio Blanco, CO to EP Blanco | 45000 | 1999-02-01 | Done |  | CP90-1777
| TransColorado |  | KN/Questar | NW Colorado to Red Cedar Lateral | 300000 | 1999-03-01 | Done |  | CP90-1777 |  |  | 170900000 | 295
| CIG/ECT/CMS/WGR |  | Fort Union Gas Gathering | Gillette, WY to Glenrock, WY | 450000 | 1999-09-01 | Done |  |  |  |  | 43000000 | 106
| CIG |  | Wind River II | Lateral Expansion to NWPL/Kern (westward) | 100000 | 1999-10-01 | Dead
| KNE |  | Wyoming Pipeline Project | Wind & Powder River/Big Horn to Rockport | 450000 | 1999-10-01 | Low |  |  |  |  | 110000000
| KN/Devon |  | Thunder Creek Gas Gathering | Gillette, WY to Glenrock, WY | 450000 | 1999-11-01 | Done |  |  |  |  | 100000000 | 126
| CIG |  | Medicine Bow Lateral | Glenrock to Rockport | 368000 | 1999-12-01 | Done | WGR/CMS/ECT/MCN/Devon |  |  |  | 78200000 | 150
| CMS/ENA/NBPL |  | Bighorn Gas Gathering LLC |  | 250000 | 1999-12-01 | Done
| Questar |  | Fidlar Compressor Station | Expands southern part of system | 58850 | 2000-06-01 | Done |  | CP00-41 |  |  | 3325000 |  | 4829
| CIG (WIC) |  | Medicine Bow Lateral II | Glenrock to Rockport | 120000 | 2000-08-01 | Done | WGR/CMS/ECT/MCN/Devon | CP99-624 |  |  | 12100000 | 6
| Burlington Resources/ECT |  | Lost Creek Gathering | Madden Field, WY to Wamsutter Plant | 275000 | 2000-10-01 | Done |  |  |  |  | 54000000 | 124
| Questar |  | Southern System Expansion | Southern System to Clay Basin/Kanda | 280000 | 2000-10-01 | Dead
| Questar |  | Wyoming Pipeline Project | Wyoming to Kanda (Pinedale Area Porduction) | 300000 | 2000-10-01 | Low
| Questar |  | Opal Connection | Seven miles to connect to Opal | 100000 | 2000-10-01 | Low
| CIG |  | Pickerwire Lateral |  | 33000 | 2000-11-01 | Done
| Northwest Pipelne |  | Silver Gem Lateral | Filer, Idaho to Wells, Nevada | 90000 | 2000-11-01 | Dead
| CIG |  | Nixon Plant Lateral | CIG's Watkins Station to Colorado Springs | 85000 | 2000-12-02 | High
| Questar/CIG |  | Southern System Expansion | Price, UT to Kern in Salt Lake City Area | 272000 | 2001-06-01 | High |  |  |  | 10 | 80850915 | 75.6 | 9336
| CIG |  | Raton Basin Lateral Expansion | Morton Co, KS to Texas Co, OK | 85000 | 2001-09-01 | Med |  | CP00-452 |  |  |  | 48
| Paiute Pipeline |  | System Expansion | Wells, Nevada to Paiute @ Elko, Nevada | 90000 | 2001-11-01 | Dead | replaced
| Questar |  | Mainline 104 Expansion |  | 272000 | 2001-11-01 | Med | PD Recvd | CP00-68 |  |  | 80800000 | 75 | 9336
| Totem Storage |  | CIG/PSCO connected storage facility' | 9 Bcf MSQ | 250000 | 2001-11-01 | Low
| CIG |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 180000 | 2001-12-01 | Dead | replaced
| CIG (Duplicate ???) |  | Medicine Bow Lateral III | Glenrock to Rockport | 550000 | 2001-12-01 | High
| CIG (WIC) |  | Medicine Bow Lateral III | Glenrock to Rockport | 675000 | 2001-12-01 | High |  |  |  |  | 168000000 | 155 | 14340
| El Paso |  | Dumas Gas Transmission | Raton Basin to EPNG/NNG Dumas |  | 2002-04-01 | Med | [5 empty] | 185
| Trailblazer |  | Expansion/Extension | Glenrock to Gage | 300000 | 2002-10-01 | High | [5 empty] | 149 | 5200
| CIG |  | Valley Line Expansion | Adams Co, CO to Nixon Lateral | 232000 | 2002-12-01 | High |  | CP01-45 |  |  | 72000000 | 85 | 4470
| CIG/Piaute Pipeline |  | Ruby Pipeline/Nevada Exp | Uintah Basin to Paiute @ Elko, Nevada | 250000 | 2003-01-01 | Low | [5 empty] | 400
| CIG |  | COCO Pipeline | Cheyenne Hub to Midcontinent PLs | 500000 | 2003-10-01 | Low
| Northern Border |  | Bison Pipeline | Gillete, WY to McCabe, MT | 500000 | 2003-11-01 | Med |  |  |  |  | 225000000 | 325
| CMS/Pennaco Energy |  | Powder River Lateral Feeder | Montana to Gillette, WY
| KN |  | Pathfinder Pipeline | Glenrock to Rockport
| Questar/Montana Power |  | Clear Creek Storage | 4 Bcf with 50,000/d Inj. | 35000 |  | High |  |  |  |  | 3300000
Michigan:
| Great Lakes |  | River Crossing Security | Zone 3 - Under the St. Clair River | 50000 | 1996-11-01 | Done |  | CP96-26 |  | 2 | 3900000
| Great Lakes |  | Security Loop I | Looping in Lower Michigan | 5000 | 1996-11-01 | Done |  | CP95-375 |  |  | 17400000 | 14 | 14800
| Great Lakes |  | Security Loop II | Looping in Delta and Mackinac Counties, MI | 5000 | 1998-11-01 | Done |  | CP96-297 |  |  | 44300000 | 25
| Great Lakes |  | Security Loop III | Looping in Delta and Mackinac Counties, MI | 0 | 1999-11-01 | Done |  | CP98-143 |  |  | 11000000 | 14
| CMS |  | Little Bear PL | Michigan Production | 75000 | 1996-08-01 | Done |  | Non-Jurisdictional |  |  | 13600000
| ANR |  | Link Pipeline | Michigan to Consumers of Toronto | 150000 | 1996-11-01 | Done |  | CP93-564
| Great Lakes |  |  | Emerson to St. Clair | 126000 | 1998-11-01 | Done | 30000 | CP96-647 |  |  | 149000000 | 72 | 14800
| Great Lakes |  | 300 Expansion | Emerson to St. Clair | 304000 | 2000-11-01 | Dead |  | CP98-309 |  |  | 620000000
| Great Lakes |  | Nexus 98/99 | Emerson to St. Clair | 2000000 | 1999-11-01 | Dead
| ANR |  | Michigan Leg South Looping | Bridgman to Sandwich Compressors | 135000 | 1997-06-01 | Done |  | CP96-641 |  |  | 18000000 | 12
Midcontinent:
| Viking |  |  | Emerson to NNG | 20000 | 1996-11-01 | Done |  | CP96-32 |  |  | 8400000
| TransOk |  | Trident Ambrose Plant | Cushing to Blackwell, OK | 300000 | 1997-04-01 | Done |  | Non-Jurisdictional |  |  | 35000000
| TransOk |  |  | Bradley to Atoka, OK (Texoma) | 300000 | 1997-07-01 | Dead |  | Non-Jurisdictional |  |  | 40000000
| Viking |  |  | Emerson to NNG | 61300 | 1997-11-01 | Done |  | CP97-93 |  |  | 27900000
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 244000 | 1997-11-01 | Done |  | CP97-25 |  |  | 102000000 | 50 | 41000
| PEPL |  | Tuscola to Illinois | Replaced by Spectrum Project | 150000 | 1997-11-01 | Dead
| Williams Natural Gas |  | SW Missouri Expansion | waiting on Missouri Comm approval | 15610 | 1999-05-01 | Done |  | CP96-726 |  | 20 |  | 12.5
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (main,branch,TBS) | 32000 | 1998-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 31000 | 1999-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 21000 | 2000-11-01 | Done |  | CP97-25
| Northern Natural Gas |  | East Leg 2000 | Replaced with Ill/WI Express | 450000 | 2000-11-01 | replaced
| Northern Natural Gas |  | Peak Day 2000 | NNG Market Area Expansion (branch,TBS) | 20000 | 2001-11-01 | Done |  | CP97-25
| Williams Natural Gas |  | St, Louis Access | Conversion of 200 mile petroleum pipeline | 28000 | 1998-10-01 | Done
| Northern Natural Gas |  | NNG Zone E/F Koch | NNG Market Area Expansion (Rosemount) | 20000 | 1998-11-01 | Done - At Risk |  | CP98-132 |  |  | 9400000
| Viking |  |  | Minnesota Looping | 28000 | 1999-11-01 | Done |  | CP98-761 |  |  | 21300000 | 45
| Viking |  | 2001 Expansion | Emerson to Marshfield |  | 2001-11-01 | Low |  | CP98-762 |  |  | 21300001 | 46
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 650000 | 2001-11-01 | Dead
| Williams Natural Gas |  | Ottowa Compressor Station | Compression Upgrades/Additions | 44200 | 2001-06-01 | Done |  | CP00-82 |  |  | 9700000 | 1.5
| Williams Natural Gas |  | Blackwell-Cotton Valley Pipeline | Compression Upgrades/Additions | 55000 | 2001-07-01 | High | [5 empty] | 37
| Williams Natural Gas |  | Western Farmers | Cheyenne Hub to Hugoton | 540000 | 2003-11-01 | Low | [5 empty] | 400 | 13000
Canada:
| TCPL |  | Conventional 96 | Alberta to Ontario/Export | 150000 | 1996-11-01 | Done | 15000 |  |  |  | 489000
| NovaGas Clearinghouse |  | Pesh Creek Pipeline | British Columbia to Alberta | 60000 | 1997-05-01 | Done |  |  |  |  | 2900000
| Alberta Pipeline Project |  | CU Gas Ltd, Amoco & Shell Can. | Central Alberta to Carbon Hub to Empress | 1200000 | 1998-11-01 | Dead |  |  |  |  | 326868598.8233
| Alberta Pipeline Project |  | Phase II | Kaybob region extension | 1000000 | 1999-11-01 | Dead |  |  |  |  | 326868598.8233
| TCPL |  | Conventional 97 | Alberta to Ontario/Export | 286700 | 1997-11-01 | Done | 20000 |  |  |  | 900000000
| Penn West Petroleum, Ltd. |  | Wildboy Project | Wildboy Field (Fort Nelson, BC) to NOVA | 10000 | 1999-11-01 | Done |  |  |  |  | 15000000 | 40
| Foothills |  | NBPL Expansion | Nova to NBPL | 698900 | 1998-12-01 | Done | 15000 |  |  |  | 125000000 | 71 | 51000
| TCPL |  | Nexus 98 | Alberta to Ontario/Export | 2000000 | 1998-11-01 | Dead |  |  |  |  | 1190000000
| TCPL |  | Conventional 98 | 58.5 Domestic/397.4 Export | 455900 | 1998-11-01 | Done | 33539 |  |  |  | 877600000
| Nova |  | NBPL Expansion | Alberta to Foothills | 500000 | 1998-12-01 | Done | 15000 |  |  |  | 365400000
| Union Gas |  |  | System-wide |  | 1998-11-01 | Dead
| TCPL |  | Nexus 99 | Alberta to Ontario/Export | 938000 | 1999-11-01 | Dead
| TCPL |  | Conventional 99 | 108.0 Expansion/44.0 turnback | 108000 | 1999-11-01 | Done |  |  |  |  | 404500000
| TransQuebec & Martimies PL |  | TQM Extension | Lachenaie, PQ to East Hereford, NH | 194000 | 1998-11-01 | Done |  |  |  |  | 175000000 | 135
| TCPL |  | TransVoyageur Transmission | Empress, Alberta to Emerson, Manitoba | 2000000 | 1999-11-01 | Dead
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS | 212200 | 1998-11-01 | Dead |  |  |  |  | 1000000000
| Gaz Metropolitain/TCPL |  | Trans-Quebec & Maritimes | Onshore Nova Scotia to Quebec City & PNTGS | 285000 | 1999-11-01 | Dead |  |  |  |  | 1000000000
| Sable Offshore Energy Project |  | Maritimes and Northeast feed | Nova Scotia/New Brunswick to US | 400000 | 1999-12-01 | Done
| BC Gas |  | Alberta Southern Crossing | Alberta to BC interior | 105000 | 2000-11-01 | High | PG&E and BC Hydro |  |  |  | 376000000 | 194
| TCPL/ANG Pipeline |  | Kootenay Pacific Pipeline | Yahk, BC to Vancouver/Sumas | 550000 | 2000-11-01 | Dead |  |  |  |  | 530000000
| Westcoast |  | Sunshine Coast Regional Dist | MSQ | 3000000 | 2000-05-01 | Dead |  |  |  |  | 87000000
| Crowsnest Pipeline |  | CU Gas Ltd and Shell Canada | Waterton Plant to ANG station 4 (BC) | 150000 | 1998-11-01 | Dead
| TCPL/Westcoast/CGT/MCN |  | Canadian Millenium | Dawn to Lake Erie | 700000 | 2002-11-01 | on hold |  |  |  |  | 700000000
| Westcoast |  | Howe Sound LNG | MSQ | 3000000 | 2001-11-01 | Low |  |  |  |  | 72000000
| Palliser |  | Settlement reached with Nova | Nightingale, AB to Empress | 1200000 |  | Dead
| AEC Suffield Gas Pipeline |  | Alberta Energy Company | Suffield, Alberta to TCPL/Burstall, Sask | 200000 | 1998-12-01 | Done | NEB approval 8/98 |  |  |  | 26200000
| ANG/BC Pipeline |  | BC Pipeline (Southern Crossing) | Cranbrook to Kingsgate to Oliver | 250000 | 2000-12-01 | Done |  |  |  |  | 379000000 | 200
| Westcoast |  | West Liard - NWT Pipeline | West Liard valley to Northern BC (Alliance) | 50000 | 2000-05-01 | Done
| Maritimes and Northeast |  | New Brunswick to Quebec lateral | Fredericton, NB to Quebec City (Riviere-du-Loup)
| AEC Suffield Gas Pipeline |  | Alberta Energy Company | Burstall, Sask to SW Alberta
| Aiken Creek Storage |  | Unocal Canada | Increase working capacity to 80 Bcf |  | 2001-08-01 | High | [6 empty] | 18500
| TCPL/Westcoast |  | Canadian Arctic Pipeline | Mackenzie Delta/Canadian Arctic to AB/BC | 4000000 |  | Low |  |  |  |  | 6000000000
| BC Hydro/PG&E Trading |  | Southern Crossing Pipeline | Cranbrook to Kingsgate to Oliver | 275000 | 275000 | Med
Alaska:
| TransAlaska Natural Gas Systems |  | Arco/BP/Exxon/Phillips/Mobil/Hess/Unocal | Prudhoe Bay delevelopment (LNG) | 15000 |  | Low
| ANGTS |  | TCE/Westcoast | Alaskan Highway to Boundry Link | 2500000 | 2007-11-01 | Low |  |  |  |  | 6000000000 | 1700
| Arctic Resources (ARC) |  | Native Organizations (Hoagland's) | North Slope to Mackenzie to Alta | 1500000 | 2007-11-01 | Low |  |  |  |  | 5300000000 | 1200
| Enbridge Consortium |  | Mackenzie Delta | Mackenzie to Fort Saskatchewan | 1200000 | 2007-11-01 | Low |  |  |  |  | 2850000000 | 1250
Chicago:
| NGPL |  | Chicago | Harper to Chicago | 110000 | 1998-11-01 | Done | 10000 | CP96-27 |  |  | 24000000 | 5 | 9000
| Midwestern |  | PL Reversal | Chicago to Tennessee | 500000 | 2001-11-01 | on hold
| Northern Border |  | Expansion | Monchy to Harper | 700463 | 1998-12-01 | Done | 55000 | CP95-194 |  |  | 457900000
| Northern Border |  | Extension | Harper to Chicago | 663050 | 1998-12-01 | Done | 45000 | CP95-194 |  |  | 338900000 | 793 | 293000
| Alliance |  | Fort St John, BC to Chicago | Canadian Side | 1325000 | 2000-12-01 | Done |  |  |  |  | 1600000000 | 1445
| Alliance |  | Fort St John, BC to Chicago | US Side |  | 2000-12-01 | Done |  | CP97-168 |  |  | 1400000000 | 887 | 320000
| Alliance |  | Chicago Portion | Aux Sable Liquids Plant |  | 2000-12-01 | Done |  |  |  |  | 365000000
| Northern Border |  | Chicago Extension | Chicago to NIPSCO | 198300 | 2001-11-01 | High |  | CP99-21 |  |  | 93000000 | 34 | 30500
| Viking, TCPL & NICOR |  | Viking Voyaguer | Marshfield, WI to Minn, ND, Wisc and Chicago | 1400000 | 1999-11-01 | Dead |  | CP98-60/62/64/65 |  |  | 1200000000 | 773
| ANR |  | Supply Link | Sandwich Compressor to Defiance | 750000 | 2002-11-01 | Low |  | CP97-319 |  |  | 124800000 | 73 | 15000
| Enbridge/MCN/Westcoast |  | Vector | Chicago to Dawn (with NIPSCO/Crossroads) | 700000 | 2000-12-01 | Done |  | CP98-131 |  | 10 | 443000000 | 270 | 60000
| Enbridge/MCN/Westcoast |  | Vector Expansion | Compression | 300000 | 2001-11-01 | Med |  |  |  | 3
| CMS |  | TriState Pipeline | Chicago to Dawn | 650000 | 2000-11-01 | Dead |  | CP99-63 |  |  | 361000000 | 226
| ANR |  | Wisconsin Loop Expansion Proj | 11.7 miles of 30" looping from Joliet to WI | 116000 | 1999-03-01 | Done |  | CP97-765 |  |  | 24000000 | 11
| ANR |  | Wisconsin Loop Expansion I | Comp. additions at Woodstock | 109000 | 2000-11-01 | Done |  | CP99-241 |  |  | 23800000 | 0 | 20000
| ANR |  | Wisconsin Loop Expansion II | Comp. additions at Janesville/Weyauwega | 85000 | 2001-11-01 | Done |  | CP99-341 |  |  |  | 3 | 3000
| ANR |  | Wisconsin Loop Expansion III | Chicago to Wisconsin, IL and MN | 100000 | 2002-11-01 | Med | 30000
| NGPL |  |  | Gage to Chicago |  |  | Dead
| Enron/NBPL/El Paso/PGL&C |  | Illinois-Wisconsin Express | Joliet to Wisconsin | 650000 | 2001-11-01 | Dead
| Crossroads |  | NBPL connection | 25 mile expansion to NGPL/NBPL | 485000 | 2001-11-01 | Low |  |  |  |  | 35000000 | 25
| CMS/WICOR/Viking |  | Guardian Pipeline | Chicago to Wisconsin | 750000 | 2002-11-01 | High | PD recd | CP00-36 | DEIS recd |  | 224000000 | 147 | 24000
| KN Energy/NICOR |  | Horizon | Chicago | 380000 | 2002-04-01 | Med | PD recd | CP00-129 |  | 10 | 75000000 | 28.5 | 8900
| Peoples/Coastal |  | Whitecap Energy - Land | ANR @ Crete, IL to Southeastern WI | 1500000 | 2002-04-01 | Low | 30000 |  |  |  | 334000000 | 21
| Peoples/Coastal |  | Whitecap Energy - Lake | ANR @ Crete, IL to Southeastern WI | 1500000 | 2003-11-01 | Low | 30001 |  |  |  |  | 90
| NGPL |  | Hub America | Chicago to Lebanon/TETCO M3 | 100000 | 2000-11-01 | High |  |  | rolled-in
| TETCO |  | PSI Wabash Power Lateral | Midwestern Int at Vigo County, Ind | 215000 | 2001-04-01 | High |  |  |  |  | 8000000 | 9
| NGPL |  | St Louis Lateral |  | 300000 | 2002-06-01 | Med | 311 fac. |  |  |  | 35000000 | 47
Appalachian:
| ANR |  | Replaced by Independence | Chicago to Lebanon | 250000 |  | Dead
| Columbia Gas |  | Storage | Storage Withdrawal | 210000 | 1997-11-01 | Done |  | CP96-213 |  | 15 | 270000000 | 42 | 45699
|  |  |  | Transport increase | 42500 | 1997-11-01 | Done
| Columbia Gas |  | Storage | Storage Withdrawal | 126000 | 1998-11-01 | Done |  | CP96-213 |  | 15
|  |  |  | Transport increase | 25500 | 1998-11-01 | Done
| Columbia Gas |  | Storage | Storage Withdrawal | 80000 | 1999-11-01 | Done |  | CP96-213 |  | 15
|  |  |  | Transport increase | 17000 | 1999-11-01 | Done
| Columbia Gas/TETCO |  |  | Capacity Lease | 141500 | 1997-11-01 | Done |  | CP96-559 |  | 17 | 63200000
| TETCO/CNG |  | WinterNet | Oakford Storage to CNG (Phased) | 64000 | 1997-11-01 | Dead |  | CP96-606 |  | 24 | 18589000
| TETCO/CNG |  | SS-E | Oakford Storage to CNG 4.6 Bcf | 70000 |  |  |  | CP96-607 |  | 25 | 18589001
| CNG |  |  | Transport increase | 102820 | 1997-11-01 | Done |  | CP96-492 |  |  | 55929000 | 36 | 13600
| NE Hub Partners |  | Tioga Storage | Pennsylvania 6.0 Bcf | 500000 | 1999-11-01 | High
| CNG |  | Bath Petroleum | Storage Withdrawal | 168320 | 1999-11-01 | Dead |  | CP96-492
| CNG |  | High Deliverability Storage | Salt Like Firm Storage (12 cycles) |  | 2002-11-01 | Low
| CNG |  | Capstone Project | replacement of Tennessee Capacity | 0 | 2001-11-01 | High
Note on B153: ECT: Trunkline, Marathon Ashland Petroleum and TEPPCO Partners LP
Note on B397: ECT: one third ownership each
Note on D101: julie gomez: Uses Tennessee 500 line capacity
Note on D110: ECT: The LNG will come from output from the planned second and third trains of Atlantic LNG project in Trinidad and Tobago.
Note on D201: Julie Gomez: Serves 620 MW Presidente Juarez power plant
Note on D363: ECT: Producers include Chevron Canada, Canadian Forest, Ranger, Purcell, Anderson Exploration and Talisman
Note on E110: ECT: Can take delivery of 80 Bcf annually, or 220,000 M/d fo LNG starting mid 2002
Note on E112: ECT: Southern Company's capacity is in the name of Georgia Power for the Wansley Plant
Note on E119: ECT: Scana would extend the system 300 miles to the proposed ethanol facilities and power plants in Onslow, Greene and Martin Counties, NC
Note on E207: ECT: To serve the existing 150MW Hermosillo Plant and a proposed 225MW expansion plant. The 12 mile east branch line will cross the border near Douglas and serve the proposed 225MW El Fresnal/Nogales plant.
Note on E209: Julie Gomez: Will interconnect with Sempra'a Rosarito Pipelien south of Tijuana
Note on E225: ECT: Includes 50,000/d of capacity from Blanco to Thoreau
Note on E232: ECT: The Canadian portion of the project would originate on the international border in Boundry Pass, Strait of Georgia and interconnect with the existing Centra transmission system at a point south of Duncan, BC. The Canadian portion would be about 31 miles long with about 23 miles offshore and eight miles onshore. The 16" pipe would move 100,000 M/d and be in service 11/2002
Note on E397: ECT: Proposed to connect to Alliance, NBPL, NGPL, Midwestern and Joliet Hub
Note on F53: Julie Gomez: Could be expanded to 1.0 Bcf/d. NJ Natural controls
Note on F60: Julie Gomez: Willaims 100,000/d, ConEd 30,000/d,Aquila 25,000/d, ConEd Energy 10,000/d and St Lawrence Cement 1,000/d
Note on F63: Shippers inlcude: Sithe 70,000/d, Southern Kendall 35,000/d Southern Connecticut 20,000 Prov Gas 500/d Mass Water Resource Auth 25,000/d and TTECO 80,000/d
Note on F66: jgomez: Virginia Power 100,000/d and PPL 30,000/d
Note on F67: ECT: DirectLink (an affiliate) has contracted for 500,000/d. Dynegy has contracted for 350,000/d.
Note on F68: Julie Gomez: 125,000 is incremental capacity and the remaining 489,628 would be leased back to Transco.
Note on F97: ECT: Southern Company 40,000/d, Visy Paper 4500/d and AGL 61160/d Santee Cooper 80,000/d, Sylacaugh Utilities Board 4000/d, MGAG 14,439/d
Note on F101: julie gomez: Southern Co bought 7Bcf of storage at Petal and can deliver to Transco, SoNat, Koch and Deston
Note on F105: julie gomez: UCG 27,500, Citizens, APG Industries and City of Pulaski
Note on F107: jgomez: AGL signed up for 200,000/d for 20 years.
Note on F108: ECT: FPL 101142/d. Southern 60937/d, TECO 180,000/d, JEA 14000/d, Tallahassee 2677/d, Peoples 1504/d, US Agri-Chem 115/d
Note on F110: ECT: 540,000 Peak Day Deliverability
Note on F112: ECT: Southern Company 140000/d and CP&L 75000/d
Note on F118: ECT: 15 year contracts with Southern Co 284,050 South Carolina PL Corp 50,000 LaGrange, GA 1,750 Phase I of 88,150 will start June 1, 2002
Note on F123: jgomez: Shippers include Coral 6,646/d Interconn 6646/d, P&G Paper 1,564/d MGAG 1270/d CE Mineral 782/d milwhite 80/d and City of Lenox 12/d.
Note on F232: ECT: BC Hydro has sined up for 97,000/d of capacity Connects two 250MW plants on Shawnigan Lake (81,000/d) and the local LDC Centra Gas
Note on F235: ECT: PITCO's 60% of Max DQ
Note on F237: ECT: 400,000/d MDIQ 500,000/d MDWQ
Note on F264: ECT: WGR anchored
Note on F283: julie gomez: Primero Gas Marketing and El Paso Energy Raton LLC
Note on F285: jgomez: Shippers include CIG Resources 150,000/d, Questar Gas 100,000/d and 40,000 Texaco
Note on F292: jgomez: Shippers include Front Range Power 85,000/d, PSCO 178,000/d
Note on F326: ECT: LaClede subscribed
Note on F331: ECT: MEP Pleasant Hill Generating Unit (600MW) and Tyson Foods
Note on F332: ECT: Empire District Electric Company State Line Plant in Jasper Co, MO 500 MW (CC)
Note on F362: ECT: 600,000/d ??
Note on F386: Julie Gomez: DirectLink 507,000/d (contract not allowed by FERC), Dynegy 303,900/d, Cogentrix 101,300/d, Gleason 80,000/d and Duke 50,700/d
Note on F391: ECT: 59,000/d contracted to three shippers and an additional 25,000/d as of 11/1/01
Note on F397: ECT: WICOR is 650,000/d
Note on F398: ECT: Nicor is 300,000/d
Note on M53: Julie Gomez: ecorp Marketing (an affiliate of Central New York) has 400,000/d on the lateral and 90,000/d on Tennessee's 300 line
Note on M56: ECT: AES signed for 20 year 10 month contract at a negotiated rate of $.0425 plus fuel
Note on O402: julie gomez: PSI (Cynergi) will reimburse Midw for $6.3 mil
Note on P100: ECT: 30" pipeline

## Offshore99
DEEP WATER FIELDS |  |  | 2025-09-26 23:09
Royalty Relief for production in depths of 200 + meters | [12 empty] | Associated
|  | Water | [8 empty] | Water |  | Non-Associated |  | MMS | Flowing Gas Additions: |  |  |  |  | After
Project/Field | Location | Depth | Operator (First) | Status | Discovery | Year of First | Est. Reserves | Peak/Test Prod'n | Facilities Capacity | Platform | Depth | Pipeline | Gas | Flowing | Est | 1996 | 1997 | 1998 | 1999 | 2000 | 2000
| Area / Block | Feet |  |  | Year | Production | MMBOE (Prvd) | Oil/Gas | Oil/Gas | Type | Meter |  | G=Gas A=Assoc | ** | ID | [6 empty] | NOTES
Agate | Ship Shoal 360/361 |  | Phillips |  |  | 1998 |  |  |  | subsea | 0 | Transco |  |  | 1998 | Flowing Gas Additions: 1998: 50 | Production to Mahogany Platform
Alabaster(/Zinc) | Miss. Canyon 397 | 1059 | Exxon/EEX | Producing | 1984 | 1992 | 100 | 2,500 b/d, 115 MMcf/d |  | FIX | 322.7674 | SoNat | G | ** | 1992-04-01 | Flowing Gas Additions: 1996: 85; Flowing Gas Additions: 1997: -50; Flowing Gas Additions: 1998: 70 | Rec'ing prod. From Miss. Can 354 (1990) (Combined A/Z to hit 150 mmcf)
Allegheny | Green Canyon 253/254 | 3186 | EEX | planning | 1996 | 1999 | 52 | 25,000 b/d, 35 MMcf/d |  | TLP/SS | 971.0454 | Discovery | G |  | 1999 | Flowing Gas Additions: 1999: 35
Amberjack | Miss. Canyon 109 | 1029 | BP | Producing | 1986 | 1991 | (52) | 22,000 b/d |  | FIX | 313.6239 | Transco | A | ** | 1991-10-01 | Flowing Gas Additions: 1996: 7
Amundsen | East Breaks 335 | [9 empty] | 0
Angus | Green Canyon 113 | 2045 | Shell/Marathon | planning | 1997 | 1999 | 64 | 40,000 b/d, 60 MMcf/d |  | SS | 623.2856 | tie into Bullwinkle | A |  | 1999 | Flowing Gas Additions: 1999: 60
Anstey (East) | Miss. Canyon 607 | 5000 | Amoco | planning
Ariel | Miss. Canyon 429 | 6201 | Amoco | planning | 1997 | 2000 | 50
Arnold | Ewing Bank 963 | 1752 | Marathon |  | 1996 |  | 25 | 17,000 b/d |  | SS | 533.9835 |  | A |  | 1999 | Flowing Gas Additions: 1999: 0 | Production to go to Lobster via 2 6" lines
Atlantis | Main Pass |  | CNG | [7 empty] | 0 |  | A |  | 1999-01-01
Auger | Garden Banks 426/427/470/471 | 2864 | Shell | planning | 1987 | 1994 | (186.5) 220 | 100,000 b/d, 300 MMcf/d |  | TLP | 872.9046 | ANR/Garden Banks | A | ** | 1994-04-01 | Flowing Gas Additions: 1996: 155; Flowing Gas Additions: 1997: 85
BAHA | Alaminos Canyon 600 | 7620 | Shell |  |  |  | 50 |  |  |  | 2322.4627 |  | G |  | 2005 | After 2000: 700
Baldpate (Antioch) | Garden Banks 259/260 | 1641 | Amerada Hess | Producing | 1997 | 1998 | 100-200 | 65,000 b/d | 60 mbo & 200 mmcf/d (75 mbw) | CT | 500.1524 | Garden Banks | A |  | 1998-09-01 | Flowing Gas Additions: 1998: 50; Flowing Gas Additions: 1999: 150; Flowing Gas Additions: 2000: 48 | Gas 12 in. 13 mi. ties to 30 in. GB gathering in GB85, oil via 16 in. 17 mi. To Poseidon, ties to 20-24in Pos. PL system Mobil plat. SMI 205 (both pl work pres 2200 psi)
Banshee | Miss. Canyon 849 |  | UPR | abandoned | [6 empty] | 0
Bison | Green Canyon 166/106 | 2518 | Exxon | planning | [6 empty] | 767.4489 |  | A |  | 2001 | After 2000: 15
Black Widow | Ewing Bank 966 | 1850 | Shell | planning | 1998 | 1998 |  |  |  | SS |  |  | A |  | 1999 | Flowing Gas Additions: 1999: 5
Blood Sweat & Tears | Miss. Canyon 717/718 | 2786 | BP | [7 empty] | 849.1314 |  | A |  | 1999 | Flowing Gas Additions: 1999: 60
Bluethroat | Miss. Canyon 755 | 2861 | Union Pac Res | PRIMRY | 1998 | [5 empty] | 871.7777
Boomslang | Ewing Bank 994 | 850 | Murphy Oil | drilling | 1998 | [5 empty] | 259.0042 | [10 empty] | 185' pay, 3 zones, interest 42.5% W.I. In 5 adjacent blocks
Boomvang East | East Breaks 688 | 3767 | Reading & Bates |  | 1988 |  | 35 |  |  | SS | 1148.1256 |  | A |  | 2002 | After 2000: 15
Boomvang North | East Breaks 643 | 3688 | Reading & Bates |  | 1997 |  | 35-45 |  |  | NORCEN (?) | 1124.0475 |  | A |  | 2001 | After 2000: 20
Boxer | Green Canyon 19 | 757 | Shell | [7 empty] | 230.7223 |  | A | ** | 1988
Brutus | Green Canyon 158 | 2877 | Shell | planning | 1989 |  | 100-150 |  |  | SS | 876.8668 | Manta Ray/Nautilus | A |  | 2002 | After 2000: 60
Bullwinkle | Green Canyon 64/65 | 1330 | Shell |  | 1983 | 1989 | (180) |  | 200 mbo & 320 mmcf/d | FIX | 405.3642 | Manta Ray/Nautilus | A | ** | 1989-07-01 | Flowing Gas Additions: 1996: 10; Flowing Gas Additions: 1997: 5; Flowing Gas Additions: 1998: 86 | Expanding and 65 mbw/d
Busch | Main Pass 255/ Viosca Knoll 698 |  | Snyder | producing | [6 empty] | 0
Calypso | Garden Banks 798/799/842/843 | [9 empty] | 0
Cardamon | Garden Banks 471 | 2873 | Shell | planning |  |  | 50
Cerveza | East Breaks 160/161 | 935 | Unocal |  | 1980s |  |  |  |  | jacket plat | 284.9046
Cerveza Ligera | East Breaks 158/159 | 935 | Unocal |  | 1980s |  |  |  |  | jacket plat | 284.9046
Chimichanga(part of Enchilada) | Garden Banks 127 |  | Shell | producing |  | 1998 |  |  |  |  | 0 | [10 empty] | Production to Enchilada
Cinnamon | Green Canyon 45/89 | 671 | Shell | Producing |  | 1998 |  | 1930 bo & 1.4 mmcf/d | 3000 bo & 2 mmcf/d | tri-plat | 204.461 | [10 empty] | Sending prod to Enchilada (GB 128)
Cognac | Miss. Canyon 194 | 1023 | Shell | Producing | 1976 | 1979 | (283) |  |  | FIX | 311.7952 | SoNat | A | ** | 1980-09-01 | Flowing Gas Additions: 1996: 60; Flowing Gas Additions: 1999: 60
Comiskey | Walker Ridge 233 | [9 empty] | 0
Conch-Marathon | Green Canyon 66/110/153/154 | [9 empty] | 0
Conch-Mobil | Mobile 869 | [9 empty] | 0
Conger | Garden Banks 215 | 1500 | Amerada Hess | planning | 1998 |  | 50-100 |  |  | SS/FIX
Cooper | Garden Banks 387/388 | 2163 | EEX | Producing | 1989 | 1995 | (66) | 12,000 b/d |  | FPS | 659.2502 | Tennessee Blue Water | A | ** | 1995-09-01 | Flowing Gas Additions: 1996: 11; Flowing Gas Additions: 1997: 4 | Production to platform at Eugene Island 315 (120 mmcf and 40 bo/d capacity
Cornell | West Delta 109 |  | Texaco | [7 empty] | 0 | Tennessee/VK |  | ** |  | Flowing Gas Additions: 1996: 20; Flowing Gas Additions: 1997: 30; Flowing Gas Additions: 1998: 25
Corundum | East Breaks 171/172/215/216 | [9 empty] | 0
Coulomb | Miss. Canyon 657/655 | 7520 | Shell | planning | 1988 |  | 50 |  |  |  | 2291.9842 |  | A |  | 2005 | After 2000: 100
Crystal | Miss. Canyon 321/322/365 | 621 | Freeport McMoran | [6 empty] | 8 slot 4PP | 189.2254
Destin Dome | Destin Dome 12/13/14/15/16/54/55/56/97 | [9 empty] | 0
Diamond | Miss. Canyon 401/445 | 2095 | Oryx |  | 1988 | 1994 | (6) |  |  | SS | 638.5248 | SoNat | G | ** | 1993-07-01 | Flowing Gas Additions: 1996: 30; Flowing Gas Additions: 1997: -25
Diana | East Breaks 945/946 | 4634 | Exxon |  | 1991 | 2000 | 350 | 4,800 b/d, 2.6 MMcf/d |  | SPAR/FPS | 1412.3743 | to Hoover facility | G |  | 2000 | Flowing Gas Additions: 2000: 100; After 2000: 170
Diana South | Alaminos Canyon 65 | 4852 | Exxon/BP |  | 1996 | 2000 |  |  |  | SS | 1478.8174 |  | G |  | 2005 | [6 empty] | Pipeline to be installed in 1999
Dionysis | Viosca Knoll 864 | [9 empty] | 0
Dizzy | Green Canyon 365 | [9 empty] | 0
Dulcimer | Garden Banks 367 | 1120 | Mariner | planning | 1998 | 1999 |  |  |  | SS | 341.3593 |  | G |  | 1999 | Flowing Gas Additions: 1999: 15 | 2 Prod intervals 150' pay, testing third interval-gas
Elvis | Miss. Canyon 580 | [9 empty] | 0
Emerald | Ewing Bank 786 |  | R&B | abandoned | [6 empty] | 0
Enchilada | Garden Banks 128 |  | Shell |  |  | 1998 | 100 | 200 mmcf & 10 mbc/d peak | 400 mmcf & 60 mb/d | 2 Plat A & B | 0 | Garden Banks | A | ** | 1997-10-01 | Flowing Gas Additions: 1997: 100; Flowing Gas Additions: 1998: 200 | 400 bcf & 25 mmbo (dev of adjoining tracts could get to 300 mmcf/d and 40 mbo/d)
Europa | Miss. Canyon 934/935/890/891 | 3889 | Shell/BP/Conoco | planning | 1994 | 2000 | 160 | 60,000 b/d, 45 MMcf/d |  | SS | 1185.3094 | tie into Mars | A |  | 2000 | After 2000: 45
Flathead | Miss. Canyon 899 | 4452 | Shell | planning | [6 empty] | 1356.9034 |  | A |  | 2001 | After 2000: 50
Fourier | Miss. Canyon 522 | 6950 | Shell | planning | 1987 | 2000 | 50 |  |  |  | 2118.2566 |  | A |  | 2001 | After 2000: 50
Fuji | Green Canyon 505/506/549 | 4275 | Texaco | planning | 1995 | 2000 | 50 |  |  |  | 1302.9564 |  | A |  | 2002 | After 2000: 100
Fuji | Viosca Knoll 872 |  | Amoco | [7 empty] | 0 | Destin |  |  | 2000 | Flowing Gas Additions: 2000: 100
Garden Banks 65 | GB 65, 21, 22, E Cam 373 |  | Kerr McGee |  |  | est. 1998 |  | ini 60 mmcf/d |  |  |  |  | G |  | 1998 | [6 empty] | (1997 OGJ)
Gamera | Atwater Valley 119 | [9 empty] | 0
Gemini | Miss. Canyon 291/292/247 | 3763 | Texaco/Chevron | planning | 1995 | 1999 | 150 | 2-3,000 b/d, 150-200 MMcf/d |  | SS | 1146.9064 | Destin | A |  | 2000 | Flowing Gas Additions: 2000: 100; After 2000: 100 | Subsalt play - offset by GC 506 wildcat (32 mi. extension to MP260?)
Genesis | Green Canyon 205 | 2599 | Chevron | planning | 1996 | 1998 | (160) | 55,000 bbl, 72 MMcf/d |  | SPAR | 792.1365 | Transco | A |  | 1999 | Flowing Gas Additions: 1999: 72
George | Miss. Canyon 442 | [9 empty] | 0
Glider | Green Canyon 248 | 3300 | Shell | planning | 1996 | 2000 | 100-150 |  |  | TLP | 1005.7909 |  | A |  | 2001 | After 2000: 60
Gomez | Miss. Canyon 667/711/755 | 3000 | UPRC | planning | 1997 | 2001 | 120 | 40,000 b/d |  | SPAR/TLP | 914.3554 |  | A |  | 2000 | Flowing Gas Additions: 2000: 60
Grand Canyon | Green Canyon 141 | 1715 | Conoco | planning | [6 empty] | 522.7065 |  | A |  | 2001 | After 2000: 25
Grand Canyon | Green Canyon 141 | [9 empty] | 0
Guernsey | Green Canyon 200/201/244/245 | [9 empty] | 0
Gunnison | Green Canyon 303 | 2000 | Vastar | planning | [6 empty] | 609.4217 | [10 empty] | To drill in 98 or 99
Hardy | Grand Isle 115 |  | Texaco | [7 empty] | 0 | Discovery
Hercules | Ewing Bank 873 | 778 | Marathon | Producing | 1993? | 1994 |  |  |  | Fixed | 778 | Discovery | A | ** | 1994 | Flowing Gas Additions: 1996: 25 | (9/25/95) Prod. Exceeds 46,000 bo/d
Hershel South | Miss. Canyon 520 | 6739 | Amoco/Shell | planning | 1997 |  | 50
Hoover | Alaminos Canyon 25/26 | 4795 | Exxon/BP | planning | 1997 | 2000 | 100 |  | 100000 bo & 325 mmcf/d | SPAR | 1461.4447 | new pipelines | A |  | 2000 | Flowing Gas Additions: 2000: 60 | Est. 300 mmboe reserves by Exxon (w/Diana)
Iron Horse | Green Canyon 625 | [9 empty] | 0
Jolliet | Green Canyon 184 | 1720 | Conoco | Producing | 1981 | 1989 | (57) |  |  | TLP | 524.2304 | Tennessee Blue Water | A | ** | 1989-11-01 | Flowing Gas Additions: 1996: 25; Flowing Gas Additions: 1997: 5; Flowing Gas Additions: 1998: 35
Kepler | Miss. Canyon 383 | 5729 | Shell | planning | 1997 | 2000 | 50 |  |  |  | 1746.114 |  | A |  | 2002 | After 2000: 50
Keweenaw | Miss. Canyon 619 | [9 empty] | 0
Kilauea | Green Canyon 6/50 | [9 empty] | 0
Kilmarnock | Garden Banks 258 |  | Vastar | Well P&A | 1998? | [5 empty] | 0
King | Miss. Canyon 764 | 3300 | Vastar | planning | 1997 | 1999 |  |  |  |  | 1005.7909 |  | A |  | 2003 | After 2000: 25
King | Miss. Canyon 84/85/129 | 5149 | Amoco | planning | 1993 | 2001 |  |  |  | SPAR | 1569.3386 |  | A |  | 2001 | After 2000: 40
King Kong | Green Canyon 472/473/517 | 3817 | British Borneo/Shell | planning | 1997 | 2000 | 250 |  |  | SS | 1163.3648 |  | A |  | 2000 | Flowing Gas Additions: 2000: 125
King's Peak #1 | Desoto Canyon 133/177 | 6530 | Amoco |  | 1993 | 2001 | 250 |  |  | SS | 1990.2469 |  |  |  | 2001 | Flowing Gas Additions: 2000: 40 | Planned up-grade to J-lay System
Kings Peak #2 | Miss. Canyon 217 | 6500 | Amoco | planning | 1994 | 2000 | 250 |  |  | SS | [11 empty] | Planned up-grade to J-lay System
Klamath | Ewing Bank 921/964/965 | 1673 |  |  | 1991 |  |  |  |  | SS
Knight | Garden Banks 372 | 1740 | Santa Fe | planning | [6 empty] | 530.3261 |  | A |  | 2000 | Flowing Gas Additions: 2000: 25
Ladybug | Garden Banks 409 | 1355 | Texaco | planning | 1997 |  | 15-20 | 7,266 b/d, 3.7 MMcf/d |  |  | 412.9838 |  | A |  | 2002 | After 2000: 4
Lafitt Pincay | Ewing Bank 958/959/1002/1003 | 1450 | Tatham |  | 1994 | 1997 | 75 |  |  | FPS/SPAR | 441.9384 |  | A |  | 1998/99 | Flowing Gas Additions: 1998: 40; Flowing Gas Additions: 1999: 10
Legacy | Miss. Canyon 29 |  | Oryx | planning | [6 empty] | 0 | [10 empty] | Well was to drill 1998
Lena | Miss. Canyon 281 | 1018 | Exxon | Producing | 1976 | 1983 | (88) |  |  | CT | 310.2713 | Texas Eastern/Destin | A | ** | 1984-05-01 | Flowing Gas Additions: 1996: 15; Flowing Gas Additions: 1997: 4; Flowing Gas Additions: 1998: 40
Leo | Miss. Canyon 502/503/546 | 2500 | British Borneo | planning | 1998 | [5 empty] | 761.9628 | [10 empty] | 200 feet net oil/gas pay
Llano | Garden Banks 386 | 2300 | EEX | planning | 1998 | 1999 |  |  |  | SS | 701.0058 |  | A |  | 1999 | Flowing Gas Additions: 1999: 25 | Five prospects in are, Travis (GB 387), Rex (GB 386-7), Huey (GB 390-346), Bowie, (GB 388), Llano (GB 385-6)
Lobster | Ewing Bank 873/874/917/918 | 775 | Marathon? | [7 empty] | 236.1509 | [10 empty] | Arnold production to come here via 2-6" lines
Macaroni | Garden Banks 602 | 3684 | Shell | planning | 1995 | 1999 | 78 | 35,000 b/d, 65 MMcf/d |  | SS | 1122.8284 | tied into Auger/Garden Banks | A |  | 1999 | Flowing Gas Additions: 1999: 65
Mad Dog | Green Canyon 782/825/826 | [9 empty] | 0
Mahogany | Ship Shoal 349/359 | 370 | Phillips | producing |  | 1996 |  | 100 mmcf & 45 mbo/d (peak) |  |  | 112.7705 | Manta Ray/Nautilus | A | ** | 1996 | Flowing Gas Additions: 1996: 30; Flowing Gas Additions: 1998: 75 | Gas to LOGS via 16 in (9 mi) | SS 337,338 part of structure (acquired Ana and Amoco respect.)
Marlin | Viosca Knoll 915 | 3236 | Amoco | planning | 1993 | 1999 | 100 | 40,000 b/d, 250 MMcf/d |  | TLP | 986.2847 | Destin | A |  | 2Q 1999 | Flowing Gas Additions: 1999: 250
Marquette | Green Canyon 52/53 | [9 empty] | 0
Mars | Miss. Canyon 807 | 2958 | Shell | Producing | 1989 | 1996 | (166) | 140,000 b/d, 140 MMcf/d |  | TLP/SS | 901.5544 | TETCO(WD143)/MCGS | A | ** | 1996-07-01 | Flowing Gas Additions: 1996: 30; Flowing Gas Additions: 1997: 80; Flowing Gas Additions: 1999: 90 | Oil (116 mi) via 18" and 24" to Clovelly La., Gas 55 mi via 14" to WD 143 gathering plat
Mensa | Miss. Canyon 686/687/730/731 | 5376 | Shell | Producing | 1987 | 1997 | (142) | 300 MMcf/d |  | SS | 1638.5248 | Mississippi Canyon Gath | G | ** | 1997-07-01 | Flowing Gas Additions: 1997: 108; Flowing Gas Additions: 1998: 192
Metallica | Miss. Canyon 911 | 7000 | BP | planning |  | 2004 |  |  |  |  | 2133.4959
Mickey | Miss. Canyon 211 | 4356 | Exxon | planning | 1991 |  | 100-200 |  |  | SS | 1327.644 |  | A |  | 2002 | After 2000: 75
Mirage | Miss. Canyon 941 | 3860 | Vastar | planning | [6 empty] | 1176.1838 | [10 empty] | To drill in 98 or 99
Mirage/Zeus | Miss. Canyon 941 | 3905 | Vastar/Unocal | planning | [6 empty] | 1190.1859 | Mississippi Canyon Gath | A |  | 2002 | After 2000: 40
Morpeth | Ewing Bank 921/964/965 | 1673 | British Borneo | Producing | 1997 | 1998 | 77 | 35,000 b/d, 65 MMcf/d | 100 mmcf & 50 mbo/d | TLP/SS | 509.9055 | Discovery | A | ** | 1996-10-01 | Flowing Gas Additions: 1997: 25; Flowing Gas Additions: 1998: 20; Flowing Gas Additions: 2000: 40 | Hub for surrounding fields (Black Widow) Oil & gas will go to Discovery PL via Amberjack
Mosquitto Hawk | Garden Banks 269 | 1102 | Texaco | planning | [6 empty] | 335.8732 |  | A |  | 2000 | Flowing Gas Additions: 2000: 25
Mustique | Garden Banks 240 |  | Mariner | [7 empty] | 0
Nakika | Miss. Canyon 429/522/383 | 6274 | Amoco/Shell |  | 1997 | 2000 |  |  |  | FPS | 1912.2219 |  | A |  | 2001 | After 2000: 50
Narcissus | Miss. Canyon 638 | 4250 | Texaco |  | 1997 | [5 empty] | 1295.3368 |  | A |  | 2004 | After 2000: 37
Nautilus | Main Pass 280 | 307 | CNG | planning |  |  |  |  | 15 mbo & 150 mmcf/d |  | 93.569 |  | A |  | 1999-01-01
Nemo | Main Pass 279 | 290 | CNG | [7 empty] | 88.3877 | Destine | A |  | 1998-12-01
Neptune | Atwater Valley 575 | 6220 | BHP | planning |  | 2001 | 100 | 30,000 b/d, 30 MMcf/d |  |  | 1895.7635 |  | A |  | 2002 | After 2000: 50
Neptune | Viosca Knoll 826 | 1930 | Oryx | Producing | 1988 | 1997 | (67) | 25 mbo & 30 mmcf/d |  | SPAR | 588.2353 | TETCO (73071) | A | ** | 1997-03-01 | Flowing Gas Additions: 1997: 20; Flowing Gas Additions: 1999: 20
Nile | Viosca Knoll 914 | 3535 | Amoco | planning | 1997 |  | 50
Nirvana | Miss. Canyon 162 | 3414 | BP | planning |  | 2001 |  |  |  | FP | 1040.5364 |  | A |  | 1999 | Flowing Gas Additions: 1999: 25
Ojai | Miss. Canyon 499/543 | 2000 | Vastar | [7 empty] | 609.4217 | [10 empty] | To drill in 98 or 99
Olivela | Green Canyon 200/201/244/245 | [9 empty] | 0
Osiris | Viosca Knoll 944 | 750 | BP | [7 empty] | 228.5331
Oyster | Ewing Bank 917 | 1185 | Marathon/Texaco |  | 1996 | 1998 | 10 | 7,500 b/d |  | SS | 361.1704 |  | A | ** | 1997 | Flowing Gas Additions: 1996: 5 | Production to go 3 miles thru 2 3" lines (host platform)
Paricutin(Star by Shell) | Atwater Valley 134/135/136/137/178/179 |  | Vastar/Shell | [7 empty] | 0
Penn State | Garden Banks 216 | 1450 | Amerada Hess | planning | 1996 | 1998 |  | 10,000 b/d |  | SS | 441.9384 | Garden Banks | A |  | 1998 | Flowing Gas Additions: 1998: 50; Flowing Gas Additions: 1999: 102
Petronius | Viosca Knoll 786 | 1754 | Texaco/Marathon | planning | 1995 | 1999 | 80-100 |  | 100 mmcf & 60 mbo/d | CT | 534.5931 | Tennessee/VK | A |  | 1999 | Flowing Gas Additions: 1999: 100 | 14 in oil (20 mi) and 12 in. gas (12 mi)to existing complexes
Phar Lap Deep | Viosca Knoll 818 |  | Tatham | [7 empty] | 0
Phar Lap Shallow | Viosca Knoll 817 | 674 | Tatham | [7 empty] | 205.4252 | Tennessee/VK | G | ** | 1995 | Flowing Gas Additions: 1996: 65
Pimento | Garden Banks 192/193/236/237 | [9 empty] | 0
Pluto | Miss. Canyon 673/674 | 2828 | Mariner | planning |  | 1999 | 20-25 |  |  | SS
Pluto | Miss. Canyon 673/717 | [9 empty] | 0
Pompano I | Viosca Knoll 989/990 | 1483 | BP | Producing | 1985 | 1994 | (193) |  |  | FIX | 451.9963 | SoNat | A | ** | 1995-08-01 | Flowing Gas Additions: 1996: 2; Flowing Gas Additions: 1997: 1; Flowing Gas Additions: 1998: 60 | (9/5/94)Designed at 40,000 bo & 50 mmcf/d & 40000 bw
Pompano II | Miss. Canyon 26 | 1865 | BP | Producing | 1985 | 1996 | (193) |  |  | SS | 568.4243 | Tennessee/VK | A | ** | 1996-07-01 | Flowing Gas Additions: 1996: 7; Flowing Gas Additions: 1997: 7
Popeye | Green Canyon 116 | 2068 | Shell | Producing | 1985 | 1996 | (60) | 9,000 b/d, 160 MMcf/d | 120 mmcf/d | SS | 630.2956 |  | A | ** | 1996-01-01 | Flowing Gas Additions: 1996: 105; Flowing Gas Additions: 1997: -39; Flowing Gas Additions: 1998: 97 | Two 6 in. lines 24 miles to Cougar plat (S. Timb. 300) Ini. Dev 200 bcf and 7 mmbc
Poseidon | Green Canyon 691 | 4489 | BP | [7 empty] | 1368.1804 |  | A |  | 2003 | After 2000: 25
Prosperity | Viosca Knoll 742 | 1000 | Texaco | planning | 1998
Ptolemy | Garden Banks 412 | [9 empty] | 0
Ram-Powell | Viosca Knoll 956 | 3255 | Shell | Producing | 1989 | 1997 | (252) | 70,000 b/d, 260 MMcf/d |  | TLP | 992.0756 | Tennessee/VK | A | ** | 1997-09-01 | Flowing Gas Additions: 1997: 56; Flowing Gas Additions: 1998: 140
Rockefeller | East Breaks 992 | 1019 | Exxon | Primry | 1997 | [5 empty] | 310.576 |  | A |  | 2000 | Flowing Gas Additions: 2000: 15
Rocky | Green Canyon 110 | 1621 | Shell | Producing | 1994 | 1996 | (7) | 6,900 b/d |  | SS | 494.0567 | Manta Ray/Nautilus | A | ** | 1996-01-01 | Flowing Gas Additions: 1996: 7; Flowing Gas Additions: 1997: -6
Rogue | Miss. Canyon 705 | [9 empty] | 0
Salsa | Garden Banks 171 | 1130 | Shell/Hess/Oryx | planning | [6 empty] | 344.4072 | Garden Banks | A |  | 1998
Say Hey | Green Canyon 622 | [9 empty] | 0
Seastar | Garden Banks 70/71 | [9 empty] | 0
Seattle Slew | Ewing Bank 914 | 1019 | Tatham | Producing | 1997 | 1993 | (10) |  |  | FPS | 310.576 | Trunkline | A | ** | 1993-08-01 | Flowing Gas Additions: 1996: 3
Serrano | Garden Banks 516 | 3153 | Shell | planning | 1997 | 2001 | 50 |  |  | SS | 960.9875 |  | A |  | 2000 | Flowing Gas Additions: 2000: 25 | Tie-back to Auger TLP
Shasta | Green Canyon 92/136/137 | 1040 | Texaco | planning | 1994 | 1995 | 8 |  | 50 mmcf/d | SS | 316.9765 | Tennessee Blue Water | A | ** | 1995-11-01 | Flowing Gas Additions: 1996: 60; Flowing Gas Additions: 1997: -25 | Gas to go 8 mi. to Texaco's Kilauea platform on GC Blk 6
Sheba | Green Canyon 341 | [9 empty] | 0
Snapper | East Breaks 165/209 | [9 empty] | 0
Snyder | Main Pass 261 A-3/4/5 | [9 empty] | 0 | Transco |  | ** | 1998-08-01 | Flowing Gas Additions: 1998: 180
Spectacular Bid | Garden Banks 72 |  | Tatham | [7 empty] | 0
Specter | Viosca Knoll 784 | 1047 |  | planning | 1998 | 2000
Spend-a-buck | Garden Banks 117 | 978 | Flextrend/Tatham | [6 empty] | SS | 298.0799 | ANR/Leviathon | A | ** | 1996-07-01 | Flowing Gas Additions: 1996: 6
Spirit | Viosca Knoll 780 |  | Shell | [7 empty] | 0
Star (Paricutin by Vas) | Atwater Valley 134/135/136/137/178/179 |  | Shell/Vastar | [7 empty] | 0
Stellaria | Green Canyon 112 | 2045 | Marathon/Shell | Disc. Confirmed | [6 empty] | 623.2856 |  | A |  | 2002 | After 2000: 25 | Confirmed 120 net feet 9 mi E of Bullwinkle
Sting | Viosca Knoll 1000/1001 | 4000 | Vastar | planning | [6 empty] | 1218.8433 | [10 empty] | To drill in 98 or 99
Sunday Silence | Ewing Bank 958 | 1450 | Tatham | planning | 1994 | 1998 |  |  |  | SPAR
Tahoe I & II | Viosca Knoll 783/784 | 1395 | Shell | Producing | 1984 | 1994 | (106) | 300 MMcf/d |  | SS | 425.1753 | Tennessee/VK & Destin | A | ** | 1994-01-01 | 25 | 80 | 50 | 150
Tahoe Southeast | Viosca Knoll 827 | 1770 | Shell | Producing | 1996 | 1996 | 120 | 235 MMcf/d |  | SS
Tanzanite | Eugene Island 346 | 314 | Anadarko | Testing | 1998 | 2000 | [15 empty] | Tested 22 mbo and 29.7 mmcf/d @ 2679 psi
Tequila(Wisdom fld) | East Breaks 109/110/154 |  | Zapata |  |  |  | 90 bcf | 55 mmcf/d |  |  | 0
Teton | Miss. Canyon 294/338/339 |  | Unocal | Producing |  | 1998 |  | 25 mmcf & 300 bc/d |  |  | 0
Thor | Viosca Knoll 825 | 1710 | Oryx | Producing |  | 1998 | (67) |  |  | SPAR | 521.1826 | Tetco | A
Tick | Garden Banks 189 | 718 | Texaco | Producing? | 1988 | 1990 |  | 10 mbo & 60 mmcf/d (peak) |  | 4 LP | 218.8357 |  | A | ** | 1992 | Flowing Gas Additions: 1996: 75
Titan | Garden Banks 741/785 | [9 empty] | 0
Toro | Green Canyon 69 | 1465 | Shell | planning |  | 2000
Troika (Wasatch) | Green Canyon 200/201/244/245 | 2721 | BP | Producing | 1994 | 1997 | 200 | 80,000 b/d, 140 MMcf/d | Shell to handle @ Bullwinkle | SS | 829.3203 | Nautilus | A | ** | 1997-12-01 | Flowing Gas Additions: 1997: 5; Flowing Gas Additions: 1998: 135 | To tie to Bullwinkle 14.1 miles away
Ursa | Miss. Canyon 809/810/854 | 4021 | Shell |  | 1991 | 1999 | (112) | 150,000 b/d, 400 MMcf/d |  | TLP | 1225.541 | Mississippi Canyon Gath | A |  | 2000 | Flowing Gas Additions: 2000: 80; After 2000: 320
Vancouver(now Genisis) | Green Canyon 160/161/205 | [9 empty] | 0
Venus | Miss. Canyon 853/897 | 3790 | Shell | planning | [6 empty] | 1155.1356 |  | A |  | 2001 | After 2000: 50
Vince | Miss. Canyon 627 | [9 empty] | 0
Virgo | Viosca Knoll 823 | 1130 | Elf | planning | 1997 | 1999 |  | 1,800 b/d, 22.7 MMcf/d |  | FIX | 344.4072 | Tetco/DIGS | G |  | 2000 | Flowing Gas Additions: 2000: 200 | Secured extension to leases
VK 862 | Viosca Knoll 862 | 1043 | Walter Oil | Producing |  |  | (4) |  |  | SS | 317.8909 |  | A | ** | 1995 | Flowing Gas Additions: 1997: 5
Wisdom Tequila plat) | East Breaks 109/110/154 |  | Zapata | [7 empty] | 0
Wrigley | Walker Ridge 382 | [9 empty] | 0
Yankee | Walker Ridge 49 | [9 empty] | 0
Yukon | Green Canyon 60 | [9 empty] | 0
Zeus | Miss. Canyon 941 | [9 empty] | 0
Zinc(/Alabaster) | Miss. Canyon 354 | 1478 | Exxon | Producing | 1977 | 1993 | (46) | 2,500 b/d, 115 MMcf/d |  | SS | 450.4724 | SoNat | G | ** | 1993 | Flowing Gas Additions: 1996: 40; Flowing Gas Additions: 1998: 80
| Atwater Valley 8 | 3135 | Shell | [7 empty] | 955.5014 |  | A |  | 2005 | After 2000: 50
| East Breaks 109/110 | 662 | Panaco | [7 empty] | 201.7678 |  | G | ** | 1987 | Flowing Gas Additions: 1996: 35
| East Breaks 165 | 883 | BP | [7 empty] | 269.1253 |  | A | ** | 1987 | Flowing Gas Additions: 1996: 40
| East Breaks 250 | 1884 | EO&G | [7 empty] | 574.2443
| Ewing Bank 1006 | 1884 | Marathon |  | 1997 | 1998 |  |  |  | SS | 574.2443 |  | A |  | 1998 | Flowing Gas Additions: 1998: 10
| Garden Banks 200 | 1060 | Amerada Hess | PRIMRY | 1998 | [5 empty] | 323.0886
| Garden Banks 208 | 1250 | Agip | planning | [6 empty] | 380.9814 |  | A |  | 2001 | After 2000: 25
| Garden Banks 253 | 1400 | Marathon | planning | [6 empty] | 426.6992 |  | A |  | 1999 | Flowing Gas Additions: 1999: 25
| Garden Banks 254 | 1920 | Chevron |  | 1993 | [5 empty] | 585.1874 |  | A |  | 2002 | After 2000: 25
| Garden Banks 259/216 | 1946 | Amerada Hess | planning | [5 empty] | CT
| Garden Banks 302 | 2411 | Conoco | planning | 1991 | [5 empty] | 734.8369 |  | A |  | 2000 | Flowing Gas Additions: 2000: 25
| Garden Banks 543 | 2000 | Marathon | planning | [6 empty] | 609.5703 |  | A |  | 2001 | After 2000: 25
| Green Canyon 112 | 2172 | Marathon | PRIMRY | 1998
| Green Canyon 153 | 1500 | Marathon | planning | [6 empty] | 457.1777 |  | A |  | 2004 | After 2000: 0
| Green Canyon 181 | 1550 | Amoco | planning
| Green Canyon 228 | 1638 | Texaco | planning
| Green Canyon 236 | 2000 | Marathon | planning
| Green Canyon 296 | 3920 | Shell | planning
| Green Canyon 37 | 2024 | British Borneo | planning
| Green Canyon 473 | 3700 | Shell | planning | 1991
| Green Canyon 72 | 1655 | Mobil | planning | [5 empty] | SS
| Green Canyon 82 | 2400 | Kerr McGee | planning
| Miss. Canyon 243 | 3100 | Conoco | planning | 1990 | 2000 |  |  |  |  | 944.8339 |  | A |  | 2001
| Miss. Canyon 26 | 1272 | BP | planning | [6 empty] | 387.6867 |  |  |  | 2001 | After 2000: 25
| Miss. Canyon 311 | 402 | Shell | [7 empty] | 122.5236 |  | A | ** | 1980 | Flowing Gas Additions: 1996: 115
| Miss. Canyon 365 | 615 | Samedan | [7 empty] | 187.4429 |  | G | ** | 1992 | Flowing Gas Additions: 1996: 80
| Miss. Canyon 401 | 1367 | Oryx | Producing | [5 empty] | SS
| Miss. Canyon 429 | 6274 | Shell | planning | 1987 | 2001
| Miss. Canyon 441 | 1520 | EEX | Producing | 1986 | 1993 | 38 |  |  | SS | 463.2734 |  | G | ** | 1993 | [6 empty] | Gas to Plat in Ewing Banks Blk 482 (6 mi)
| Miss. Canyon 442 | 1531 | Enserch | Producing | [5 empty] | SS
| Miss. Canyon 443 | 2095 | Walter | planning |  | 1999 |  |  |  | SS
| Miss. Canyon 486 | 1200 | AEDC | Producing | [5 empty] | SS | 365.7422 |  | A |  | 2003 | After 2000: 25
| Miss. Canyon 520 | 6739 | Shell | planning |  |  | 50 |  |  |  | 2053.947 |  | A |  | 2003 | After 2000: 50
| Miss. Canyon 533 | 1000 | Walter | planning | [5 empty] | SS
| Miss. Canyon 837 | 3900 | Walter | planning |  | 1999 |  |  |  | SS
| Viosca Knoll 35 | 1296 | OEDC | [7 empty] | 395.0015 |  |  | ** | 1997-08-01 | Flowing Gas Additions: 1996: 3; Flowing Gas Additions: 1997: 1
| Viosca Knoll 956 to MP 289 | 300-1000 | Shell | Contracted | 1995 |  |  |  | 12 in oil line 41.7 km
| Viosca Knoll 956 to VK 817A | 300-1001 | Shell | Contracted | 1995 |  |  |  | 14 in nat. gas line
| Viosca Knoll 824 | 1667 | Shell | PRIMRY | 1998
| Viosca Knoll 986 | 640 | Walter O & G | PRIMRY | 1996
| Main Pass 260 | 314 | Snyder | planning | 1998 | 1999 est. |  | 2.75 mbc & 25.8 mmcf/d
| Main Pass 261 |  | Snyder | dev |  |  |  | 30 mmcf/d & 721 b/d
Mobile 823 Field | Mobile Bay 823 |  | Mobil | producing | [8 empty] | G | ** |  | Flowing Gas Additions: 1998: 400; Flowing Gas Additions: 1999: 400+ | New well tested 53 mmcf/d
Destin PL Extensions | MP 279 & 281 to MP 260 (13 mi)
Destin PL Extensions

## Offshore
|  | DEEP WATER FIELDS |  |  |  |  | 2025-09-26 23:09
Assoicated |  | Royalty Relief for production in depths of 200 + meters
Non-Associated |  |  |  |  | Water | Water |  |  | MMS | Flowing Gas Additions: |  |  |  |  | After
Gas | Project/Field | Operator (First) | Location | Platform | Depth | Depth | Pipeline | Flowing | Est | 1996 | 1997 | 1998 | 1999 | 2000 | 2000
G=Gas A=Assoc |  |  |  | Type | Meter | Feet |  | ** | ID
G | South Diana | Exxon/BP | Alaminos Canyon 65 |  | 1478.8174 | 4852 |  |  | 2005
A | Hoover | Exxon/BP | Alaminos Canyon 25 | FPS | 1461.4447 | 4795 |  |  | 2000 | Flowing Gas Additions: 2000: 60
G | BAHA | Shell | Alaminos Canyon 600 |  | 2322.4627 | 7620 |  |  | 2005 | After 2000: 700
A | Neptune | BP Exploration | Atwater Valley 575 |  | 1895.7635 | 6220 |  |  | 2002 | After 2000: 50
A |  | Shell | Atwater Valley 8 |  | 955.5014 | 3135 |  |  | 2005 | After 2000: 50
| King's Peak | Amoco | Desoto Canyon 133 |  | 1990.2469 | 6530 |  |  | 2001
G |  | Panaco | East Breaks 109/110 |  | 201.7678 | 662 |  | ** | 1987 | Flowing Gas Additions: 1996: 35
A |  | BP Exploration | East Breaks 165 |  | 269.1253 | 883 |  | ** | 1987 | Flowing Gas Additions: 1996: 40
|  | EO&G | East Breaks 250
A | North Boomvang | Reading & Bates | East Breaks 643 |  | 1124.0475 | 3688 |  |  | 2001 | After 2000: 20
A | Boomvang | Reading & Bates | East Breaks 688 | SS | 1148.1256 | 3767 |  |  | 2002 | After 2000: 15
G | Diana | Exxon | East Breaks 945/6 | FPS | 1412.3743 | 4634 |  |  | 2000 | Flowing Gas Additions: 2000: 100; After 2000: 170
A | Rockefeller | Exxon | East Breaks 992 |  | 310.576 | 1019 |  |  | 2000 | Flowing Gas Additions: 2000: 15
A | Morpeth/Klamath | British-Borneo | Ewing Bank 921, 964/5 | SS | 509.9055 | 1673 | Discovery | ** | 1996-10-01 | Flowing Gas Additions: 1997: 25; Flowing Gas Additions: 1998: 20; Flowing Gas Additions: 2000: 40
A | Hercules | Marathon | Ewing Bank 873 |  | 0 |  | Discovery | ** | 1994 | Flowing Gas Additions: 1996: 25
A | Seattle Slew | Tatham | Ewing Bank 914 | FPS | 310.576 | 1019 | Trunkline | ** | 1993-08-01 | Flowing Gas Additions: 1996: 3
A | Oyster | Marathon/Texaco | Ewing Bank 917 | SS | 361.1704 | 1185 |  | ** | 1997 | Flowing Gas Additions: 1996: 5
A | Lafitt Pincay (Sun Silence) | Tatham | Ewing Bank 958/1003 | FPS/SPAR | 441.9384 | 1450 | Leviathon |  | 1998/99 | Flowing Gas Additions: 1998: 40; Flowing Gas Additions: 1999: 10
A | Arnold | Marathon | Ewing Bank 963 | SS | 533.9835 | 1752 |  |  | 1999 | Flowing Gas Additions: 1999: 0
A | Black Widow | Shell | Ewing Bank 966 | SS |  |  |  |  | 1999 | Flowing Gas Additions: 1999: 5
A |  | Marathon | Ewing Bank 1006 | [5 empty] | 1998 | Flowing Gas Additions: 1998: 10
A | Spend-a-buck | Flextrend | Garden Banks 117 | SS | 298.0799 | 978 | ANR/Leviathon | ** | 1996-07-01 | Flowing Gas Additions: 1996: 6
A | Cooper | Ensearch | Garden Banks 387/8 | FPS | 659.2502 | 2163 | Tennessee Blue Water | ** | 1995-09-01 | Flowing Gas Additions: 1996: 11; Flowing Gas Additions: 1997: 4
A | Enchilada | Shell | Garden Banks 128 |  | 0 |  | Garden Banks | ** | 1997-10-01 | Flowing Gas Additions: 1997: 100; Flowing Gas Additions: 1998: 200
A | Salsa | Shell/Hess/Oryx | Garden Banks 171 |  | 344.4072 | 1130 | Garden Banks |  | 1998
A | Tick | Texaco | Garden Banks 189 |  | 218.8357 | 718 |  | ** | 1992 | Flowing Gas Additions: 1996: 75
A |  | AGIP | Garden Banks 208 |  | 380.9814 | 1250 |  |  | 2001 | After 2000: 25
A | Penn State | Hess | Garden Banks 216 | SS | 441.9384 | 1450 | Garden Banks |  | 1998 | Flowing Gas Additions: 1998: 50; Flowing Gas Additions: 1999: 102
A |  | Marathon | Garden Banks 253 |  | 426.6992 | 1400 |  |  | 1999 | Flowing Gas Additions: 1999: 25
A |  | Chevron | Garden Banks 254 |  | 585.1874 | 1920 |  |  | 2002 | After 2000: 25
A | Baldpate (Antioch) | Hess | Garden Banks 259/260 | CT | 493.4471 | 1619 | Garden Banks |  | 1998-09-01 | Flowing Gas Additions: 1998: 50; Flowing Gas Additions: 1999: 102; Flowing Gas Additions: 2000: 48
A | Mosquitto Hawk | Texaco | Garden Banks 269 |  | 335.8732 | 1102 |  |  | 2000 | Flowing Gas Additions: 2000: 25
A |  | Conoco | Garden Banks 302 |  | 734.8369 | 2411 |  |  | 2000 | Flowing Gas Additions: 2000: 25
G | Dulcimer | Mariner Energy | Garden Banks 367 | SS | 341.3593 | 1120 |  |  | 1999 | Flowing Gas Additions: 1999: 15
A | Knight | Santa Fe | Garden Banks 372 |  | 530.3261 | 1740 |  |  | 2000 | Flowing Gas Additions: 2000: 25
A | GB 386 | Ensearch | Garden Banks 386 | SS | 701.0058 | 2300 |  |  | 1999 | Flowing Gas Additions: 1999: 25
A | Cooper | Ensearch | Garden Banks 388 | FPS | 651.021 | 2136 |  | ** | 1995 | Flowing Gas Additions: 1996: 16
A | Ladybug | Texaco | Garden Banks 409 |  | 412.9838 | 1355 |  |  | 2002 | After 2000: 4
A | Auger | Shell | Garden Banks 426/7/470/1 | TLP | 872.9046 | 2864 | ANR/Garden Banks | ** | 1994-04-01 | Flowing Gas Additions: 1996: 155; Flowing Gas Additions: 1997: 85
A | Serrano | Shell | Garden Banks 516 | SS | 960.9875 | 3153 | ANR/Garden Banks |  | 2000 | Flowing Gas Additions: 2000: 25
A |  | Marathon | Garden Banks 543 |  | 609.5703 | 2000 |  |  | 2001 | After 2000: 25
A | Macaroni | Shell | Garden Banks 602 | SS | 1122.8284 | 3684 | tied into Auger/Garden Banks |  | 1999 | Flowing Gas Additions: 1999: 65
| Hardy | Texaco | Grand Island 115 |  | 0 |  | Discovery
A | Boxer | Shell | Green Canyon 19 |  | 230.7223 | 757 |  | ** | 1988
A | Rocky | Shell | Green Canyon 110 | SS | 494.0567 | 1621 | Manta Ray/Nautilus | ** | 1996-01-01 | Flowing Gas Additions: 1996: 7; Flowing Gas Additions: 1997: -6
A | Stellaria | Marathon/Shell | Green Canyon 112 |  | 623.2856 | 2045 |  |  | 2002 | After 2000: 25
A | Angus | Shell/Marathon | Green Canyon 113 | SS | 609.5703 | 2000 | tie into Bullwinkle |  | 1999 | Flowing Gas Additions: 1999: 60
A | Popeye | Shell | Green Canyon 116 | SS | 630.2956 | 2068 | Nautilus | ** | 1996-01-01 | Flowing Gas Additions: 1996: 105; Flowing Gas Additions: 1997: -39; Flowing Gas Additions: 1998: 97
A | Grand Canyon | Conoco | Green Canyon 141 |  | 522.7065 | 1715 |  |  | 2001 | After 2000: 25
A |  | Marathon | Green Canyon 153 |  | 457.1777 | 1500 |  |  | 2004 | After 2000: 0
A | Brutus | Shell | Green Canyon 158 | SS | 876.8668 | 2877 | Manta Ray/Nautilus |  | 2002 | After 2000: 60
A | Bison | Exxon | Green Canyon 166/106 |  | 767.4489 | 2518 |  |  | 2001 | After 2000: 15
A | Jolliet | Texaco/Conoco | Green Canyon 184 | TLP | 524.2304 | 1720 | Tennessee Blue Water | ** | 1989-11-01 | Flowing Gas Additions: 1996: 25; Flowing Gas Additions: 1997: 5; Flowing Gas Additions: 1998: 35
A | Genesis | Chevron | Green Canyon 205 | SPAR | 792.1365 | 2599 | Transco |  | 1999 | Flowing Gas Additions: 1999: 72
A | Troika | BP Exploration | Green Canyon 200/1,244/5 | SS | 829.3203 | 2721 | Nautilus | ** | 1997-12-01 | Flowing Gas Additions: 1997: 5; Flowing Gas Additions: 1998: 135
A | Glider | Shell | Green Canyon 248 | TLP | 1005.7909 | 3300 |  |  | 2001 | After 2000: 60
G | Allegheny | Ensearch | Green Canyon 254 | FPS | 971.0454 | 3186 | Discovery |  | 1999 | Flowing Gas Additions: 1999: 35
A | King Kong | British-Borneo/Shell | Green Canyon 472/473/517 |  | 1163.3648 | 3817 |  |  | 2000 | Flowing Gas Additions: 2000: 125
A | Fuji | Texaco | Green Canyon 506 |  | 1302.9564 | 4275 |  |  | 2002 | After 2000: 100
A | Bullwinkle | Shell | Green Canyon 65 | FP | 405.3642 | 1330 | Manta Ray/Nautilus | ** | 1989-07-01 | Flowing Gas Additions: 1996: 10; Flowing Gas Additions: 1997: 5; Flowing Gas Additions: 1998: 86
A | Poseiden | BP Exploration | Green Canyon 691 |  | 1368.1804 | 4489 |  |  | 2003 | After 2000: 25
A | Shasta | Texaco | Green Canyon 92,136/7 | SS | 316.9765 | 1040 | Tennessee Blue Water | ** | 1995-11-01 | Flowing Gas Additions: 1996: 60; Flowing Gas Additions: 1997: -25
A | Nemo | CNG | Main Pass 279 |  | 88.3877 | 290 | Destin |  | 1998-12-01
A | Nautilus | CNG | Main Pass 280 |  | 93.569 | 307 | Destin |  | 1999-01-01
A | Atlantis | CNG | Main Pass |  |  |  | Destin |  | 1999-01-01
| Snyder |  | Main Pass 261 A-3/4/5 |  |  |  | Transco | ** | 1998-08-01 | Flowing Gas Additions: 1998: 180
|  | BP | Mississippi Canyon 26 |  | 387.6867 | 1272 |  |  | 2001 | After 2000: 25
A | Pompano II | BP | Mississippi Canyon 28 | SS | 568.4243 | 1865 | Tennessee/VK | ** | 1996-07-01 | Flowing Gas Additions: 1996: 7; Flowing Gas Additions: 1997: 7
A | King | Amoco | Mississippi Canyon 84 | SS | 1569.3386 | 5149 | Destin |  | 2001 | After 2000: 40
A | Amberjack | BP Exploration | Mississippi Canyon 109 | FP | 313.6239 | 1029 | Transco | ** | 1991-10-01 | Flowing Gas Additions: 1996: 7
A | Nirvana | BP Exploration | Mississippi Canyon 162 | FP | 1040.5364 | 3414 |  |  | 1999 | Flowing Gas Additions: 1999: 25
A | Cognac | Shell | Mississippi Canyon 194 | FP | 311.7952 | 1023 | SoNat | ** | 1980-09-01 | Flowing Gas Additions: 1996: 60; Flowing Gas Additions: 1999: 60
A | Mickey | Exxon | Mississippi Canyon 211 | SS | 1327.644 | 4356 |  |  | 2002 | After 2000: 75
A |  | Conoco | Mississippi Canyon 243 |  | 944.8339 | 3100 |  |  | 2001 | After 2000: 25
A | King's Peak | Amoco | Mississippi Canyon 260/1 | SS | 1990.2469 | 6530 | Destin |  | 2000 | Flowing Gas Additions: 2000: 40
A | Lena | Exxon | Mississippi Canyon 281 | CT | 310.2713 | 1018 | Texas Eastern/Destin | ** | 1984-05-01 | Flowing Gas Additions: 1996: 15; Flowing Gas Additions: 1997: 4; Flowing Gas Additions: 1998: 40
A | Gemini | Texaco/Chevron | Mississippi Canyon 291/292/247 | SS | 1146.9064 | 3763 | Destin |  | 2000 | Flowing Gas Additions: 2000: 100; After 2000: 100
A |  | Shell | Mississippi Canyon 311 |  | 122.5236 | 402 |  | ** | 1980 | Flowing Gas Additions: 1996: 115
G | Alabaster | Exxon/Ensearch | Mississippi Canyon 397 | FP | 322.7674 | 1059 | SoNat | ** | 1992-04-01 | Flowing Gas Additions: 1996: 85; Flowing Gas Additions: 1997: -50; Flowing Gas Additions: 1998: 70
G | Zinc | Exxon | Mississippi Canyon 354 | SS | 450.4724 | 1478 | SoNat | ** | 1993 | Flowing Gas Additions: 1996: 40; Flowing Gas Additions: 1998: 80
G |  | Somedan | Mississippi Canyon 365 |  | 187.4429 | 615 |  | ** | 1992 | Flowing Gas Additions: 1996: 80
A |  | Shell | Mississippi Canyon 383 |  | 1746.114 | 5729 |  |  | 2002 | After 2000: 50
G | Diamond | Oryx | Mississippi Canyon 401/445 | SS | 638.5248 | 2095 | SoNat | ** | 1993-07-01 | Flowing Gas Additions: 1996: 30; Flowing Gas Additions: 1997: -25
A | Nakika | Amoco/Shell | Mississippi Canyon 429/522/383 |  | 1912.2219 | 6274 | Destin |  | 2001 | After 2000: 50
G |  | Ensearch | Mississippi Canyon 441 | SS | 463.2734 | 1520 |  |  | 1993
A |  | AEDC | Mississippi Canyon 486 | SS | 365.7422 | 1200 |  |  | 2003 | After 2000: 25
| Leo | British-Borneo | Mississippi Canyon 502 |  | 761.9628 | 2500
A |  | Shell | Mississippi Canyon 520 |  | 2053.947 | 6739 |  |  | 2003 | After 2000: 50
A | Fourier | Shell | Mississippi Canyon 522 |  | 2118.2566 | 6950 |  |  | 2001 | After 2000: 50
A | Narcissus | Texaco | Mississippi Canyon 638 |  | 1295.3368 | 4250 |  |  | 2004 | After 2000: 37
A | Coulomb | Shell | Mississippi Canyon 657/655 |  | 2291.9842 | 7520 |  |  | 2005 | After 2000: 100
A | Gomez | UPR | Mississippi Canyon 711 |  | 914.3554 | 3000
A | Blood Sweat & Tears | BP Exploration | Mississippi Canyon 718 |  | 849.1314 | 2786 |  |  | 1999 | Flowing Gas Additions: 1999: 60
G | Mensa | Shell | Mississippi Canyon 686/687/730/731 | SS | 1638.5248 | 5376 | Mississippi Canyon Gath | ** | 1997-07-01 | Flowing Gas Additions: 1997: 108; Flowing Gas Additions: 1998: 192
A | Gomez | UPRC | Mississippi Canyon 755 | Spar/TLP | 914.3554 | 3000 |  |  | 2000 | Flowing Gas Additions: 2000: 60
A | King | Vastar | Mississippi Canyon 764 |  | 1005.7909 | 3300 |  |  | 2003 | After 2000: 25
A | Mars | Shell | Mississippi Canyon 807 | TLP/SS | 901.5544 | 2958 | TETCO(WD143)/MCGS | ** | 1996-07-01 | Flowing Gas Additions: 1996: 30; Flowing Gas Additions: 1997: 80; Flowing Gas Additions: 1999: 90
A | Ursa | Shell | Mississippi Canyon 854/810 | TLP | 1225.541 | 4021 | Mississippi Canyon Gath |  | 2000 | Flowing Gas Additions: 2000: 80; After 2000: 320
| Metallica | BP Exploration | Mississippi Canyon 911 |  | 2133.4959 | 7000
A | Europa | Shell/BP/Conoco | Mississippi Canyon 934/5 890/1 |  | 1185.3094 | 3889 | tie into Mars |  | 2000 | Flowing Gas Additions: 2000: 45
A | Mirage/Zeus | Vastar/Unocal | Mississippi Canyon 941 |  | 1190.1859 | 3905 | Mississippi Canyon Gath |  | 2002 | After 2000: 40
A | Venus | Shell | Mississippi Canyon 853/97 |  | 1155.1356 | 3790 |  |  | 2001 | After 2000: 50
A | Flathead | Shell | Mississippi Canyon 899 |  | 1356.9034 | 4452 |  |  | 2001 | After 2000: 50
A | Mahogany | Phillips | Ship Shoal 349/359 |  | 112.7705 | 370 | Manta Ray/Nautilus | ** | 1996 | Flowing Gas Additions: 1996: 30; Flowing Gas Additions: 1998: 75
| Agate | Phillips | Ship Shoal 360/361 |  | 0 |  | Transco |  | 1998 | Flowing Gas Additions: 1998: 50
| Spirit | Shell | Viosca Knoll 780 |  |  |  | Destin
A | Tahoe I & II | Shell | Viosca Knoll 783/784 | SS | 425.1753 | 1395 | Tennessee/VK & Destin | ** | 1994-01-01 | 25 | 80 | 50 | 150
will increase with Destin ID
A | Petronius | Texaco/Marathon | Viosca Knoll 786 | CT | 534.5931 | 1754 | Tennessee/VK |  | 1999 | Flowing Gas Additions: 1999: 100; Flowing Gas Additions: 2000: platform dropped in sea
G | Phar Lap | Tatham | Viosca Knoll 817 |  | 205.4252 | 674 | Tennessee/VK | ** | 1995 | Flowing Gas Additions: 1996: 65
G | Virgo | Elf | Viosca Knoll 823 | FPS | 344.4072 | 1130 | DIGS II |  | 2000 | Flowing Gas Additions: 2000: 200
A | Thor | Oryx | Viosca Knoll 825 | SPAR | 521.1826 | 1710 | DIGS II
A | Neptune | Oryx | Viosca Knoll 826 | SPAR | 588.2353 | 1930 | TETCO (73071) | ** | 1997-03-01 | Flowing Gas Additions: 1997: 20; Flowing Gas Additions: 1999: 20
A | VK 862 | Walter Oil | Viosca Knoll 862 | SS | 317.8909 | 1043 |  | ** | 1995 | Flowing Gas Additions: 1997: 5
| Fuji | Amoco | Viosca Knoll 872 |  | 0 |  | Destin |  | 2000 | Flowing Gas Additions: 2000: 100
A | Marlin | Amoco | Viosca Knoll 915 | SPAR | 986.2847 | 3236 | Destin |  | 2Q 1999 | Flowing Gas Additions: 1999: 250
A | Ram-Powell | Shell | Viosca Knoll 956 | TLP | 992.0756 | 3255 | Tennessee/VK | ** | 1997-09-01 | Flowing Gas Additions: 1997: 56; Flowing Gas Additions: 1998: 140
A | Pompano | BP Exploration | Viosca Knoll 989/990 | FP/SS | 451.9963 | 1483 | SoNat | ** | 1995-08-01 | Flowing Gas Additions: 1996: 2; Flowing Gas Additions: 1997: 1; Flowing Gas Additions: 1998: 60
|  | OEDC | Viosca Knoll 35 |  | 395.0015 | 1296 |  | ** | 1997-08-01 | Flowing Gas Additions: 1996: 3; Flowing Gas Additions: 1997: 1
| Cornell | Texaco | West Delta 109 |  | 0 |  | Tennessee/VK | ** |  | Flowing Gas Additions: 1996: 20; Flowing Gas Additions: 1997: 30; Flowing Gas Additions: 1998: 25
| TOTAL | [8 empty] | 1192 | 476 | 1685 | 1271 | 1053 | 1706

## 1995
ENRON CAPITAL & TRADE RESOURCES |  |  | 2025-09-26 23:09
PIPELINE EXPANSION UPDATE
[8 empty] | Project | Cost of
|  |  |  | Daily | Start | ECT |  | Term | Project
| Pipeline | Project | Path | Quantity | Date | Position | Docket | Years
West:
| Tuscarora | Sierra Pacific/TCPL | PGT Malin to Reno, NV | 110000 | 1995-11-01
| El Paso | San Juan Basin Triangle Fac. |  | 300000 | 1995-12-01
| Kern River |  | Opal to Bakersfield | 700000 | 1992-03-01
Midwest:
| Crossroads | NIPSCO | Chicago to Columbia Gas | 250000 | 1995-10-01
| Bluewater |  |  | 250000
Southeast:
| Transco |  |  | 115000 | 1995-11-01
| Florida Gas Transmission | Phase III |  | 535000 | 1995-03-01
| Transco | Eminence Salt Dome Storage | Increase Capacity by 3.0 to 15.0 Bcf | 0
Texas:
| TECO |  |  | 300000
Deep Water Louisiana:
Gateway
| Transco | Mobile Bay |  | 829000 | 1994-12-01 | 100000 |  | 5
DIGS

## Commit
ENRON CAPITAL & TRADE RESOURCES |  |  |  |  | 2025-09-26 23:09
Pipeline Capacity Purchases
|  | Capacity | Term | Start | Cumulative
Pipeline | Route | per day | (Years) | Date | Volume
Calendar Year 1996
CIG | Opal to White Rock | 175 | 1 | 1996-04-01 | 63875
Transco | Mobile Bay | 100000 | 5 | 1996-07-01 | 182500000
Iroquois | Waddington to S. Comack | 15000 | 10 | 1996-11-01 | 54750000
TCPL | Empress to Waddington | 15000 | 10 | 1996-11-01 | 54750000
Questar | MAP 106 to 164 | 7000 | 1 | 1996-11-01 | 2555000
PGT | Stanfield to Malin | 10000 | 0.5 | 1996-12-01 | 1825000
Transwestern | San Juan to East Points | 8000 | 5 | 1996-12-01 | 14600000
|  | 155175 | 5.4917 |  | 311043875
Calendar Year 1997
NWPL | Texaco Cap Release | 15000 | 5 | 1997-02-01 | 27375000
CIG |  | 12000 | 0.5 | 1997-05-01 | 2190000
El Paso | San Juan to East | 16495 | 5 | 1997-05-01 | 30103375
NOVA | AECO to A/BC Border | 67500 | 11.26 | 1997-07-01 | 277418250
ANG | A/BC Border to Kingsgate | 67500 | 11.26 | 1997-07-01 | 277418250
PGT | Kingsgate to Malin | 67500 | 26.26 | 1997-07-01 | 646980750
PGT | Kingsgate to Malin | 10000 | 6 | 1997-11-01 | 21900000
TCPL | Empress to Niagara | 21344 | 10 | 1997-11-01 | 77905600
National Fuel | Niagara to Leidy | 25000 | 10 | 1997-11-01 | 91250000
Transco | Leidy to NYC | 30000 | 15 | 1997-11-01 | 164250000
|  | 332339 | 13.3285 |  | 1616791225
Calendar Year 1998
NOVA | AECO to Empress | 35000 | 9.25 | 1998-01-01 | 118168750
TCPL | Empress to Waddington | 35000 | 9.25 | 1998-01-01 | 118168750
Iroquois | Waddington to Wright | 35000 | 9.25 | 1998-01-01 | 118168750
Tennessee | Wright to Boston | 35000 | 9.25 | 1998-01-01 | 118168750
Transwestern | Ignacio to Border | 55000 | 5 | 1998-07-01 | 100375000
El Paso | Bondad Expansion | 100000 | 10 | 1998-11-01 | 365000000
Great Lakes | Emerson to St. Clair | 30000 | 10 | 1998-11-01 | 109500000
TCPL | Empress to Emerson | 30000 | 10 | 1998-11-01 | 109500000
NOVA | AECO to Foothills | 15000 | 10 | 1998-11-01 | 54750000
Foothills | Foothills to Monchy | 15000 | 10 | 1998-11-01 | 54750000
NBPL | Monchy to Chicago | 55000 | 10 | 1998-11-01 | 200750000
NBPL | Ventura to Chicago | 75000 | 10 | 1998-11-01 | 273750000
NGPL | Harper to Chicago | 15000 | 10 | 1998-11-01 | 54750000
Portland | Border to Dracut | 30000 | 20 | 1998-11-01 | 219000000
NGPL | Panola Co to Louisiana | 50000 | 3 | 1998-03-01 | 54750000
|  | 610000 | 9.2951 |  | 2069550000
Calendar Year 1999
TCPL | Empress to Emerson | 20000 | 10 | 1999-11-01 | 73000000
73000000
Capacity Release Percentage |  |  |  |  | 47.19%