## Sheet1
Application | Production Version | Date Moved to Production | Nature of Request/Bug Fix | Requested By | Date Requested | Developer | Developer Priority | Users | Date Moved To Stage (User Testing) | Test Version | Assigned QA | Status Update Date | Status | Same Day Fix | In User Test
Build Route Report | 3.0.3.10 |  | Modifications for Daylight Savings Time | Cara Semperger | 2001-10-01 | Vish |  | David Poston, Corry Bentley, Cara Semperger | 2001-10-02 | 3.0.3.9 | Karen | 2001-10-03 | In Production
CARP |  |  | Modify CARP report to allow user to specify a deal number in the parameters and that will give a CARP based only on that one deal for any given date range. | Scotty Gilbert | 2001-08-29 | Bill Crooks | 1 | Scotty Gilbert, Melissa Ratnala |  |  |  |  | Work In Progress
CARP |  |  | Streamline CARP for reconciliation export. | Thresa Allen |  | Bill Crooks | 2 | [5 empty] | Work in Progress
Deal Blotter - DealBlotter.exe | 5.2.2.541 | 2001-05-09 | Legal Secondary Legal Entity functionality. Add ability to enter monthly options. This functionality will also be applied to Deal Entry and possibly Option Exercise. | Stacey White |  | DC | 1(Legal Entity) | Corry Bentley, Hai Chen, Donnie Vinson |  |  |  |  | Work In Progress
Deal Blotter - DealBlotter.exe |  |  | Remove all inactive criteria from selection list. | Casey Evans | 2001-08-08 | DC | 2 |  |  | 3.0.0.212 | Karen |  | QA Testing.
Deal Blotter - DealBlotter.exe (Enhancement to EOL Bridge)/Deal Entry - Pdeal.exe |  |  | Change Ercot Imbalance Deals to resemble the California Imbalance Deals, in that it removes the mark to market flag associated with the transactions. | Tom Chapman | 2001-08-01 | Kroum/DC |  | Tom Chapman |  | 3.0.0.212 | Karen |  | QA Testing.
Deal Blotter |  |  | Multi user read only access to one trader's blotter. Note: It may be best to accomplish this functionality using deal ticker. | Kate Symes | 2001-09-20 | Kroum |  | Kate Symes
Deal Data Upload |  |  | Add the ability to update transmission volume and prices | Rebecca Grace | 2001-08-10 | Chuck |  | Rebecca Grace, Kathy Reeves | 2001-10-17 | 1.2.0.3 |  | 2001-10-17 | In Stage. User testing.
Deal Entry |  |  | Warning message when selecting inactive counterparties, delivery points, ect. Note: Cannot be done until Kroum finishes current changes | Casey Evans | 2001-08-08 | DC | 1 |  | 2001-08-08 | 3.0.0.196 |  |  | In Stage. User testing.
Deal Entry |  |  | Remove the mark to market flag associated with the transactions for Ercot Imbalance Deals. Other changes to deal entry must be completed prior to this change. | Tom Chapman | 2001-08-01 | DC |  | Tom Chapman |  |  |  |  | Work In Progress
Deal Entry |  |  | Deals done under the EPMI Short Term West Hourly desk should default to 'not confirmed'. | Kate Symes | 2001-08-15 | Kroum |  | Kate Symes
Deal Entry |  |  | Add credit watch information. | Stacey White | 2001-09-19 | Kroum |  | Stacey White, Casey Evans
Deal Entry |  |  | Add capability to handle deals between identical desks. | Casey Evans | 2001-09-04
Deal Entry/Deal Blotter |  |  | Change default interest rate and Canadian deals | Kathy Reeves | 2001-08-22 | Kroum
Deal Entry/Deal Blotter |  |  | Canadian Holiday Masks | Mark Dupuy | 2001-10-16 | Kroum | 4 | Mark Dupuy
Deal Entry/Deal Blotter/EOL Bridge |  |  | Set defaults based on firmness codes | Melissa Murphy | 2001-09-19 | Kroum/Vish
Deal Entry/Deal Blotter/EOL Bridge |  |  | Add flag in Deal Entry to prevent transaction confirmation. | Melissa Murphy | 2001-09-19 | Kroum/vish
Deal Entry |  |  | Add additional field to Deal Batch Processing functionality to batch change the deal date in a deal with a number of legs. | Casey Evans | 2001-09-17 | Kroum |  | Casey Evans |  |  | Karen | 2001-09-18 | Work In Progress. Found issue during testing. Kroum is creating a vew version to correct error.
Deal Entry |  |  | Implement summary of emmissions deals | Heather Dunton | 2001-09-19 | Kroum/DC
Deal Entry |  |  | Add ability to UNKILL all legs on a deal | Casey Evans | 2001-10-08 | Kroum
Deal Scheduling | 2.0.0.60 | 2001-10-10 | Show cross portfolio deals | Heather Dunton | 2001-07-31 | Kroum |  | Cara Semperger, Corry Bentley, Heather Dunton | 2001-09-10 | 2.0.0.60 | Karen | 2001-10-10 | In Production
Deal Ticker - DealTicker.exe | 5.3.4.9 | 2001-07-17 | Nikolay is adding functionality to select multiple regions. | Corry Bentley |  | DC | 1 | Corry Bentley | 2001-08-16 | 5.3.9.12 | Karen | 2001-08-16 | Moved to stage. Notified user
Entrans - Entrans.Exe |  |  | Add service deals to transmission report. | Michael Jacobson | 2001-08-28 | Kroum |  | Michael Jacobson | 2001-08-29 | 1.0.4.22 | Karen | 2001-09-12 | Moved to stage. Notified user Corry found a problem during testing, however the developer could not recreate the problem.
EOL Bridge |  |  | Modify logic to accommodate trades done through he Mid Marketer trading application being released into production. (Changes include modifying the existing borker/external trading platform logic so that when the bridge sees a deal where there is an external exchange Global ID and no external deal number, it looks to see if the Global ID being provided for the external exchange matches the list of current brokers programmed into the bridge. If the code does not match, the bridge should default a broker name of "ORIG" into Enpower. | Torrey Moorer | 2001-08-24 | Vish | 1 | [5 empty] | Move to production 10/10/01.
Ercot Price Download |  |  | Download pub prices for Ercot. | Rebecca Grace |  | Chuck | 1
Expiry Time (Deal Entry) |  |  | Add additional column for expiry time. | Melissa Murphy | 2001-07-20 | Kroum | 3 | Melissa Murphy |  |  |  |  | On hold…per Melissa. |  | y
Financial Liquidation - FinLiq.exe | 3.9.1.0 | 2001-10-24 | Nikolay is adding modifications for interdesk transactions | Casey Evans |  | Nikolay | 1 | Casey Evans, Rebecca Grace, Elsie Lew, Kim Durham | 2001-10-04 | 3.9.1.0 | Karen | 2001-10-10 | In Production
Forward Obligation |  |  | Show basis options on reports. | Cara Semperger | 2001-07-30 | Kroum |  | Corry Bentley, Heather Dunton, Kate Symes, Cara Semperger, Mike Tully | 2001-07-21 | 3.1.0.41 | Karen |  | In stage, User found error during testing.
Nepool report |  |  | Firm Purchase/Firm Sale for SR_Energy. Nepool system border added to delivery points. Link ENWENGPOW deals to market products. Modify headers to correct inaccurate descriptions. Implement Boston Edison fix in cc_confirm reconciliation report. EES contract number is not pulling correctly. | Rebecca Grace | 2001-08-08 | Chuck | 1 | Rebecca Grace
New Deal Summary - NewDealSum.exe | 1.2.2.11 | 2001-04-20 | break the Price column in the New Deal Summary into two separate columns - peak and off-peak | Casey Evans | 2001-05-03 | Nikolay | 4 | Stacey White, Donnie Vinson, Casey Evans |  |  |  |  | Work In Progress
New Deal Summary - NewDealSum.exe |  |  | Add counterpary selection. For deals that show as two rows, zeroe out the second row. | John Postelwaithe | 2001-10-05 | Nikolay |  | Casey Evans,Jon Paul Lewis, John Postelwaite | 2001-10-09 | 1.0.1.0 | Karen | 2001-10-09 | In Stage, awaiting user testing.
NYISO Price Download/PJM |  |  | Drop down selection of indexes to download. Date range selection. Real time or day ahead indicator. Zonal or generator indicator. New option for PJM downloads to make use of Pub Code mapping table to eliminate existing default PJM ini files. | Rebecca Grace | 2001-08-08 | Chuck | 2 | Rebecca Grace
Option Obligation |  |  | add ability to choose a single desk and view all deals where the desk is either a counterparty or Enron. |  |  | Nikolay/Vish | 2 | Hai Chen |  |  |  |  | User is using shortcut to access report. Work in progress, no production version.
PCS/PID |  |  | Print transmission deals only in PCS. Break out annuity deals in PCS and PID. C alculate demand charge directly in PCS and PID. | Fran Chang | 2001-08-22 | Nikolay
Refresh Global Data |  |  | When refreshing global data, the old data is first deleted ant then the new data is refreshed from the Global tables. If there is a problem with the Global table (and it is empty) we're hosed. The app. should check to see if there is data in global BEFORE deleting any existing data | Duong Luu | 2001-08-16 | D.C. | 2 | [5 empty] | Work in progress. Waiting for response from M. Berger.
Schedule Extraction |  |  | Modified report to show all 24 hours on a legal size page (landscaped) when printed. | Corry Bentley | 2001-09-25 | Nikolay |  | Corry Bentley | 2001-10-09 | 2.1.1.18 | Karen | 2001-10-09 | Moved to stage. Notified user.
Table Edit |  |  | Modify autoconfirm rules to add new criteria. | Melissa Murphy | 2001-09-19 | Vish
Table Edit |  |  | Support secondary legal entity CP ID. | Donnie Vinson | 2001-10-05 | D.C. |  | Donnie Vinson, Melissa Murphy, John Postelwaithe, Kathy Reeves | 2001-10-09 | 1.1.1.1 | Karen | 2001-10-09 | Moved to stage. Notified user.
WestDeskVolumes |  |  | Consolidate data from WestDeskVolumes Report with data from FERC report. | Will Smith | 2001-08-09 | Nikolay | 5
y
y