## 09142001
EES Reconciliation Project Scorecard – Power
| Totals from RGS |  | Deals reconciled from Usage to RGS |  |  | Deals reconciled to Contracts |  |  | Investment
State/Utility | # Customers in RPS | # Deals in RPS | # Customers Not In RPS | June Volume for Customers | Invoice Amt (Potential P/L Impact)) | # Deals Completed | # Deals w/ Incomplete Documentation | % Complete based on Volume | Actual cost as (9/21/2001) | Estimated Cost to Date | Estimated Remaining Cost for 90% Coverage on Deal Volume | Estimated Remaining for 100% of Deals
CA
PG&E | 8 | 340 | *1 | *1 | *1 | 0 | *2 | #VALUE! | TBD | TBD | TBD | TBD
SCEG | 10 | 565 | *1 | *1 | *1 | 1 | *2 | #VALUE! | TBD | TBD | TBD | TBD
SDG&E | 8 | 173 | *1 | *1 | *1 | 13 | *2 | #VALUE! | TBD | TBD | TBD | TBD
IL
COMED | 54 | 742 | *1 | *1 | *1 | 320 | *2 | #VALUE! | TBD | TBD | TBD | TBD
ME
BHE | 10 | 34 | *1 | *1 | *1 | 0 | *2 | #VALUE! | TBD | TBD | TBD | TBD
CMP | 141 | 363 | *1 | *1 | *1 | 0 | *2 | #VALUE! | TBD | TBD | TBD | TBD
MA
BECO | 103 | 267 | *1 | *1 | *1 | 57 | *2 | #VALUE! | TBD | TBD | TBD | TBD
WMECO | 11 | 36 | *1 | *1 | *1 | 0 | *2 | #VALUE! | TBD | TBD | TBD | TBD
MECO | 103 | 197 | *1 | *1 | *1 | 39 | *2 | #VALUE! | TBD | TBD | TBD | TBD
NJ
JCP&L | 30 | 207 | *1 | *1 | *1 | 45 | *2 | #VALUE! | TBD | TBD | TBD | TBD
PSE&G | 47 | 954 | *1 | *1 | *1 | 70 | *2 | #VALUE! | TBD | TBD | TBD | TBD
NY
CONED | 1015 | 1981 | *1 | *1 | *1 | 710 | *2 | #VALUE! | TBD | TBD | TBD | TBD
OH
Ohio Ed. | 6 | 117 | *1 | *1 | *1 | 24 | *2 | #VALUE! | TBD | TBD | TBD | TBD
TOTAL | 1546 | 5976 | 0 | 0 | 0 | 1324 | 0 |  | 0 | 0 | 0 | 0
| Actual Cost as (9/28) |  |  |  | Estimated cost to date | Estimated Cost to Complete
| Database Support | [6 empty] | *1 | Currently we have not yet set up the CSC reconciliation database.
| Contract Administration | [7 empty] | We estimate starting this by Monday, 10/1/2001.
[8 empty] | *2 | This work is in progress; to be completed by mid of next week.
** All results for data dump as of 9/13/2001.