## Sheet1
Transwestern Project Sun Devil
ENSR Cost Estimate for Environmental Support |  |  | REVISED 9/20/01 - 1530 mdt
Project Manager: Scott Patti
|  | Phase I | Phase II | Phase III
|  | thru 3/2002 | thru 12/2002 | thru in-service
TASKS |  | SUBTOTAL | SUBTOTAL | SUBTOTAL
1 | Data Collection and Review | 30000
2 | Agency Consultation | 30000 | 10000 | 20000
3 | Route Selection | 30000
4 | Wildlife Habitat/Land Use Field Surveys | 30000
5 | T&E Species Surveys |  | 160000
6 | Wetland Delineation and Report | 120000
7 | Cultural Resources Survey and Report | 400000 | 100000
8 | Cultural Resources Testing/Mitigation |  | 300000 | 500000
9 | Cultural Resources Management | 30000 | 45000 | 60000
10 | FERC Resource Reports | 100000
11 | Response to FERC Data Requests |  | 20000
12 | Biological Assessment | 30000
13 | Map/Alignment Sheet Review | 15000
14 | Section 404 Permits |  | 25000
15 | 404 Permit Conditions Follow-Up |  | 11000
16 | Air Quality Permits | 20000 | 20000
17 | Water Withdrawal/Discharge Permits |  | 25000
18 | Agency/Public Meetings | 30000 | 20000 | 20000
19 | Coordination Meetings | 30000 | 30000 | 30000
20 | Project Management | 50000 | 75000 | 150000
21 | GIS Web Page Set Up & Maintenance | 20000 | 30000 | 20000
22 | Environmental Compliance Plan Prep |  | 50000
23 | EIS Review and Input |  |  | 10000
24 | Implementation Plan Preparation |  |  | 10000
25 | Permit Book Preparation |  |  | 15000
26 | Permit Compliance Tracking |  |  | 35000
27 | Env. Inspector Management |  |  | 30000
28 | Env. Inspector Subcontract |  |  | 1584000
29 | Hydrotest Discharge Water Analysis |  |  | 15000
30 | Environmental Training Support |  |  | 15000
31 | Field Support |  |  | 35000
32 | Restoration Support |  |  | 15000
| ENSR PROJECT TOTAL | 965000 | 921000 | 2564000
| Third-Party Contractor | 150000 | 350000 | 50000
|  | Phase I | Phase II | Phase III
| PROJECT TOTAL BY PHASE | 1115000 | 1271000 | 2614000
| GRAND TOTAL - ENVIRONMENTAL |  | 5000000
Assumption: Environmental Inspector subcontract costs assume 6 spreads, 2 EIs per spread, $11,000/per month/EI, and
a 12-month construction season. For a 9-month construction schedule, assume 8 spreads, 2 EIs per spread, and
$11,000/month/EI.