## Sheet1
Agreements Receiving DASH Approval
|  | Total Cost |  | Form Approved by
Agreement | Description | Current | Projected | Acct | Fin
FPUA Technical Services Agreement (FPUA/FPRP) | Reimburses FPUA for costs associated with work FPRP had agreed to perform. Costs relate to the relocation of a power distribution line, refurbishment of an existing fuel tank, demolition of two existing fuel tanks and remediation work necessary to clear the site for construction |  | 575000 | Under Review | Under Review
2nd Amendment to Option to Lease (FPUA/FPRP) | Amends the Option to Lease to include the work associated in the aforementioned TSA |  | 0 | Under Review | Under Review
Cockerill Mechanical Industries HRSG Contract (ENA/CMI) | In addition to the costs associated with the entire HRSG construction, the CMI HRSG contract includes two initial payments which will be used for design and specification work. These payments will provide FPRP with the “option” to cancel the procurement and construction phase through the end of March. |  |  | Under Review | Under Review
| (through Feb) |  | 156000
| (through Mar) |  | 150000
Technical Design Services Agreement (FPRP/Stone & Webster) | Relates to design and specification work associated with the design of the project Facilities. Under this arrangement, the EPC contractor will provide a “not-to-exceed” price by mid-Feb and a turn-key price by the end of March. |  | 840000 | Yes | Yes
Professional Engineering Services Agreement (B&V/FPRP) | Contract to review the current transmission system and prepare an analysis of the required upgrades |  | 70000 | Yes | Yes
Other Development Agreements (Secondary)
Tank Engineering & Management Agreement | Design and specification work for tank demolition | 16500 |  | Yes | No
Thomas Lucido & Associates Agreement | Relates to site plan and landscaping | 9500 |  | Yes | Yes
LBFH, Inc. Agreements | Engineering services for air and building permits, site plans and other required permits or approvals, surveying | 44800 |  | Yes | No
[To what does this line relate?] |  | 16500
Environmental Consulting & Technology Agreement | Consulting work for the air and building permit applications | 32500 |  | Yes | No
REG Agreement | Architectural designs incorporated for building aesthetics |  |  | Yes | No
|  |  |  | Yes | No
Katz Kutter (Florida Legal Counsel) Engagement Letter | Legal review of the ramifications of the Florida Siting Act |  |  | No | No
Andrews & Kurth Engagement Letter | Preparation and review of all of the definitive documents (Participation, Steam, O&M, Ground Lease, etc.) | 420000 | 330000 | No | No
Law Gibb DSA and Tasking Letter | Conducted Phase I, Phase II environmental review; Reviewed and prepared a remediation plan to define FPUA clean-up obligation |  |  | No | No
Greenburg Traurig (Florida Land Use Counsel) Engagement Letter | Legal assistance regarding site plans and other city approvals and title matters |  |  | No | No
Culpepper [No agreement found] | Preliminary engineering, replaced by LBFH |  |  | No | No
FP&L Interconnection Study Agreement (FP&L/FPRP) | Cost study for required interconnection upgrades |  |  | No | No
| Totals | 539800 | 2121000